## Summary
\\WorleyParsons.com\CA\Data\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option A-11032014.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-A | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 6927000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 2692000
| 3.01 | EPCM COSTS |  | 962000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 10581000
| 4.01 | CONTINGENCY | 25% | 2645000
|  | TOTAL COSTS |  | 13226000

## Detail Costs
\\WorleyParsons.com\CA\Data\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option A-11032014.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-A | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW
|  | MTO No.: |  | REVISION: | 0
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Edmonton to Dawson City 2,519km. Dawson City to Site approx 110km. 2ea D9 dozer , 1ea grader, 1ea 70ton excavator, 2ea wheel loader, 8ea 50ton rock truck. | 14 | EA |  | 0 | 0 |  | 0 | 18723.36 | 262127.04 |  | 0 |  | 0 | 262127.04 | 25% | 65531.76 | 327658.8
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Major Road Improvements | 15km |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.05 |  |  | Clear & grub | Medium | 9 | HA |  | 0 | 0 |  | 0 | 11877.51 | 106897.59 |  | 0 |  | 0 | 106897.59 | 25% | 26724.3975 | 133621.9875
1.06 |  |  | Road embankment widening, 3m | Cut to fill existing shoulder. Approx 8M3 / LM. | 120000 | M3 |  | 0 | 0 |  | 0 | 4.63 | 555600 |  | 0 |  | 0 | 555600 | 25% | 138900 | 694500
1.07 |  |  | Re-grade road sub-base | Av. 150mm dp x 5m wide | 11250 | M3 |  | 0 | 0 |  | 0 | 12.57 | 141412.5 |  | 0 |  | 0 | 141412.5 | 25% | 35353.125 | 176765.625
1.08 |  |  | Gravel resurfacing, 100mm thk x 8m wide | Drill & blast, crushing, load & haul and place. | 12000 | M3 |  | 0 | 0 |  | 0 | 160.88 | 1930560 |  | 0 |  | 0 | 1930560 | 25% | 482640 | 2413200
1.09 |  |  | Bridge construction | 15m clear span x 11m w. Supply & install. | 1 | LS |  | 0 | 0 |  | 0 | 889246.4788 | 889246.4788 |  | 0 |  | 0 | 889246.4788 | 25% | 222311.6197 | 1111558.0985
1.1 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.11 |  |  | Bulk Earthworks |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.12 |  |  | Waste dump to porcupine pit |  | 50000 | M3 |  | 0 | 0 |  | 0 | 4.9 | 245000 |  | 0 |  | 0 | 245000 | 25% | 61250 | 306250
1.13 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.14 |  |  | Channel Armouring |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.15 |  |  | Rip-rap - 800 mm dia. | Drill & blast, screen & sort, load & haul to site, double handling and place. | 3000 | M3 |  | 0 | 0 |  | 0 | 141.27 | 423810 |  | 0 |  | 0 | 423810 | 25% | 105952.5 | 529762.5
1.16 |  |  | Granular filter | Drill & blast, crushing, load & haul and place. | 2200 | M3 |  | 0 | 0 |  | 0 | 157.35 | 346170 |  | 0 |  | 0 | 346170 | 25% | 86542.5 | 432712.5
1.17 |  |  | Waste rock | Load, haul, place & compact | 3000 | M3 |  | 0 | 0 |  | 0 | 10.12 | 30360 |  | 0 |  | 0 | 30360 | 25% | 7590 | 37950
1.18 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.19 |  |  | Water Diversion |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.2 |  |  | Aquadam - supply & install | 6' x 100' lg | 1 | EA |  | 0 | 0 |  | 0 | 26000 | 26000 |  | 0 |  | 0 | 26000 | 25% | 6500 | 32500
1.21 |  |  | 610mm HDPE DR21 pipe | Trench 1.6m dp, BF 1m cover, supply & install. | 500 | LM |  | 0 | 0 |  | 0 | 980.0724 | 490036.2 |  | 0 |  | 0 | 490036.2 | 25% | 122509.05 | 612545.25
1.22 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.23 |  |  | Support Equipment |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.24 |  |  | Shop truck | 1ea | 60.8 | DY |  | 0 | 0 |  | 0 | 300 | 18240 |  | 0 |  | 0 | 18240 | 25% | 4560 | 22800
1.25 |  |  | Temp maintenance shop | 1ea | 1 | LS |  | 0 | 0 |  | 0 | 15000 | 15000 |  | 0 |  | 0 | 15000 | 25% | 3750 | 18750
1.26 |  |  | Shop trailer | 1ea | 2 | MO |  | 0 | 0 |  | 0 | 2000 | 4000 |  | 0 |  | 0 | 4000 | 25% | 1000 | 5000
1.27 |  |  | Fuel bowser | 1ea | 2 | MO |  | 0 | 0 |  | 0 | 5000 | 10000 |  | 0 |  | 0 | 10000 | 25% | 2500 | 12500
1.28 |  |  | Pick-up trucks | 6ea | 60.8 | DY |  | 0 | 0 |  | 0 | 900 | 54720 |  | 0 |  | 0 | 54720 | 25% | 13680 | 68400
1.29 |  |  | Portable light towers | 6ea | 2 | MO |  | 0 | 0 |  | 0 | 22440 | 44880 |  | 0 |  | 0 | 44880 | 25% | 11220 | 56100
1.3 |  |  | Generator | 6ea | 2 | MO |  | 0 | 0 |  | 0 | 7920 | 15840 |  | 0 |  | 0 | 15840 | 25% | 3960 | 19800
1.31 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.32 |  |  | Support Labour | *During Road Improvements, Quarry Development & Creek Stabiliztion Work. |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.33 |  |  | Heavy duty mechanic | 1ea/shift | 60.8 | DY |  | 0 | 0 |  | 0 | 2640 | 160512 |  | 0 |  | 0 | 160512 | 25% | 40128 | 200640
1.34 |  |  | Welder | 1ea/shift | 60.8 | DY |  | 0 | 0 |  | 0 | 2640 | 160512 |  | 0 |  | 0 | 160512 | 25% | 40128 | 200640
1.35 |  |  | Labourer | 2ea/shift | 121.6 | DY |  | 0 | 0 |  | 0 | 1800 | 218880 |  | 0 |  | 0 | 218880 | 25% | 54720 | 273600
1.36 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.37 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.38 |  |  | Equipment washdown facilites | 1ea - 80'x120' temprorary building , 300mm SOG, 4ea - 4.5 GPM pressure washers w/ 600Gal tanks, 4man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 733293.728 | 733293.728 |  | 0 |  | 0 | 733293.728 | 25% | 183323.432 | 916617.16
1.39 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 14000 | 14000 |  | 0 |  | 0 | 14000 | 25% | 3500 | 17500
1.4 |  |  | PPE; respirators, overalls |  | 50 | EA |  | 0 | 0 |  | 0 | 500 | 25000 |  | 0 |  | 0 | 25000 | 25% | 6250 | 31250
1.41 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.42 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.43 |  |  | Fuel truck & driver | 27,000 liter tanker | 7.3247 | LD |  | 0 | 0 |  | 0 | 685.6 | 5021.8169 |  | 0 |  | 0 | 5021.8169 | 25% | 1255.4542 | 6277.2711
1.44 |  |  |  | *fuel included in all-in rates. | 197767 | liters |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.45 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.46 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 6927119.3537 |  | 0 | 0% | 0 | 6927119.3537 | 25% | 1731779.8384 | 8658899.1921
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | 40 man temporary camp x 2.75mo. | 3344 | MDY |  | 0 | 0 |  | 0 | 557.93 | 1865717.92 |  | 0 |  | 0 | 1865717.92 | 25% | 466429.48 | 2332147.4
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 3% |  |  | 0 | 0 |  | 0 | 6927119.3537 | 207813.5806 |  | 0 |  | 0 | 207813.5806 | 25% | 51953.3952 | 259766.9758
2.03 |  |  | SNOW REMOVAL | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.04 |  |  | ROAD MAINTENANCE | 1ea Grader 12hrs/day | 75 | DY |  | 0 | 0 |  | 0 | 2677.2 | 200790 |  | 0 |  | 0 | 200790 | 25% | 50197.5 | 250987.5
2.05 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.08 |  |  | CONTRACTOR LOA AND TRAVEL | Edm to Dawson City charter flight + DC to Site by charter bus. 1 flight/man every two weeks. | 90 | Round Trip |  | 0 | 0 |  | 0 | 1144 | 102960 |  | 0 |  | 0 | 102960 | 25% | 25740 | 128700
2.09 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.1 |  |  | TRANSPORTATION AND FREIGHT | HDPE pipe & aquadam. | 4 | LD |  | 0 | 0 |  | 0 | 9361.68 | 37446.72 |  | 0 |  | 0 | 37446.72 | 25% | 9361.68 | 46808.4
2.11 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.14 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 6927119.3537 | 138542.3871 |  | 0 |  | 0 | 138542.3871 | 25% | 34635.5968 | 173177.9838
2.15 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS |  | 2% |  |  | 0 | 0 |  | 0 | 6927119.3537 | 138542.3871 |  | 0 |  | 0 | 138542.3871 | 25% | 34635.5968 | 173177.9838
2.16 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.17 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 2691812.9948 |  | 0 | 0% | 0 | 2691812.9948 | 25% | 672953.2487 | 3364766.2434
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 9618932.3484 | 961893.2348 |  | 0 |  | 0 | 961893.2348 | 25% | 240473.3087 | 1202366.5436
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 961893.2348 |  | 0 | 0% | 0 | 961893.2348 | 25% | 240473.3087 | 1202366.5436
| TOTAL | [16 empty] | 10580825.5833 | 25% | 2645206.3958 | 13226031.9791

## Pivot Table
Sum of labour cost |  |  |  | Labour Type List Source
type of labour | % labour | Total |  | Camp Op & Maintenance
Camp Op & Maintenance |  | 373143.584 |  | Engineering
Engineering |  | 1080049.4376 |  | Equip Maintenance
Equip Maintenance |  | 539904 |  | Equip Op
Equip Op |  | 1295917.9047 |  | Equip Op / Equip Maintenance
Equip Op / Equip Maintenance |  | 13000 |  | Equip Op / Labour
Equip Op / Labour |  | 20781.3581 |  | Equip Op / Welders / Labour
Equip Op / Welders / Labour |  | 293451.338 |  | Labour
Labour |  | 318347.4728 |  | Truck Driver
Truck Driver |  | 107863.9061
(blank) |  | 0
Grand Total |  | 4042459.0013
Sum of labour cost
| % labour of |  | % labour of
type of labour | all-in rate | Total | total labour
Camp Op & Maintenance |  | 373143.584 | 9.231%
Engineering |  | 1080049.4376 | 26.72%
Equip Maintenance |  | 539904 | 13.36%
Equip Op |  | 1295917.9047 | 32.06%
Equip Op / Equip Maintenance |  | 13000 | 0.3216%
Equip Op / Labour |  | 20781.3581 | 0.5141%
Equip Op / Welders / Labour |  | 293451.338 | 7.259%
Labour |  | 318347.4728 | 7.875%
Truck Driver |  | 107863.9061 | 2.668%
Grand Total |  | 4042459.0013 | 100%
Sum of labour cost
type of labour |  | Total | labour % of total labour cost
Equip Op |  | 1431489.1189 | 35.41%
Labour |  | 504808.9546 | 12.49%
Truck Driver |  | 107863.9061 | 2.668%
Equip Maintenance |  | 545104 | 13.48%
Camp Op & Maintenance |  | 373143.584 | 9.231%
Engineering |  | 1080049.4376 | 26.72%
Total |  | 4042459.0013 | 100%
* Contingency not included.