## Summary
\\WorleyParsons.com\CA\Data\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option B2-11032014.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-B2 | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 18456000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 10018000
| 3.01 | EPCM COSTS |  | 2847000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 31321000
| 4.01 | CONTINGENCY | 25% | 7830000
|  | TOTAL COSTS |  | 39151000

## Detail Costs
\\WorleyParsons.com\CA\Data\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option B2-11032014.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-B2 | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW
|  | MTO No.: |  | REVISION: | 0
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Edmonton to Dawson City 2,519km. Dawson City to Site approx 110km. 1ea D9 dozer , 1ea grader, 1ea 70ton excavator, 1ea wheel loader, 8ea 50ton rock truck, 1ea packer. Second Season Remob: 2ea PC2000, 5ea 777, 1ea D9, 2ea 70ton excavator, 3ea wheel loader | 26 | EA |  | 0 | 0 |  | 0 | 29170.3754 | 758429.76 |  | 0 |  | 0 | 758429.76 | 25% | 189607.44 | 948037.2
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Major Road Improvements | 15km |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.05 |  |  | Clear & grub | Medium | 9 | HA |  | 0 | 0 |  | 0 | 11877.51 | 106897.59 |  | 0 |  | 0 | 106897.59 | 25% | 26724.3975 | 133621.9875
1.06 |  |  | Road embankment widening, 3m | Cut to fill existing shoulder. Approx 8M3 / LM. | 120000 | M3 |  | 0 | 0 |  | 0 | 4.63 | 555600 |  | 0 |  | 0 | 555600 | 25% | 138900 | 694500
1.07 |  |  | Re-grade road sub-base | Av. 150mm dp x 5m wide | 11250 | M3 |  | 0 | 0 |  | 0 | 12.57 | 141412.5 |  | 0 |  | 0 | 141412.5 | 25% | 35353.125 | 176765.625
1.08 |  |  | Gravel resurfacing, 100mm thk x 8m wide | Drill & blast, crushing, load & haul and place. | 12000 | M3 |  | 0 | 0 |  | 0 | 159.23 | 1910760 |  | 0 |  | 0 | 1910760 | 25% | 477690 | 2388450
1.09 |  |  | Bridge construction | 15m clear span x 11m w. Supply & install. | 1 | LS |  | 0 | 0 |  | 0 | 889246.4788 | 889246.4788 |  | 0 |  | 0 | 889246.4788 | 25% | 222311.6197 | 1111558.0985
1.1 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.11 |  |  | Bulk Earthworks |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.12 |  |  | New Channel to Channel Fill | Equip Set 2 | 600000 | M3 |  | 0 | 0 |  | 0 | 3.95 | 2370000 |  | 0 |  | 0 | 2370000 | 25% | 592500 | 2962500
1.13 |  |  | Waste Dump to Channel Fill | 1ea-D8 w/ 345 ex; push top of existing channel to fill channel bed. | 100000 | M3 |  | 0 | 0 |  | 0 | 5.22 | 522000 |  | 0 |  | 0 | 522000 | 25% | 130500 | 652500
1.14 |  |  | Channel to Porupine Pit | Equip Set 1 | 900000 | M3 |  | 0 | 0 |  | 0 | 4.9 | 4410000 |  | 0 |  | 0 | 4410000 | 25% | 1102500 | 5512500
1.15 |  |  | Waste Dump to Porcupine Pit | Equip Set 1 | 350000 | M3 |  | 0 | 0 |  | 0 | 4.9 | 1715000 |  | 0 |  | 0 | 1715000 | 25% | 428750 | 2143750
1.16 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.17 |  |  | Access Road Construction |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.18 |  |  | Gravel resurfacing, 300mm thk x 6m wide | Drill & blast, crushing, load & haul and place. | 1350 | M3 |  | 0 | 0 |  | 0 | 159.23 | 214960.5 |  | 0 |  | 0 | 214960.5 | 25% | 53740.125 | 268700.625
1.19 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.2 |  |  | Channel Armouring |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.21 |  |  | Rip-rap - 500mm dia. | Drill & blast, screen & sort, load & haul to site, double handling and place. | 6525 | M3 |  | 0 | 0 |  | 0 | 125.11 | 816342.75 |  | 0 |  | 0 | 816342.75 | 25% | 204085.6875 | 1020428.4375
1.22 |  |  | Rip-rap - 800 mm dia. | Drill & blast, screen & sort, load & haul to site, double handling and place. | 7100 | M3 |  | 0 | 0 |  | 0 | 135.28 | 960488 |  | 0 |  | 0 | 960488 | 25% | 240122 | 1200610
1.23 |  |  | Granular filter | Drill & blast, crushing, load & haul and place. | 5200 | M3 |  | 0 | 0 |  | 0 | 155.7 | 809640 |  | 0 |  | 0 | 809640 | 25% | 202410 | 1012050
1.24 |  |  | Geotextile 10oz | Under cobble layer. | 9700 | M2 |  | 0 | 0 |  | 0 | 3.62 | 35114 |  | 0 |  | 0 | 35114 | 25% | 8778.5 | 43892.5
1.25 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.26 |  |  | Support Equipment |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.27 |  |  | Shop truck | 1ea | 212.8 | DY |  | 0 | 0 |  | 0 | 300 | 63840 |  | 0 |  | 0 | 63840 | 25% | 15960 | 79800
1.28 |  |  | Temp maintenance shop | 1ea | 1 | LS |  | 0 | 0 |  | 0 | 15000 | 15000 |  | 0 |  | 0 | 15000 | 25% | 3750 | 18750
1.29 |  |  | Shop trailer | 1ea | 7 | MO |  | 0 | 0 |  | 0 | 2000 | 14000 |  | 0 |  | 0 | 14000 | 25% | 3500 | 17500
1.3 |  |  | Fuel bowser | 1ea | 7 | MO |  | 0 | 0 |  | 0 | 5000 | 35000 |  | 0 |  | 0 | 35000 | 25% | 8750 | 43750
1.31 |  |  | Pick-up trucks | 6ea | 212.8 | DY |  | 0 | 0 |  | 0 | 900 | 191520 |  | 0 |  | 0 | 191520 | 25% | 47880 | 239400
1.32 |  |  | Portable light towers | 6ea | 7 | MO |  | 0 | 0 |  | 0 | 22440 | 157080 |  | 0 |  | 0 | 157080 | 25% | 39270 | 196350
1.33 |  |  | Generator | 6ea | 7 | MO |  | 0 | 0 |  | 0 | 7920 | 55440 |  | 0 |  | 0 | 55440 | 25% | 13860 | 69300
1.34 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.35 |  |  | Support Labour | *During Road Improvements, Quarry Development & Creek Stabiliztion Work. |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.36 |  |  | Heavy duty mechanic | 1ea/shift | 91.2 | DY |  | 0 | 0 |  | 0 | 2640 | 240768 |  | 0 |  | 0 | 240768 | 25% | 60192 | 300960
1.37 |  |  | Welder | 1ea/shift | 91.2 | DY |  | 0 | 0 |  | 0 | 2640 | 240768 |  | 0 |  | 0 | 240768 | 25% | 60192 | 300960
1.38 |  |  | Labourer | 2ea/shift | 182.4 | DY |  | 0 | 0 |  | 0 | 1800 | 328320 |  | 0 |  | 0 | 328320 | 25% | 82080 | 410400
1.39 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.4 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.41 |  |  | Equipment washdown facilites | 1ea - 80'x120' temprorary building , 300mm SOG, 4ea - 4.5 GPM pressure washers w/ 600Gal tanks, 4man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 797158.048 | 797158.048 |  | 0 |  | 0 | 797158.048 | 25% | 199289.512 | 996447.56
1.42 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 26000 | 26000 |  | 0 |  | 0 | 26000 | 25% | 6500 | 32500
1.43 |  |  | PPE; respirators, overalls |  | 60 | EA |  | 0 | 0 |  | 0 | 500 | 30000 |  | 0 |  | 0 | 30000 | 25% | 7500 | 37500
1.44 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.45 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.46 |  |  | Fuel truck & driver | 27,000 liter tanker | 65.6312 | LD |  | 0 | 0 |  | 0 | 685.6 | 44996.7406 |  | 0 |  | 0 | 44996.7406 | 25% | 11249.1851 | 56245.9257
1.47 |  |  |  | *fuel included in all-in rates. | 1772042 | liters |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.48 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.49 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 18455782.3674 |  | 0 | 0% | 0 | 18455782.3674 | 25% | 4613945.5918 | 23069727.9592
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | 60 man temporary camp x 6.75mo. | 12312 | MDY |  | 0 | 0 |  | 0 | 434.86 | 5353996.32 |  | 0 |  | 0 | 5353996.32 | 25% | 1338499.08 | 6692495.4
2.02 |  |  | TEMPORARY CAMP - MAINTENANCE | Winterize & Rental | 10 | MO |  | 0 | 0 |  |  | 129070 | 1290700 |  | 0 |  | 0 | 1290700 | 25% | 322675 | 1613375
2.03 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES | n/a | 3% |  |  | 0 | 0 |  | 0 | 18455782.3674 | 553673.471 |  | 0 |  | 0 | 553673.471 | 25% | 138418.3678 | 692091.8388
2.04 |  |  | SNOW REMOVAL | n/a |  |  |  | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0
2.05 |  |  | ROAD MAINTENANCE | 1ea Grader 12hrs/day | 212.8 | DY |  | 0 | 0 |  | 0 | 2677.2 | 569708.16 |  | 0 |  | 0 | 569708.16 | 25% | 142427.04 | 712135.2
2.06 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.08 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.09 |  |  | CONTRACTOR LOA AND TRAVEL | Edm to Dawson City charter flight (42 pass) + DC to Site by charter bus. 1 flight per week for 6.75 months. | 27 | Round Trip |  | 0 | 0 |  | 0 | 56000 | 1512000 |  | 0 |  | 0 | 1512000 | 25% | 378000 | 1890000
2.1 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.11 |  |  | TRANSPORTATION AND FREIGHT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.14 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.15 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 18455782.3674 | 369115.6473 |  | 0 |  | 0 | 369115.6473 | 25% | 92278.9118 | 461394.5592
2.16 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS |  | 2% |  |  | 0 | 0 |  | 0 | 18455782.3674 | 369115.6473 |  | 0 |  | 0 | 369115.6473 | 25% | 92278.9118 | 461394.5592
2.17 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.18 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 10018309.2457 |  | 0 | 0% | 0 | 10018309.2457 | 25% | 2504577.3114 | 12522886.5571
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 28474091.6131 | 2847409.1613 |  | 0 |  | 0 | 2847409.1613 | 25% | 711852.2903 | 3559261.4516
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 2847409.1613 |  | 0 | 0% | 0 | 2847409.1613 | 25% | 711852.2903 | 3559261.4516
| TOTAL | [16 empty] | 31321500.7744 | 25% | 7830375.1936 | 39151875.968

## Basis of Estimate
BASIS OF ESTIMATE
| PROJECT DETAILS: | Civil Earthworks; bulk excavation, creek stabilization, quarry development and road improvements.
| CLIENT: | Assessment and Abandoned Mines
| PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-B2
| PROJ # (GBS): | 307071-00895
DOC NUMBER:
| ACCURACY LEVEL: | +/-50%
| DATE: | 2014-03-28
SCOPE OF ESTIMATE:
Major civil earthworks to excavate and relocate rockslide waste, excavate new channel and fill existing channel. Excess excavated material will be relocated to existing spoil pit. New channel will be armoured with rip-rap. Eight gabion drop structures will also be constructed within the new channel.
REFERENCE DOCUMENTS:
- Clinton Creek Option B Summary
- Site Plan - Drawing 1
- Option CC-2 Plan & Profile Armoured Channel Over Waste Rock - Drawing 08
- Option CC-2 Sections Armoured Channel Over Waste Rock - Drawing 09
- Proposed Waster Rock Dump Geometry For Alternative Creek Channel Alignment - Drawing 07
KEY QUALIFICATIONS
- All work will be performed in 12 hour double shifts over 7 months, no down time has been factored into costs: Camp mobilization & set-up, site access road improvements, quarry development, crushing and stockpiling aggregates to site will begin in the summer of the first year. In spring of the second year the bulk excavations will commence along with the eight drop structures and armouring the new channel.
- The camp will be winterized and remain on site over the winter.
Utilized Major Equipment:
- 1ea - track drill, 1ea - 70ton excavator, 8ea - 25ton rock trucks.
- 1ea - crusher jaw, 1ea - cone crusher, 1ea - screener.
- 1ea - grader, 1ea - 30ton packer, 4ea - wheel loader, 1ea - water truck.
- 5ea - 90ton rock trucks, 2ea - PC2000 Shovel, 2ea - D9 dozers.
- All required aggregates will be produced by a mobile crushing plant at an off-site quarrry approximately 15km from site and off existing site road.
- Last 15km of site road will require improvements; clearing & grubbing, widening and resurfacing.
- Direct haul roads from excavations and fill areas. No allowances for switchbacks or extensive haul road developments.
- All work will be performed by non-local workforce.
- All heavy equipment, camp and facilities will be able to cross the river via existing ferry or ice bridge.
- 60 man camp has been allowed for to accommodate all contractor, engineering and owner field personnel for 7 month construction period.
- All equipment, camp and facilities will be able to be demobilized from site after completion of the project.
ASSUMPTIONS OF COST ESTIMATE
- All equipment mobilized to site from Edmonton, AB through Dawson City.
- Suitable rock for required aggregates will be available approximately 15km from site and off existing road.
- Drill and blasting costs associated with rip-rap material produced from off-site quarry is assumed to be granite material with a bulk density of 2.7 t/m3 with no swell factor.
- Powder Factor of 0.4 kg/t assumed adequate to blast material to for rip rap sizes between 200 to 800 mm in diameter.
- Swell factor of 30% for all materials excavated applied along with 90% fill factor for buckets.
- General equipment mechanical availibility of 89%, consuming 90% of net labour operating hours.
- 88.4% labour effeciency included into net productivity time for operators after incorporating scheduled delays (shift change, inspection and breaks).
- Sufficient site preparations have been completed previously to accommodate camp and site facilities.
EXCLUSIONS FROM COST ESTIMATE
- Clearing & grubbing over waste dump excavation area.
- Dewatering
- Demolition, removal, disposal and/or relocation of existing structures and facilities.
- Traffic safety and control to existing site road and road improvements.
- Lost time to severe weather or force majeure.
- Costs related to environmental habitat compensation and social impacts.
- Extended periods of industrial / labour unrest.
- First nations contracts or work agreements.
- All permitting and associated costs.
- Construction insurance
- Escalation
- All Owners costs
- All taxes and duties
QUANTITY DERIVATION
- Material take-offs provided by engineering discipline(s) and the estimator.
COST BASIS
- Earthwork rates derived from minning models and built-up earthwork calculations utiliziting BC Road Builder rates and historical data.
- Capital Costs for bulk earthwork and drill & blast rates were estimated using average investment method at a rate of 8%. These equipment prices were based on dated quotes or found online.
- Rates include all labour and equipment costs to operate and maintain equipment. Including all contractor overhead, profit and indirects; supervision, survey, support equipment.
- Diesel fuel rate of $1.60/liter allowed for all earthwork based on Yukon Government - Energy, Mines and Resources, surveyed October 30, 2013.
- Fuel consumption rates and maintainence costs obtained from historic data or interpolated.
LABOUR RATES
- Average operator rate of approximately $50/hr allowed for within all earthwork unit costs. Based on AB CLRA Collective Agreements (2011 - 2015).
- Work will commence using double 12hr shifts, working 14 days on with 7 days off.
INDIRECTS:
- Contractor indirect costs have been included within all direct costs.
- A 60 man temporary camp has been allowed for the duration of the work. Camp costs were derived from quotes and a temporary camp of similar size from historical data base and estimates.
- Chartered flights from Edmonton, AB to Dawson City have been included for a 30 man turnaround once per week for 7 months. And additional allowance has also been inlcuded to charter buses from Dawson City to site once per week.
- Grader and dozer for snow removal and road maintenance are included for 12 hours per day, twice per week over a 6 month period.
- An allowance of 3% of the total direct cost has been included for contractor Temporary Facilities.
- An allowance of 2% of the total direct cost has been included for Environmental Monitoring and Testing.
- An allowance of 2% of the total direct cost has been included for potential Geotechnical Investigations and Recommendations.

## Pivot table
Sum of labour cost
type of labour | % labour | Total
Camp Op & Maintenance |  | 1070799.264
Engineering |  | 3143565.406
Equip Maintenance |  | 809856
Equip Op |  | 1990637.01
Equip Op / Equip Maintenance |  | 2449070
Equip Op / Labour |  | 64535
Equip Op / Welders / Labour |  | 293451.338
Labour |  | 134977.8099
Truck Driver |  | 292448.4603
(blank) |  | 0
Grand Total |  | 10249340.2882
Sum of labour cost
| % labour of |  | % labour of
type of labour | all-in rate | Total | total labour
Camp Op & Maintenance |  | 1070799.264 | 10.45%
Engineering |  | 3143565.406 | 30.67%
Equip Maintenance |  | 809856 | 7.902%
Equip Op |  | 1990637.01 | 19.42%
Equip Op / Equip Maintenance |  | 2449070 | 23.89%
Equip Op / Labour |  | 64535 | 0.6297%
Equip Op / Welders / Labour |  | 293451.338 | 2.863%
Labour |  | 134977.8099 | 1.317%
Truck Driver |  | 292448.4603 | 2.853%
Grand Total |  | 10249340.2882 | 100%
Sum of labour cost
type of labour |  | Total | labour % of total labour cost
Equip Op |  | 3609727.0452 | 35.22%
Labour |  | 343316.1127 | 3.35%
Truck Driver |  | 292448.4603 | 2.853%
Equip Maintenance |  | 1789484 | 17.46%
Camp Op & Maintenance |  | 1070799.264 | 10.45%
Engineering |  | 3143565.406 | 30.67%
Total |  | 10249340.2882 | 100%
* Contingency not included.