## Summary
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option C-11032014.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-C | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 8025000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 4963000
| 3.01 | EPCM COSTS |  | 1299000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 14287000
| 4.01 | CONTINGENCY | 25% | 3572000
|  | TOTAL COSTS |  | 17859000

## Detail Costs
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option C-11032014.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-C | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW
|  | MTO No.: |  | REVISION: | 0
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Edmonton to Dawson City 2,519km. Dawson City to Site approx 110km. 1ea-345, 1ea-D8, 7ea-40ton rock truck, 1ea-grader, 1ea-packer. Second Season Remob: 2ea-wheel loaders, 2ea-345 | 15 | EA |  | 0 | 0 |  | 0 | 18723.36 | 280850.4 |  | 0 |  | 0 | 280850.4 | 25% | 70212.6 | 351063
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Major Road Improvements | 15km |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.05 |  |  | Clear & grub | Medium | 9 | HA |  | 0 | 0 |  | 0 | 11877.51 | 106897.59 |  | 0 |  | 0 | 106897.59 | 25% | 26724.3975 | 133621.9875
1.06 |  |  | Road embankment widening, 3m | Cut to fill existing shoulder. Approx 8M3 / LM. | 120000 | M3 |  | 0 | 0 |  | 0 | 4.63 | 555600 |  | 0 |  | 0 | 555600 | 25% | 138900 | 694500
1.07 |  |  | Re-grade road sub-base | Av. 150mm dp x 5m wide | 11250 | M3 |  | 0 | 0 |  | 0 | 12.57 | 141412.5 |  | 0 |  | 0 | 141412.5 | 25% | 35353.125 | 176765.625
1.08 |  |  | Gravel resurfacing, 100mm thk x 8m wide | Drill & blast, crushing, load & haul and place. | 12000 | M3 |  | 0 | 0 |  | 0 | 123.3 | 1479600 |  | 0 |  | 0 | 1479600 | 25% | 369900 | 1849500
1.09 |  |  | Bridge construction | 15m clear span x 11m w. Supply & install. | 1 | LS |  | 0 | 0 |  | 0 | 889246.4788 | 889246.4788 |  | 0 |  | 0 | 889246.4788 | 25% | 222311.6197 | 1111558.0985
1.1 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.11 |  |  | Bulk Earthworks |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.12 |  |  | Waste dump to channel fill | 1ea-D8 w/ 345 ex; push top of existing channel to fill channel bed. | 25000 | M3 |  | 0 | 0 |  | 0 | 5.22 | 130500 |  | 0 |  | 0 | 130500 | 25% | 32625 | 163125
1.13 |  |  | Waste dump to porcupine pit | Equip Set 1 | 150000 | M3 |  | 0 | 0 |  | 0 | 4.9 | 735000 |  | 0 |  | 0 | 735000 | 25% | 183750 | 918750
1.14 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.15 |  |  | Access Road Construction |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.16 |  |  | Gravel resurfacing, 300mm thk x 6m wide | Drill & blast, crushing, load & haul and place. | 990 | M3 |  | 0 | 0 |  | 0 | 156.92 | 155350.8 |  | 0 |  | 0 | 155350.8 | 25% | 38837.7 | 194188.5
1.17 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.18 |  |  | Gabion Drop Structures |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.19 |  |  | Gabion baskets (3m lg x 1m dp x 0.5m h) | Supply, load, haul, assemble, place | 1250 | EA |  | 0 | 0 |  | 0 | 638.72 | 798400 |  | 0 |  | 0 | 798400 | 25% | 199600 | 998000
1.2 |  |  | Gabion rock - 100 to 200 mm dia. | (8 drop structures) Drill & blast, screen & sort, load & haul to site, double handling and place. | 1850 | M3 |  | 0 | 0 |  | 0 | 111.51 | 206293.5 |  | 0 |  | 0 | 206293.5 | 25% | 51573.375 | 257866.875
1.21 |  |  | Rip-rap - 300 mm dia. | Drill & blast, screen & sort, load & haul to site, double handling and place. | 1100 | M3 |  | 0 | 0 |  | 0 | 121.68 | 133848 |  | 0 |  | 0 | 133848 | 25% | 33462 | 167310
1.24 |  |  | Geotextile 10oz | Under cobble layer. | 5300 | M2 |  | 0 | 0 |  | 0 | 3.62 | 19186 |  | 0 |  | 0 | 19186 | 25% | 4796.5 | 23982.5
1.22 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.23 |  |  | Water Diversion |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.24 |  |  | Aquadam - supply & install | 6' x 100' lg. | 1 | EA |  | 0 | 0 |  | 0 | 26000 | 26000 |  | 0 |  | 0 | 26000 | 25% | 6500 | 32500
1.25 |  |  | 610mm HDPE DR21 pipe | Trench 1.6m dp, BF 1m cover, supply & install. | 900 | LM |  | 0 | 0 |  | 0 | 980.0724 | 882065.16 |  | 0 |  | 0 | 882065.16 | 25% | 220516.29 | 1102581.45
1.26 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.27 |  |  | Support Equipment |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.28 |  |  | Shop truck | 1ea | 60.8 | DY |  | 0 | 0 |  | 0 | 300 | 18240 |  | 0 |  | 0 | 18240 | 25% | 4560 | 22800
1.29 |  |  | Temp maintenance shop | 1ea | 1 | LS |  | 0 | 0 |  | 0 | 15000 | 15000 |  | 0 |  | 0 | 15000 | 25% | 3750 | 18750
1.3 |  |  | Shop trailer | 1ea | 2 | MO |  | 0 | 0 |  | 0 | 2000 | 4000 |  | 0 |  | 0 | 4000 | 25% | 1000 | 5000
1.31 |  |  | Fuel bowser | 1ea on-site | 2 | MO |  | 0 | 0 |  | 0 | 5000 | 10000 |  | 0 |  | 0 | 10000 | 25% | 2500 | 12500
1.32 |  |  | Pick-up trucks | 6ea | 60.8 | DY |  | 0 | 0 |  | 0 | 900 | 54720 |  | 0 |  | 0 | 54720 | 25% | 13680 | 68400
1.33 |  |  | Portable light towers | 6ea | 2 | MO |  | 0 | 0 |  | 0 | 22440 | 44880 |  | 0 |  | 0 | 44880 | 25% | 11220 | 56100
1.34 |  |  | Generator | 6ea | 2 | MO |  | 0 | 0 |  | 0 | 7920 | 15840 |  | 0 |  | 0 | 15840 | 25% | 3960 | 19800
1.35 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.36 |  |  | Support Labour | *During Road Improvements, Quarry Development & Creek Stabiliztion Work. |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.37 |  |  | Heavy duty mechanic | 1ea/shift | 60.8 | DY |  | 0 | 0 |  | 0 | 2640 | 160512 |  | 0 |  | 0 | 160512 | 25% | 40128 | 200640
1.38 |  |  | Welder | 1ea/shift | 60.8 | DY |  | 0 | 0 |  | 0 | 2640 | 160512 |  | 0 |  | 0 | 160512 | 25% | 40128 | 200640
1.39 |  |  | Labourer | 2ea/shift | 121.6 | DY |  | 0 | 0 |  | 0 | 1800 | 218880 |  | 0 |  | 0 | 218880 | 25% | 54720 | 273600
1.4 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.37 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.38 |  |  | Equipment washdown facilites | 1ea - 80'x120' temprorary building , 300mm SOG, 4ea - 4.5 GPM pressure washers w/ 600Gal tanks, 4man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 733293.728 | 733293.728 |  | 0 |  | 0 | 733293.728 | 25% | 183323.432 | 916617.16
1.39 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 15000 | 15000 |  | 0 |  | 0 | 15000 | 25% | 3750 | 18750
1.4 |  |  | PPE; respirators, overalls |  | 50 | EA |  | 0 | 0 |  | 0 | 500 | 25000 |  | 0 |  | 0 | 25000 | 25% | 6250 | 31250
1.41 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.41 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.42 |  |  | Fuel truck & driver | 27,000 liter tanker | 13 | LD |  | 0 | 0 |  | 0 | 685.6 | 8912.8 |  | 0 |  | 0 | 8912.8 | 25% | 2228.2 | 11141
1.43 |  |  |  | *fuel included in all-in rates. | 329027 | liters |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.44 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.45 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 8025040.9568 |  | 0 | 0% | 0 | 8025040.9568 | 25% | 2006260.2392 | 10031301.196
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | 40 man temporary camp x 5mo. | 6080 | MDY |  | 0 | 0 |  | 0 | 534.8 | 3251584 |  | 0 |  | 0 | 3251584 | 25% | 812896 | 4064480
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 3% |  |  | 0 | 0 |  | 0 | 8025040.9568 | 240751.2287 |  | 0 |  | 0 | 240751.2287 | 25% | 60187.8072 | 300939.0359
2.03 |  |  | SNOW REMOVAL | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.04 |  |  | ROAD MAINTENANCE | 1ea grader 12hrs/day | 152 | DY |  | 0 | 0 |  | 0 | 2677.2 | 406934.4 |  | 0 |  | 0 | 406934.4 | 25% | 101733.6 | 508668
2.05 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.08 |  |  | CONTRACTOR LOA AND TRAVEL | Edm to Dawson City charter flight + DC to Site by charter bus. 1 flight/man every two weeks. | 600 | Round Trip |  | 0 | 0 |  | 0 | 1144 | 686400 |  | 0 |  | 0 | 686400 | 25% | 171600 | 858000
2.09 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.1 |  |  | TRANSPORTATION AND FREIGHT | HDPE pipe & aquadam. | 6 | LD |  | 0 | 0 |  | 0 | 9361.68 | 56170.08 |  | 0 |  | 0 | 56170.08 | 25% | 14042.52 | 70212.6
2.11 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.14 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 8025040.9568 | 160500.8191 |  | 0 |  | 0 | 160500.8191 | 25% | 40125.2048 | 200626.0239
2.15 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS |  | 2% |  |  | 0 | 0 |  | 0 | 8025040.9568 | 160500.8191 |  | 0 |  | 0 | 160500.8191 | 25% | 40125.2048 | 200626.0239
2.16 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.17 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 4962841.347 |  | 0 | 0% | 0 | 4962841.347 | 25% | 1240710.3367 | 6203551.6837
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 12987882.3038 | 1298788.2304 |  | 0 |  | 0 | 1298788.2304 | 25% | 324697.0576 | 1623485.288
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 1298788.2304 |  | 0 | 0% | 0 | 1298788.2304 | 25% | 324697.0576 | 1623485.288
| TOTAL | [16 empty] | 14286670.5342 | 25% | 3571667.6335 | 17858338.1677

## Pivot Table
Sum of labour cost
type of labour | % labour | Total
Camp Op & Maintenance |  | 650316.8
Engineering |  | 1424039.0809
Equip Maintenance |  | 539904
Equip Op |  | 1222092.2301
Equip Op / Equip Maintenance |  | 234165
Equip Op / Labour |  | 311670.2852
Equip Op / Welders / Labour |  | 293451.338
Labour |  | 73329.3728
Truck Driver |  | 103645.32
(blank) |  | 0
Grand Total |  | 4852613.4271
Sum of labour cost
| % labour of |  | % labour of
type of labour | all-in rate | Total | total labour
Camp Op & Maintenance |  | 650316.8 | 13.4%
Engineering |  | 1424039.0809 | 29.35%
Equip Maintenance |  | 539904 | 11.13%
Equip Op |  | 1222092.2301 | 25.18%
Equip Op / Equip Maintenance |  | 234165 | 4.826%
Equip Op / Labour |  | 311670.2852 | 6.423%
Equip Op / Welders / Labour |  | 293451.338 | 6.047%
Labour |  | 73329.3728 | 1.511%
Truck Driver |  | 103645.32 | 2.136%
Grand Total |  | 4852613.4271 | 100%
Sum of labour cost
type of labour |  | Total | labour % of total labour cost
Equip Op |  | 1635806.9079 | 33.71%
Labour |  | 405235.3182 | 8.351%
Truck Driver |  | 103645.32 | 2.136%
Equip Maintenance |  | 633570 | 13.06%
Camp Op & Maintenance |  | 650316.8 | 13.4%
Engineering |  | 1424039.0809 | 29.35%
Total |  | 4852613.4271 | 100%
* Contingency not included.