## Summary
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option D-11032014.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-D | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 10086000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 5753000
| 3.01 | EPCM COSTS |  | 1584000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 17423000
| 4.01 | CONTINGENCY | 25% | 4356000
|  | TOTAL COSTS |  | 21779000

## Detail Costs
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option D-11032014.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-D | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW
|  | MTO No.: |  | REVISION: | 0
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Edmonton to Dawson City 2,519km. Dawson City to Site approx 110km. 2ea-PC2000, 5ea 90ton rock truck, 1ea-345, 1ea-D8, 7ea-40ton rock truck, 1ea-grader, 1ea-packer. Second Season Remob: 2ea-wheel loader, 1ea-345, 1ea-D8 | 20 | EA |  | 0 | 0 |  | 0 | 32304.48 | 646089.6 |  | 0 |  | 0 | 646089.6 | 25% | 161522.4 | 807612
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Major Road Improvements | 15km |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.05 |  |  | Clear & grub | Medium | 9 | HA |  | 0 | 0 |  | 0 | 11877.51 | 106897.59 |  | 0 |  | 0 | 106897.59 | 25% | 26724.3975 | 133621.9875
1.06 |  |  | Road embankment widening, 3m | Cut to fill existing shoulder. Approx 8M3 / LM. | 120000 | M3 |  | 0 | 0 |  | 0 | 4.63 | 555600 |  | 0 |  | 0 | 555600 | 25% | 138900 | 694500
1.07 |  |  | Re-grade road sub-base | Av. 150mm dp x 5m wide | 11250 | M3 |  | 0 | 0 |  | 0 | 12.57 | 141412.5 |  | 0 |  | 0 | 141412.5 | 25% | 35353.125 | 176765.625
1.08 |  |  | Gravel resurfacing, 100mm thk x 8m wide | Drill & blast, crushing, load & haul and place. | 12000 | M3 |  | 0 | 0 |  | 0 | 123.3 | 1479600 |  | 0 |  | 0 | 1479600 | 25% | 369900 | 1849500
1.09 |  |  | Bridge construction | 15m clear span x 11m w. Supply & install. | 1 | LS |  | 0 | 0 |  | 0 | 889246.4788 | 889246.4788 |  | 0 |  | 0 | 889246.4788 | 25% | 222311.6197 | 1111558.0985
1.1 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.11 |  |  | Bulk Earthworks |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.12 |  |  | Waste dump to channel fill | 1ea-D8 & 1ea-345 ex; push top of existing channel to fill channel bed. | 25000 | M3 |  | 0 | 0 |  | 0 | 5.22 | 130500 |  | 0 |  | 0 | 130500 | 25% | 32625 | 163125
1.13 |  |  | Waste dump to porupine pit | Equip Set 1 | 425000 | M3 |  | 0 | 0 |  | 0 | 4.9 | 2082500 |  | 0 |  | 0 | 2082500 | 25% | 520625 | 2603125
1.14 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.15 |  |  | Access Road Construction |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.16 |  |  | Gravel resurfacing, 300mm thk x 6m wide | Drill & blast, crushing, load & haul and place. | 990 | M3 |  | 0 | 0 |  | 0 | 156.92 | 155350.8 |  | 0 |  | 0 | 155350.8 | 25% | 38837.7 | 194188.5
1.17 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.18 |  |  | Gabion Drop Structures |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.19 |  |  | Gabion baskets (3m lg x 1m dp x 0.5m h) | Supply, load, haul, assemble, place | 1250 | EA |  | 0 | 0 |  | 0 | 638.72 | 798400 |  | 0 |  | 0 | 798400 | 25% | 199600 | 998000
1.2 |  |  | Gabion rock - 100 to 200 mm dia. | (8 drop structures) Drill & blast, screen & sort, load & haul to site, double handling and place. | 1850 | M3 |  | 0 | 0 |  | 0 | 111.51 | 206293.5 |  | 0 |  | 0 | 206293.5 | 25% | 51573.375 | 257866.875
1.21 |  |  | Rip-rap - 300 mm dia. | Drill & blast, screen & sort, load & haul to site, double handling and place. | 1100 | M3 |  | 0 | 0 |  | 0 | 121.68 | 133848 |  | 0 |  | 0 | 133848 | 25% | 33462 | 167310
1.24 |  |  | Geotextile 10oz | Under cobble layer. | 5300 | M2 |  | 0 | 0 |  | 0 | 3.62 | 19186 |  | 0 |  | 0 | 19186 | 25% | 4796.5 | 23982.5
1.22 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.23 |  |  | Water Diversion |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.24 |  |  | Aquadam - supply & install | 6' x 100' lg. | 1 | EA |  | 0 | 0 |  | 0 | 26000 | 26000 |  | 0 |  | 0 | 26000 | 25% | 6500 | 32500
1.25 |  |  | 610mm HDPE DR21 pipe | Trench 1.6m dp, BF 1m cover, supply & install. | 900 | LM |  | 0 | 0 |  | 0 | 980.0724 | 882065.16 |  | 0 |  | 0 | 882065.16 | 25% | 220516.29 | 1102581.45
1.26 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.27 |  |  | Support Equipment |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.28 |  |  | Shop truck | 1ea | 83.6 | DY |  | 0 | 0 |  | 0 | 300 | 25080 |  | 0 |  | 0 | 25080 | 25% | 6270 | 31350
1.29 |  |  | Temp maintenance shop | 1ea | 1 | LS |  | 0 | 0 |  | 0 | 15000 | 15000 |  | 0 |  | 0 | 15000 | 25% | 3750 | 18750
1.3 |  |  | Shop trailer | 1ea | 2.75 | MO |  | 0 | 0 |  | 0 | 2000 | 5500 |  | 0 |  | 0 | 5500 | 25% | 1375 | 6875
1.31 |  |  | Fuel bowser | 1ea on-site | 2.75 | MO |  | 0 | 0 |  | 0 | 5000 | 13750 |  | 0 |  | 0 | 13750 | 25% | 3437.5 | 17187.5
1.32 |  |  | Pick-up trucks | 6ea | 83.6 | DY |  | 0 | 0 |  | 0 | 900 | 75240 |  | 0 |  | 0 | 75240 | 25% | 18810 | 94050
1.33 |  |  | Portable light towers | 6ea | 2.75 | MO |  | 0 | 0 |  | 0 | 22440 | 61710 |  | 0 |  | 0 | 61710 | 25% | 15427.5 | 77137.5
1.34 |  |  | Generator | 6ea | 2.75 | MO |  | 0 | 0 |  | 0 | 7920 | 21780 |  | 0 |  | 0 | 21780 | 25% | 5445 | 27225
1.35 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.36 |  |  | Support Labour | *During Road Improvements, Quarry Development & Creek Stabiliztion Work. |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.37 |  |  | Heavy duty mechanic | 1ea/shift | 91.2 | DY |  | 0 | 0 |  | 0 | 2640 | 240768 |  | 0 |  | 0 | 240768 | 25% | 60192 | 300960
1.38 |  |  | Welder | 1ea/shift | 91.2 | DY |  | 0 | 0 |  | 0 | 2640 | 240768 |  | 0 |  | 0 | 240768 | 25% | 60192 | 300960
1.39 |  |  | Labourer | 2ea/shift | 182.4 | DY |  | 0 | 0 |  | 0 | 1800 | 328320 |  | 0 |  | 0 | 328320 | 25% | 82080 | 410400
1.4 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.37 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.38 |  |  | Equipment washdown facilites | 1ea - 80'x120' temprorary building , 300mm SOG, 4ea - 4.5 GPM pressure washers w/ 600Gal tanks, 4man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 742873.376 | 742873.376 |  | 0 |  | 0 | 742873.376 | 25% | 185718.344 | 928591.72
1.39 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 20000 | 20000 |  | 0 |  | 0 | 20000 | 25% | 5000 | 25000
1.4 |  |  | PPE; respirators, overalls |  | 50 | EA |  | 0 | 0 |  | 0 | 500 | 25000 |  | 0 |  | 0 | 25000 | 25% | 6250 | 31250
1.41 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.41 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.42 |  |  | Fuel truck & driver | 27,000 liter tanker | 24.5838 | LD |  | 0 | 0 |  | 0 | 685.6 | 16854.6634 |  | 0 |  | 0 | 16854.6634 | 25% | 4213.6659 | 21068.3293
1.43 |  |  |  | *fuel included in all-in rates. | 663763 | liters |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.44 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.45 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 10085633.6682 |  | 0 | 0% | 0 | 10085633.6682 | 25% | 2521408.4171 | 12607042.0853
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | 50 man temporary camp x 5.25mo. | 7980 | MDY |  | 0 | 0 |  | 0 | 489.86 | 3909082.8 |  | 0 |  | 0 | 3909082.8 | 25% | 977270.7 | 4886353.5
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 3% |  |  | 0 | 0 |  | 0 | 10085633.6682 | 302569.01 |  | 0 |  | 0 | 302569.01 | 25% | 75642.2525 | 378211.2626
2.03 |  |  | SNOW REMOVAL | Grader & dozer for winter months, 12hrs/day x 7days. | 7 | DY |  | 0 | 0 |  | 0 | 4538.76 | 31771.32 |  | 0 |  | 0 | 31771.32 | 25% | 7942.83 | 39714.15
2.04 |  |  | ROAD MAINTENANCE | 1ea Grader 12hrs/day | 212.8 | DY |  | 0 | 0 |  | 0 | 2677.2 | 569708.16 |  | 0 |  | 0 | 569708.16 | 25% | 142427.04 | 712135.2
2.05 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.08 |  |  | CONTRACTOR LOA AND TRAVEL | Edm to Dawson City charter flight + DC to Site by charter bus. 1 flight/man every two weeks. | 420 | Round Trip |  | 0 | 0 |  | 0 | 1144 | 480480 |  | 0 |  | 0 | 480480 | 25% | 120120 | 600600
2.09 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.1 |  |  | TRANSPORTATION AND FREIGHT | HDPE pipe & aquadam. | 6 | LD |  | 0 | 0 |  | 0 | 9361.68 | 56170.08 |  | 0 |  | 0 | 56170.08 | 25% | 14042.52 | 70212.6
2.11 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.14 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 10085633.6682 | 201712.6734 |  | 0 |  | 0 | 201712.6734 | 25% | 50428.1683 | 252140.8417
2.15 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS |  | 2% |  |  | 0 | 0 |  | 0 | 10085633.6682 | 201712.6734 |  | 0 |  | 0 | 201712.6734 | 25% | 50428.1683 | 252140.8417
2.16 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.17 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 5753206.7168 |  | 0 | 0% | 0 | 5753206.7168 | 25% | 1438301.6792 | 7191508.396
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 15838840.385 | 1583884.0385 |  | 0 |  | 0 | 1583884.0385 | 25% | 395971.0096 | 1979855.0481
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 1583884.0385 |  | 0 | 0% | 0 | 1583884.0385 | 25% | 395971.0096 | 1979855.0481
| TOTAL | [16 empty] | 17422724.4235 | 25% | 4355681.1059 | 21778405.5294

## Pivot Table
Sum of labour cost
type of labour | % labour | Total
Camp Op & Maintenance |  | 781816.56
Engineering |  | 1880941.0865
Equip Maintenance |  | 809856
Equip Op |  | 1238369.6061
Equip Op / Equip Maintenance |  | 584515
Equip Op / Labour |  | 469132.2515
Equip Op / Welders / Labour |  | 293451.338
Labour |  | 74287.3376
Truck Driver |  | 236244.1581
(blank) |  | 0
Grand Total |  | 6368613.3378
Sum of labour cost
| % labour of |  | % labour of
type of labour | all-in rate | Total | total labour
Camp Op & Maintenance |  | 781816.56 | 12.28%
Engineering |  | 1880941.0865 | 29.53%
Equip Maintenance |  | 809856 | 12.72%
Equip Op |  | 1238369.6061 | 19.44%
Equip Op / Equip Maintenance |  | 584515 | 9.178%
Equip Op / Labour |  | 469132.2515 | 7.366%
Equip Op / Welders / Labour |  | 293451.338 | 4.608%
Labour |  | 74287.3376 | 1.166%
Truck Driver |  | 236244.1581 | 3.71%
Grand Total |  | 6368613.3378 | 100%
Sum of labour cost
type of labour |  | Total | labour % of total labour cost
Equip Op |  | 1941025.2671 | 30.48%
Labour |  | 484924.2662 | 7.614%
Truck Driver |  | 236244.1581 | 3.71%
Equip Maintenance |  | 1043662 | 16.39%
Camp Op & Maintenance |  | 781816.56 | 12.28%
Engineering |  | 1880941.0865 | 29.53%
Total |  | 6368613.3378 | 100%
* Contingency not included.