## Summary
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option D3 - 04032014.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-D3 | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 10481000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 5262000
| 3.01 | EPCM COSTS |  | 1574000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 17317000
| 4.01 | CONTINGENCY | 25% | 4329000
|  | TOTAL COSTS |  | 21646000

## Detail Costs
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option D3 - 04032014.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-D3 | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW
|  | MTO No.: |  | REVISION: | 0
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Edmonton to Dawson City 2,519km. Dawson City to Site approx 110km. 2ea-PC2000, 5ea 90ton rock truck, 1ea-345, 1ea-D8, 7ea-40ton rock truck, 1ea-grader, 1ea-packer. Second Season Remob: 2ea-wheel loader, 1ea-345, 1ea-D8 | 20 | EA |  | 0 | 0 |  | 0 | 32304.48 | 646089.6 |  | 0 |  | 0 | 646089.6 | 25% | 161522.4 | 807612
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Major Road Improvements | 15km |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.05 |  |  | Clear & grub | Medium | 9 | HA |  | 0 | 0 |  | 0 | 11877.51 | 106897.59 |  | 0 |  | 0 | 106897.59 | 25% | 26724.3975 | 133621.9875
1.06 |  |  | Road embankment widening, 3m | Cut to fill existing shoulder. Approx 8M3 / LM. | 120000 | M3 |  | 0 | 0 |  | 0 | 4.63 | 555600 |  | 0 |  | 0 | 555600 | 25% | 138900 | 694500
1.07 |  |  | Re-grade road sub-base | Av. 150mm dp x 5m wide | 11250 | M3 |  | 0 | 0 |  | 0 | 12.57 | 141412.5 |  | 0 |  | 0 | 141412.5 | 25% | 35353.125 | 176765.625
1.08 |  |  | Gravel resurfacing, 100mm thk x 8m wide | Drill & blast, crushing, load & haul and place. | 12000 | M3 |  | 0 | 0 |  | 0 | 159.61 | 1915320 |  | 0 |  | 0 | 1915320 | 25% | 478830 | 2394150
1.09 |  |  | Bridge construction | 15m clear span x 11m w. Supply & install. | 1 | LS |  | 0 | 0 |  | 0 | 889246.4788 | 889246.4788 |  | 0 |  | 0 | 889246.4788 | 25% | 222311.6197 | 1111558.0985
1.1 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.11 |  |  | Bulk Earthworks |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.12 |  |  | Waste dump to channel fill | 1ea-D8 & 1ea-345 ex; push top of existing channel to fill channel bed. | 25000 | M3 |  | 0 | 0 |  | 0 | 5.22 | 130500 |  | 0 |  | 0 | 130500 | 25% | 32625 | 163125
1.13 |  |  | Waste rock to porupine pit | Equip Set 1 | 425000 | M3 |  | 0 | 0 |  | 0 | 4.9 | 2082500 |  | 0 |  | 0 | 2082500 | 25% | 520625 | 2603125
1.14 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.15 |  |  | Access Road Construction |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.16 |  |  | Gravel resurfacing, 300mm thk x 6m wide | Drill & blast, crushing, load & haul and place. | 1350 | M3 |  | 0 | 0 |  | 0 | 159.45 | 215257.5 |  | 0 |  | 0 | 215257.5 | 25% | 53814.375 | 269071.875
1.17 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.18 |  |  | Channel Armouring |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.19 |  |  | Rip-rap - 500mm dia. | Drill & blast, screen & sort, load & haul to site, double handling and place. | 8500 | M3 |  | 0 | 0 |  | 0 | 126.59 | 1076015 |  | 0 |  | 0 | 1076015 | 25% | 269003.75 | 1345018.75
1.2 |  |  | Geotextile 10oz | Under cobble layer. | 13500 | M2 |  | 0 | 0 |  | 0 | 3.62 | 48870 |  | 0 |  | 0 | 48870 | 25% | 12217.5 | 61087.5
1.21 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.22 |  |  | Water Diversion |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.23 |  |  | Aquadam - supply & install | 6' x 100' lg. | 1 | EA |  | 0 | 0 |  | 0 | 26000 | 26000 |  | 0 |  | 0 | 26000 | 25% | 6500 | 32500
1.24 |  |  | 610mm HDPE DR21 pipe | Trench 1.6m dp, BF 1m cover, supply & install. | 900 | LM |  | 0 | 0 |  | 0 | 980.0724 | 882065.16 |  | 0 |  | 0 | 882065.16 | 25% | 220516.29 | 1102581.45
1.25 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.26 |  |  | Support Equipment |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.27 |  |  | Shop truck | 1ea | 83.6 | DY |  | 0 | 0 |  | 0 | 300 | 25080 |  | 0 |  | 0 | 25080 | 25% | 6270 | 31350
1.28 |  |  | Temp maintenance shop | 1ea | 1 | LS |  | 0 | 0 |  | 0 | 15000 | 15000 |  | 0 |  | 0 | 15000 | 25% | 3750 | 18750
1.29 |  |  | Shop trailer | 1ea | 2.75 | MO |  | 0 | 0 |  | 0 | 2000 | 5500 |  | 0 |  | 0 | 5500 | 25% | 1375 | 6875
1.3 |  |  | Fuel bowser | 1ea on-site | 2.75 | MO |  | 0 | 0 |  | 0 | 5000 | 13750 |  | 0 |  | 0 | 13750 | 25% | 3437.5 | 17187.5
1.31 |  |  | Pick-up trucks | 6ea | 83.6 | DY |  | 0 | 0 |  | 0 | 900 | 75240 |  | 0 |  | 0 | 75240 | 25% | 18810 | 94050
1.32 |  |  | Portable light towers | 6ea | 2.75 | MO |  | 0 | 0 |  | 0 | 22440 | 61710 |  | 0 |  | 0 | 61710 | 25% | 15427.5 | 77137.5
1.33 |  |  | Generator | 6ea | 2.75 | MO |  | 0 | 0 |  | 0 | 7920 | 21780 |  | 0 |  | 0 | 21780 | 25% | 5445 | 27225
1.34 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.35 |  |  | Support Labour | *During Road Improvements, Quarry Development & Creek Stabiliztion Work. |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.36 |  |  | Heavy duty mechanic | 1ea/shift | 83.6 | DY |  | 0 | 0 |  | 0 | 2640 | 220704 |  | 0 |  | 0 | 220704 | 25% | 55176 | 275880
1.37 |  |  | Welder | 1ea/shift | 83.6 | DY |  | 0 | 0 |  | 0 | 2640 | 220704 |  | 0 |  | 0 | 220704 | 25% | 55176 | 275880
1.38 |  |  | Labourer | 2ea/shift | 167.2 | DY |  | 0 | 0 |  | 0 | 1800 | 300960 |  | 0 |  | 0 | 300960 | 25% | 75240 | 376200
1.39 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.4 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.41 |  |  | Equipment washdown facilites | 1ea - 80'x120' temprorary building , 300mm SOG, 4ea - 4.5 GPM pressure washers w/ 600Gal tanks, 4man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 742873.376 | 742873.376 |  | 0 |  | 0 | 742873.376 | 25% | 185718.344 | 928591.72
1.42 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 20000 | 20000 |  | 0 |  | 0 | 20000 | 25% | 5000 | 25000
1.43 |  |  | PPE; respirators, overalls |  | 50 | EA |  | 0 | 0 |  | 0 | 500 | 25000 |  | 0 |  | 0 | 25000 | 25% | 6250 | 31250
1.44 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.45 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.46 |  |  | Fuel truck & driver | 27,000 liter tanker | 24.8801 | LD |  | 0 | 0 |  | 0 | 685.6 | 17057.8042 |  | 0 |  | 0 | 17057.8042 | 25% | 4264.451 | 21322.2552
1.47 |  |  |  | *fuel included in all-in rates. | 671763 | liters |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.48 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.49 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 10481133.009 |  | 0 | 0% | 0 | 10481133.009 | 25% | 2620283.2522 | 13101416.2612
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | 50 man temporary camp x 3.75mo. | 5700 | MDY |  | 0 | 0 |  | 0 | 618.9 | 3527730 |  | 0 |  | 0 | 3527730 | 25% | 881932.5 | 4409662.5
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 3% |  |  | 0 | 0 |  | 0 | 10481133.009 | 314433.9903 |  | 0 |  | 0 | 314433.9903 | 25% | 78608.4976 | 393042.4878
2.03 |  |  | SNOW REMOVAL | Grader & dozer for winter months, 12hrs/day x 7days. | 7 | DY |  | 0 | 0 |  | 0 | 4538.76 | 31771.32 |  | 0 |  | 0 | 31771.32 | 25% | 7942.83 | 39714.15
2.04 |  |  | ROAD MAINTENANCE | 1ea Grader 12hrs/day | 212.8 | DY |  | 0 | 0 |  | 0 | 2677.2 | 569708.16 |  | 0 |  | 0 | 569708.16 | 25% | 142427.04 | 712135.2
2.05 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.08 |  |  | CONTRACTOR LOA AND TRAVEL | Edm to Dawson City charter flight + DC to Site by charter bus. 1 flight/man every two weeks. | 300 | Round Trip |  | 0 | 0 |  | 0 | 1144 | 343200 |  | 0 |  | 0 | 343200 | 25% | 85800 | 429000
2.09 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.1 |  |  | TRANSPORTATION AND FREIGHT | HDPE pipe & aquadam. | 6 | LD |  | 0 | 0 |  | 0 | 9361.68 | 56170.08 |  | 0 |  | 0 | 56170.08 | 25% | 14042.52 | 70212.6
2.11 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.14 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 10481133.009 | 209622.6602 |  | 0 |  | 0 | 209622.6602 | 25% | 52405.665 | 262028.3252
2.15 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS |  | 2% |  |  | 0 | 0 |  | 0 | 10481133.009 | 209622.6602 |  | 0 |  | 0 | 209622.6602 | 25% | 52405.665 | 262028.3252
2.16 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.17 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 5262258.8706 |  | 0 | 0% | 0 | 5262258.8706 | 25% | 1315564.7177 | 6577823.5883
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 15743391.8796 | 1574339.188 |  | 0 |  | 0 | 1574339.188 | 25% | 393584.797 | 1967923.985
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 1574339.188 |  | 0 | 0% | 0 | 1574339.188 | 25% | 393584.797 | 1967923.985
| TOTAL | [16 empty] | 17317731.0676 | 25% | 4329432.7669 | 21647163.8345

## Sheet1
Sum of labour cost
type of labour | % labour | Total
Camp Op & Maintenance |  | 705546
Engineering |  | 1642032.6156
Equip Maintenance |  | 742368
Equip Op |  | 1493789.4225
Equip Op / Equip Maintenance |  | 730290
Equip Op / Labour |  | 482965.7489
Equip Op / Welders / Labour |  | 293451.338
Truck Driver |  | 256025.5705
(blank) |  | 0
Grand Total |  | 6346468.6955
| % labour of |  | % labour of
type of labour | all-in rate | Total | total labour
Camp Op & Maintenance |  | 705546 | 11.12%
Engineering |  | 1642032.6156 | 25.87%
Equip Maintenance |  | 742368 | 11.7%
Equip Op |  | 1493789.4225 | 23.54%
Equip Op / Equip Maintenance |  | 730290 | 11.51%
Equip Op / Labour |  | 482965.7489 | 7.61%
Equip Op / Welders / Labour |  | 293451.338 | 4.624%
Labour |  | 0 | 0%
Truck Driver |  | 256025.5705 | 4.034%
Grand Total |  | 6346468.6955 | 100%
Sum of labour cost
type of labour |  | Total | labour % of total labour cost
Equip Op |  | 2290826.8322 | 36.1%
Labour |  | 417553.6773 | 6.579%
Truck Driver |  | 256025.5705 | 4.034%
Equip Maintenance |  | 1034484 | 16.3%
Camp Op & Maintenance |  | 705546 | 11.12%
Engineering |  | 1642032.6156 | 25.87%
Total |  | 6346468.6955 | 100%
* Contingency not included.