## Summary
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option E-11032014.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-E | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 11882000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 5530000
| 3.01 | EPCM COSTS |  | 1741000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 19153000
| 4.01 | CONTINGENCY | 50% | 9577000
|  | TOTAL COSTS |  | 28730000

## Detail Costs
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option E-11032014.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-E | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW
|  | MTO No.: |  | REVISION: | 0
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Edmonton to Dawson City 2,519km. Dawson City to Site approx 110km. 1ea D9 dozer , 1ea grader, 1ea 70ton excavator, 1ea wheel loader, 8ea 50ton rock truck, 1ea packer. Second Season Remob: 2ea PC2000, 5ea 777, 1ea D9. | 18 | EA |  | 0 | 0 |  | 0 | 35893.8667 | 646089.6 |  | 0 |  | 0 | 646089.6 | 50% | 323044.8 | 969134.4
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Major Road Improvements | 15km |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.05 |  |  | Clear & grub | Medium | 9 | HA |  | 0 | 0 |  | 0 | 11877.51 | 106897.59 |  | 0 |  | 0 | 106897.59 | 50% | 53448.795 | 160346.385
1.06 |  |  | Road embankment widening, 3m | Cut to fill existing shoulder. Approx 8M3 / LM. | 120000 | M3 |  | 0 | 0 |  | 0 | 4.63 | 555600 |  | 0 |  | 0 | 555600 | 50% | 277800 | 833400
1.07 |  |  | Re-grade road sub-base | Av. 150mm dp x 5m wide | 11250 | M3 |  | 0 | 0 |  | 0 | 12.57 | 141412.5 |  | 0 |  | 0 | 141412.5 | 50% | 70706.25 | 212118.75
1.08 |  |  | Gravel resurfacing, 100mm thk x 8m wide | Drill & blast, crushing, load & haul and place. | 12000 | M3 |  | 0 | 0 |  | 0 | 168.82 | 2025840 |  | 0 |  | 0 | 2025840 | 50% | 1012920 | 3038760
1.09 |  |  | Bridge construction | 15m clear span x 11m w. Supply & install. | 1 | LS |  | 0 | 0 |  | 0 | 889246.4788 | 889246.4788 |  | 0 |  | 0 | 889246.4788 | 50% | 444623.2394 | 1333869.7182
1.1 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.11 |  |  | Bulk Earthworks |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.12 |  |  | Existing channel to porupine pit | Equip Set 1 | 450000 | M3 |  | 0 | 0 |  | 0 | 4.9 | 2205000 |  | 0 |  | 0 | 2205000 | 50% | 1102500 | 3307500
1.13 |  |  | Waste dump to porupine pit | Equip Set 1 | 500000 | M3 |  | 0 | 0 |  | 0 | 4.9 | 2450000 |  | 0 |  | 0 | 2450000 | 50% | 1225000 | 3675000
1.14 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.15 |  |  | Access Road Construction |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.16 |  |  | Gravel resurfacing, 300mm thk x 6m wide | Drill & blast, crushing, load & haul and place. | 1350 | M3 |  | 0 | 0 |  | 0 | 168.82 | 227907 |  | 0 |  | 0 | 227907 | 50% | 113953.5 | 341860.5
1.17 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.18 |  |  | Siphon |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.19 |  |  | Air pump | supply | 1 | EA |  | 0 | 0 |  | 0 | 20000 | 20000 |  | 0 |  | 0 | 20000 | 50% | 10000 | 30000
1.2 |  |  | First Location: |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.21 |  |  | 610mm HDPE DR21 pipe | Supply & install. | 900 | LM |  | 0 | 0 |  | 0 | 935.27 | 841743 |  | 0 |  | 0 | 841743 | 50% | 420871.5 | 1262614.5
1.22 |  |  | Lock blocks | Supply & place. | 46 | EA |  | 0 | 0 |  | 0 | 150 | 6900 |  | 0 |  | 0 | 6900 | 50% | 3450 | 10350
1.23 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.24 |  |  | Relocate: |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.25 |  |  | Cut & move 900m of pipe | Cut into 150m lengths, relocate 500m. | 6 | EA |  | 0 | 0 |  | 0 | 5000 | 30000 |  | 0 |  | 0 | 30000 | 50% | 15000 | 45000
1.26 |  |  | 610mm HDPE DR21 pipe | Re-weld joints | 6 | EA |  | 0 | 0 |  | 0 | 1440 | 8640 |  | 0 |  | 0 | 8640 | 50% | 4320 | 12960
1.27 |  |  | Lock blocks | Relocate | 46 | EA |  | 0 | 0 |  | 0 | 50 | 2300 |  | 0 |  | 0 | 2300 | 50% | 1150 | 3450
1.28 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.29 |  |  | Support Equipment |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.3 |  |  | Shop truck | 1ea | 136.8 | DY |  | 0 | 0 |  | 0 | 300 | 41040 |  | 0 |  | 0 | 41040 | 50% | 20520 | 61560
1.31 |  |  | Temp maintenance shop | 1ea | 1 | LS |  | 0 | 0 |  | 0 | 15000 | 15000 |  | 0 |  | 0 | 15000 | 50% | 7500 | 22500
1.32 |  |  | Shop trailer | 1ea | 4.5 | MO |  | 0 | 0 |  | 0 | 2000 | 9000 |  | 0 |  | 0 | 9000 | 50% | 4500 | 13500
1.33 |  |  | Fuel bowser | 1ea on-site | 4.5 | MO |  | 0 | 0 |  | 0 | 5000 | 22500 |  | 0 |  | 0 | 22500 | 50% | 11250 | 33750
1.34 |  |  | Pick-up trucks | 6ea | 136.8 | DY |  | 0 | 0 |  | 0 | 900 | 123120 |  | 0 |  | 0 | 123120 | 50% | 61560 | 184680
1.35 |  |  | Portable light towers | 6ea | 4.5 | MO |  | 0 | 0 |  | 0 | 22440 | 100980 |  | 0 |  | 0 | 100980 | 50% | 50490 | 151470
1.36 |  |  | Generator | 6ea | 4.5 | MO |  | 0 | 0 |  | 0 | 7920 | 35640 |  | 0 |  | 0 | 35640 | 50% | 17820 | 53460
1.37 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.38 |  |  | Support Labour | *During Road Improvements, Quarry Development & Creek Stabiliztion Work. |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.39 |  |  | Heavy duty mechanic | 1ea/shift | 60.8 | DY |  | 0 | 0 |  | 0 | 2640 | 160512 |  | 0 |  | 0 | 160512 | 50% | 80256 | 240768
1.4 |  |  | Welder | 1ea/shift | 60.8 | DY |  | 0 | 0 |  | 0 | 2640 | 160512 |  | 0 |  | 0 | 160512 | 50% | 80256 | 240768
1.41 |  |  | Labourer | 2ea/shift | 121.6 | DY |  | 0 | 0 |  | 0 | 1800 | 218880 |  | 0 |  | 0 | 218880 | 50% | 109440 | 328320
1.42 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.37 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.38 |  |  | Equipment washdown facilites | 1ea - 80'x120' temprorary building , 300mm SOG, 4ea - 4.5 GPM pressure washers w/ 600Gal tanks, 4man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 765225.888 | 765225.888 |  | 0 |  | 0 | 765225.888 | 50% | 382612.944 | 1147838.832
1.39 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 18000 | 18000 |  | 0 |  | 0 | 18000 | 50% | 9000 | 27000
1.4 |  |  | PPE; respirators, overalls |  | 50 | EA |  | 0 | 0 |  | 0 | 500 | 25000 |  | 0 |  | 0 | 25000 | 50% | 12500 | 37500
1.41 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.43 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.44 |  |  | Fuel truck & driver | 27,000 liter tanker | 42.6883 | LD |  | 0 | 0 |  | 0 | 685.6 | 29267.0705 |  | 0 |  | 0 | 29267.0705 | 50% | 14633.5353 | 43900.6058
1.45 |  |  |  | *fuel included in all-in rates. | 1152583 | liters |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.46 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.47 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 11882253.1273 |  | 0 | 0% | 0 | 11882253.1273 | 50% | 5941126.5637 | 17823379.691
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | av 50men camp x 3.75mo. | 5700 | MDY |  | 0 | 0 |  | 0 | 615.49 | 3508293 |  | 0 |  | 0 | 3508293 | 50% | 1754146.5 | 5262439.5
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 3% |  |  | 0 | 0 |  | 0 | 11882253.1273 | 356467.5938 |  | 0 |  | 0 | 356467.5938 | 50% | 178233.7969 | 534701.3907
2.03 |  |  | SNOW REMOVAL | Grader & dozer for winter months, 12hrs/day x 7days. | 7 | DY |  | 0 | 0 |  | 0 | 4538.76 | 31771.32 |  | 0 |  | 0 | 31771.32 | 50% | 15885.66 | 47656.98
2.04 |  |  | ROAD MAINTENANCE | 1ea Grader 12hrs/day | 152 | DY |  | 0 | 0 |  | 0 | 2677.2 | 406934.4 |  | 0 |  | 0 | 406934.4 | 50% | 203467.2 | 610401.6
2.05 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.08 |  |  | CONTRACTOR LOA AND TRAVEL | Edm to Dawson City charter flight + DC to Site by charter bus. 1 flight/man every two weeks. | 375 | Round Trip |  | 0 | 0 |  | 0 | 1144 | 429000 |  | 0 |  | 0 | 429000 | 50% | 214500 | 643500
2.09 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.1 |  |  | TRANSPORTATION AND FREIGHT | HDPE pipe & lock blocks. | 9 | LD |  | 0 | 0 |  | 0 | 9361.68 | 84255.12 |  | 0 |  | 0 | 84255.12 | 50% | 42127.56 | 126382.68
2.11 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.14 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 11882253.1273 | 237645.0625 |  | 0 |  | 0 | 237645.0625 | 50% | 118822.5313 | 356467.5938
2.15 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS |  | 4% |  |  | 0 | 0 |  | 0 | 11882253.1273 | 475290.1251 |  | 0 |  | 0 | 475290.1251 | 50% | 237645.0625 | 712935.1876
2.16 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.17 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 5529656.6215 |  | 0 | 0% | 0 | 5529656.6215 | 50% | 2764828.3107 | 8294484.9322
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 17411909.7488 | 1741190.9749 |  | 0 |  | 0 | 1741190.9749 | 50% | 870595.4874 | 2611786.4623
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 1741190.9749 |  | 0 | 0% | 0 | 1741190.9749 | 50% | 870595.4874 | 2611786.4623
| TOTAL | [16 empty] | 19153100.7237 | 50% | 9576550.3618 | 28729651.0855

## Pivot Table
Sum of labour cost
type of labour | % labour | Total
Camp Op & Maintenance |  | 701658.6
Engineering |  | 2081892.5387
Equip Maintenance |  | 539904
Equip Op |  | 1136119.6023
Equip Op / Equip Maintenance |  | 1210300
Equip Op / Labour |  | 291352.19
Equip Op / Welders / Labour |  | 293451.338
Labour |  | 85162.5888
Truck Driver |  | 273180.8943
(blank) |  | 0
Grand Total |  | 6613021.7522
Sum of labour cost
| % labour of |  | % labour of
type of labour | all-in rate | Total | total labour
Camp Op & Maintenance |  | 701658.6 | 10.61%
Engineering |  | 2081892.5387 | 31.48%
Equip Maintenance |  | 539904 | 8.164%
Equip Op |  | 1136119.6023 | 17.18%
Equip Op / Equip Maintenance |  | 1210300 | 18.3%
Equip Op / Labour |  | 291352.19 | 4.406%
Equip Op / Welders / Labour |  | 293451.338 | 4.437%
Labour |  | 85162.5888 | 1.288%
Truck Driver |  | 273180.8943 | 4.131%
Grand Total |  | 6613021.7522 | 100%
Sum of labour cost
type of labour |  | Total | labour % of total labour cost
Equip Op |  | 2125356.2325 | 32.14%
Labour |  | 406909.4866 | 6.153%
Truck Driver |  | 273180.8943 | 4.131%
Equip Maintenance |  | 1024024 | 15.48%
Camp Op & Maintenance |  | 701658.6 | 10.61%
Engineering |  | 2081892.5387 | 31.48%
Total |  | 6613021.7522 | 100%
* Contingency not included.