## Summary
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option E3-04032014.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-E3 | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 13218000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 6585000
| 3.01 | EPCM COSTS |  | 1980000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 21783000
| 4.01 | CONTINGENCY | 25% | 5446000
|  | TOTAL COSTS |  | 27229000

## Detail Costs
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option E3-04032014.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-E3 | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW
|  | MTO No.: |  | REVISION: | 0
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Edmonton to Dawson City 2,519km. Dawson City to Site approx 110km. 1ea D9 dozer , 1ea grader, 1ea 70ton excavator, 1ea wheel loader, 8ea 50ton rock truck, 1ea packer. Second Season Remob: 2ea PC2000, 5ea 777, 1ea D9. | 18 | EA |  | 0 | 0 |  | 0 | 35893.8667 | 646089.6 |  | 0 |  | 0 | 646089.6 | 25% | 161522.4 | 807612
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Major Road Improvements | 15km |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.05 |  |  | Clear & grub | Medium | 9 | HA |  | 0 | 0 |  | 0 | 11877.51 | 106897.59 |  | 0 |  | 0 | 106897.59 | 25% | 26724.3975 | 133621.9875
1.06 |  |  | Road embankment widening, 3m | Cut to fill existing shoulder. Approx 8M3 / LM. | 120000 | M3 |  | 0 | 0 |  | 0 | 4.63 | 555600 |  | 0 |  | 0 | 555600 | 25% | 138900 | 694500
1.07 |  |  | Re-grade road sub-base | Av. 150mm dp x 5m wide | 11250 | M3 |  | 0 | 0 |  | 0 | 12.57 | 141412.5 |  | 0 |  | 0 | 141412.5 | 25% | 35353.125 | 176765.625
1.08 |  |  | Gravel resurfacing, 100mm thk x 8m wide | Drill & blast, crushing, load & haul and place. | 12000 | M3 |  | 0 | 0 |  | 0 | 168.82 | 2025840 |  | 0 |  | 0 | 2025840 | 25% | 506460 | 2532300
1.09 |  |  | Bridge construction | 15m clear span x 11m w. Supply & install. | 1 | LS |  | 0 | 0 |  | 0 | 889246.4788 | 889246.4788 |  | 0 |  | 0 | 889246.4788 | 25% | 222311.6197 | 1111558.0985
1.1 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.11 |  |  | Bulk Earthworks |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.12 |  |  | Existing channel to porupine pit | Equip Set 1 | 525000 | M3 |  | 0 | 0 |  | 0 | 4.9 | 2572500 |  | 0 |  | 0 | 2572500 | 25% | 643125 | 3215625
1.13 |  |  | Waste dump to porupine pit | Equip Set 1 | 525000 | M3 |  | 0 | 0 |  | 0 | 4.9 | 2572500 |  | 0 |  | 0 | 2572500 | 25% | 643125 | 3215625
1.14 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.15 |  |  | Access Road Construction |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.16 |  |  | Gravel resurfacing, 300mm thk x 6m wide | Drill & blast, crushing, load & haul and place. | 1530 | M3 |  | 0 | 0 |  | 0 | 159.38 | 243851.4 |  | 0 |  | 0 | 243851.4 | 25% | 60962.85 | 304814.25
1.17 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.18 |  |  | Channel Armouring |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.19 |  |  | Rip-rap - 500mm dia. | Drill & blast, screen & sort, load & haul to site, double handling and place. | 6100 | M3 |  | 0 | 0 |  | 0 | 130.06 | 793366 |  | 0 |  | 0 | 793366 | 25% | 198341.5 | 991707.5
1.2 |  |  | Geotextile 10oz | Under cobble layer. | 9700 | M2 |  | 0 | 0 |  | 0 | 3.62 | 35114 |  | 0 |  | 0 | 35114 | 25% | 8778.5 | 43892.5
1.21 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.22 |  |  | Siphon |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.23 |  |  | Air pump | supply | 1 | EA |  | 0 | 0 |  | 0 | 20000 | 20000 |  | 0 |  | 0 | 20000 | 25% | 5000 | 25000
1.24 |  |  | First Location: |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.25 |  |  | 610mm HDPE DR21 pipe | Supply & install. | 900 | LM |  | 0 | 0 |  | 0 | 935.27 | 841743 |  | 0 |  | 0 | 841743 | 25% | 210435.75 | 1052178.75
1.26 |  |  | Lock blocks | Supply & place. | 46 | EA |  | 0 | 0 |  | 0 | 150 | 6900 |  | 0 |  | 0 | 6900 | 25% | 1725 | 8625
1.27 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.28 |  |  | Relocate: |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.29 |  |  | Cut & move 900m of pipe | Cut into 150m lengths, relocate 500m. | 6 | EA |  | 0 | 0 |  | 0 | 5000 | 30000 |  | 0 |  | 0 | 30000 | 25% | 7500 | 37500
1.3 |  |  | 610mm HDPE DR21 pipe | Re-weld joints | 6 | EA |  | 0 | 0 |  | 0 | 1440 | 8640 |  | 0 |  | 0 | 8640 | 25% | 2160 | 10800
1.31 |  |  | Lock blocks | Relocate | 46 | EA |  | 0 | 0 |  | 0 | 50 | 2300 |  | 0 |  | 0 | 2300 | 25% | 575 | 2875
1.32 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.33 |  |  | Support Equipment |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.34 |  |  | Shop truck | 1ea | 136.8 | DY |  | 0 | 0 |  | 0 | 300 | 41040 |  | 0 |  | 0 | 41040 | 25% | 10260 | 51300
1.35 |  |  | Temp maintenance shop | 1ea | 1 | LS |  | 0 | 0 |  | 0 | 15000 | 15000 |  | 0 |  | 0 | 15000 | 25% | 3750 | 18750
1.36 |  |  | Shop trailer | 1ea | 4.5 | MO |  | 0 | 0 |  | 0 | 2000 | 9000 |  | 0 |  | 0 | 9000 | 25% | 2250 | 11250
1.37 |  |  | Fuel bowser | 1ea on-site | 4.5 | MO |  | 0 | 0 |  | 0 | 5000 | 22500 |  | 0 |  | 0 | 22500 | 25% | 5625 | 28125
1.38 |  |  | Pick-up trucks | 6ea | 136.8 | DY |  | 0 | 0 |  | 0 | 900 | 123120 |  | 0 |  | 0 | 123120 | 25% | 30780 | 153900
1.39 |  |  | Portable light towers | 6ea | 4.5 | MO |  | 0 | 0 |  | 0 | 22440 | 100980 |  | 0 |  | 0 | 100980 | 25% | 25245 | 126225
1.4 |  |  | Generator | 6ea | 4.5 | MO |  | 0 | 0 |  | 0 | 7920 | 35640 |  | 0 |  | 0 | 35640 | 25% | 8910 | 44550
1.41 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.42 |  |  | Support Labour | *During Road Improvements, Quarry Development & Creek Stabiliztion Work. |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.43 |  |  | Heavy duty mechanic | 1ea/shift | 60.8 | DY |  | 0 | 0 |  | 0 | 2640 | 160512 |  | 0 |  | 0 | 160512 | 25% | 40128 | 200640
1.44 |  |  | Welder | 1ea/shift | 60.8 | DY |  | 0 | 0 |  | 0 | 2640 | 160512 |  | 0 |  | 0 | 160512 | 25% | 40128 | 200640
1.45 |  |  | Labourer | 2ea/shift | 121.6 | DY |  | 0 | 0 |  | 0 | 1800 | 218880 |  | 0 |  | 0 | 218880 | 25% | 54720 | 273600
1.42 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.43 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.44 |  |  | Equipment washdown facilites | 1ea - 80'x120' temprorary building , 300mm SOG, 4ea - 4.5 GPM pressure washers w/ 600Gal tanks, 4man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 765225.888 | 765225.888 |  | 0 |  | 0 | 765225.888 | 25% | 191306.472 | 956532.36
1.45 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 18000 | 18000 |  | 0 |  | 0 | 18000 | 25% | 4500 | 22500
1.46 |  |  | PPE; respirators, overalls |  | 50 | EA |  | 0 | 0 |  | 0 | 500 | 25000 |  | 0 |  | 0 | 25000 | 25% | 6250 | 31250
1.46 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.47 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.48 |  |  | Fuel truck & driver | 27,000 liter tanker | 44.066 | LD |  | 0 | 0 |  | 0 | 685.6 | 30211.675 |  | 0 |  | 0 | 30211.675 | 25% | 7552.9187 | 37764.5937
1.49 |  |  |  | *fuel included in all-in rates. | 1189783 | liters |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.5 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.51 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 13217622.1318 |  | 0 | 0% | 0 | 13217622.1318 | 25% | 3304405.5329 | 16522027.6647
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | av 50men camp x 4.5mo. | 7220 | MDY |  | 0 | 0 |  | 0 | 615.49 | 4443837.8 |  | 0 |  | 0 | 4443837.8 | 25% | 1110959.45 | 5554797.25
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 3% |  |  | 0 | 0 |  | 0 | 13217622.1318 | 396528.664 |  | 0 |  | 0 | 396528.664 | 25% | 99132.166 | 495660.8299
2.03 |  |  | SNOW REMOVAL | Grader & dozer for winter months, 12hrs/day x 7days. | 7 | DY |  | 0 | 0 |  | 0 | 4538.76 | 31771.32 |  | 0 |  | 0 | 31771.32 | 25% | 7942.83 | 39714.15
2.04 |  |  | ROAD MAINTENANCE | 1ea Grader 12hrs/day | 152 | DY |  | 0 | 0 |  | 0 | 2677.2 | 406934.4 |  | 0 |  | 0 | 406934.4 | 25% | 101733.6 | 508668
2.05 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.08 |  |  | CONTRACTOR LOA AND TRAVEL | Edm to Dawson City charter flight + DC to Site by charter bus. 1 flight/man every two weeks. | 375 | Round Trip |  | 0 | 0 |  | 0 | 1144 | 429000 |  | 0 |  | 0 | 429000 | 25% | 107250 | 536250
2.09 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.1 |  |  | TRANSPORTATION AND FREIGHT | HDPE pipe & lock blocks. | 9 | LD |  | 0 | 0 |  | 0 | 9361.68 | 84255.12 |  | 0 |  | 0 | 84255.12 | 25% | 21063.78 | 105318.9
2.11 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.14 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 13217622.1318 | 264352.4426 |  | 0 |  | 0 | 264352.4426 | 25% | 66088.1107 | 330440.5533
2.15 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS |  | 4% |  |  | 0 | 0 |  | 0 | 13217622.1318 | 528704.8853 |  | 0 |  | 0 | 528704.8853 | 25% | 132176.2213 | 660881.1066
2.16 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.17 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 6585384.6319 |  | 0 | 0% | 0 | 6585384.6319 | 25% | 1646346.158 | 8231730.7898
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 19803006.7637 | 1980300.6764 |  | 0 |  | 0 | 1980300.6764 | 25% | 495075.1691 | 2475375.8455
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 1980300.6764 |  | 0 | 0% | 0 | 1980300.6764 | 25% | 495075.1691 | 2475375.8455
| TOTAL | [16 empty] | 21783307.44 | 25% | 5445826.86 | 27229134.3

## Pivot Table
Sum of labour cost
type of labour | % labour | Total
Camp Op & Maintenance |  | 888767.56
Engineering |  | 2239431.9579
Equip Maintenance |  | 539904
Equip Op |  | 1403192.0343
Equip Op / Equip Maintenance |  | 1337700
Equip Op / Labour |  | 291352.19
Equip Op / Welders / Labour |  | 293451.338
Labour |  | 8640
Truck Driver |  | 273747.657
(blank) |  | 0
Grand Total |  | 7276186.7372
Sum of labour cost
| % labour of |  | % labour of
type of labour | all-in rate | Total | total labour
Camp Op & Maintenance |  | 888767.56 | 12.21%
Engineering |  | 2239431.9579 | 30.78%
Equip Maintenance |  | 539904 | 7.42%
Equip Op |  | 1403192.0343 | 19.28%
Equip Op / Equip Maintenance |  | 1337700 | 18.38%
Equip Op / Labour |  | 291352.19 | 4.004%
Equip Op / Welders / Labour |  | 293451.338 | 4.033%
Labour |  | 8640 | 0.1187%
Truck Driver |  | 273747.657 | 3.762%
Grand Total |  | 7276186.7372 | 100%
Sum of labour cost
type of labour |  | Total | labour % of total labour cost
Equip Op |  | 2468868.6645 | 33.93%
Labour |  | 330386.8978 | 4.541%
Truck Driver |  | 273747.657 | 3.762%
Equip Maintenance |  | 1074984 | 14.77%
Camp Op & Maintenance |  | 888767.56 | 12.21%
Engineering |  | 2239431.9579 | 30.78%
Total |  | 7276186.7372 | 100%
* Contingency not included.