## Summary
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option H-11032014.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-H | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 10461000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 4898000
| 3.01 | EPCM COSTS |  | 1536000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 16895000
| 4.01 | CONTINGENCY | 25% | 4224000
|  | TOTAL COSTS |  | 21119000

## Detail Costs
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton CAPEX\[307071-00895-Clinton Creek LCCA-Option H-11032014.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Option CC-H | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW
|  | MTO No.: |  | REVISION: | 0
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Edmonton to Dawson City 2,519km. Dawson City to Site approx 110km.2ea-PC2000, 5ea 90ton rock truck, 1ea-345, 1ea-D9, 1ea-963, 7ea-40ton rock trucks, 1ea-grader, 1ea-packer. Second Season Remob: 1ea-345, 1ea-963 | 21 | EA |  | 0 | 0 |  | 0 | 31657.76 | 664812.96 |  | 0 |  | 0 | 664812.96 | 25% | 166203.24 | 831016.2
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Major Road Improvements | 15km |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.05 |  |  | Clear & grub | Medium | 9 | HA |  | 0 | 0 |  | 0 | 11877.51 | 106897.59 |  | 0 |  | 0 | 106897.59 | 25% | 26724.3975 | 133621.9875
1.06 |  |  | Road embankment widening, 3m | Cut to fill existing shoulder. Approx 8M3 / LM. | 120000 | M3 |  | 0 | 0 |  | 0 | 4.63 | 555600 |  | 0 |  | 0 | 555600 | 25% | 138900 | 694500
1.07 |  |  | Re-grade road sub-base | Av. 150mm dp x 5m wide | 11250 | M3 |  | 0 | 0 |  | 0 | 12.57 | 141412.5 |  | 0 |  | 0 | 141412.5 | 25% | 35353.125 | 176765.625
1.08 |  |  | Gravel resurfacing, 100mm thk x 8m wide | Drill & blast, crushing, load & haul and place. | 12000 | M3 |  | 0 | 0 |  | 0 | 161.53 | 1938360 |  | 0 |  | 0 | 1938360 | 25% | 484590 | 2422950
1.09 |  |  | Bridge construction | 15m clear span x 11m w. Supply & install. | 1 | LS |  | 0 | 0 |  | 0 | 889246.4788 | 889246.4788 |  | 0 |  | 0 | 889246.4788 | 25% | 222311.6197 | 1111558.0985
1.1 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.11 |  |  | Bulk Earthworks |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.12 |  |  | Waste dump excavation to channel fill | 1ea-D8 & 1ea-345 ex | 25000 | M3 |  | 0 | 0 |  | 0 | 5.22 | 130500 |  | 0 |  | 0 | 130500 | 25% | 32625 | 163125
1.13 |  |  | Waste dump to porupine pit | Equip Set 1 | 425000 | M3 |  | 0 | 0 |  | 0 | 4.9 | 2082500 |  | 0 |  | 0 | 2082500 | 25% | 520625 | 2603125
1.14 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.15 |  |  | Access Road Construction |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.16 |  |  | Gravel resurfacing, 300mm thk x 6m wide | Drill & blast, crushing, load & haul and place. | 990 | M3 |  | 0 | 0 |  | 0 | 161.53 | 159914.7 |  | 0 |  | 0 | 159914.7 | 25% | 39978.675 | 199893.375
1.17 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.18 |  |  | Channel Armouring |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.19 |  |  | Gabion baskets (3m lg x 1m dp x 0.5m h) | Supply, load, haul, assemble, place | 3800 | EA |  | 0 | 0 |  | 0 | 162.2326 | 616484 |  | 0 |  | 0 | 616484 | 25% | 154121 | 770605
1.2 |  |  | Gabion rock - 100 to 200 mm dia. | Drill & blast, screen & sort, load & haul to site, double handling and place. | 5700 | M3 |  | 0 | 0 |  | 0 | 104.96 | 598272 |  | 0 |  | 0 | 598272 | 25% | 149568 | 747840
1.24 |  |  | Geotextile 10oz | Under cobble layer. | 11000 | M2 |  | 0 | 0 |  | 0 | 3.62 | 39820 |  | 0 |  | 0 | 39820 | 25% | 9955 | 49775
1.21 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.22 |  |  | Water Diversion |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.23 |  |  | Aquadam - supply & install | 6' x 100' lg | 1 | EA |  | 0 | 0 |  | 0 | 26000 | 26000 |  | 0 |  | 0 | 26000 | 25% | 6500 | 32500
1.24 |  |  | 610mm HDPE DR21 pipe | Trench 1.6m dp, BF 1m cover, supply & install. | 900 | LM |  | 0 | 0 |  | 0 | 980.0724 | 882065.16 |  | 0 |  | 0 | 882065.16 | 25% | 220516.29 | 1102581.45
1.25 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.26 |  |  | Support Equipment |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.27 |  |  | Shop truck | 1ea | 106.4 | DY |  | 0 | 0 |  | 0 | 300 | 31920 |  | 0 |  | 0 | 31920 | 25% | 7980 | 39900
1.28 |  |  | Temp maintenance shop | 1ea | 1 | LS |  | 0 | 0 |  | 0 | 15000 | 15000 |  | 0 |  | 0 | 15000 | 25% | 3750 | 18750
1.29 |  |  | Shop trailer | 1ea | 3.5 | MO |  | 0 | 0 |  | 0 | 2000 | 7000 |  | 0 |  | 0 | 7000 | 25% | 1750 | 8750
1.3 |  |  | Fuel bowser | 1ea on-site | 3.5 | MO |  | 0 | 0 |  | 0 | 5000 | 17500 |  | 0 |  | 0 | 17500 | 25% | 4375 | 21875
1.31 |  |  | Pick-up trucks | 6ea | 106.4 | DY |  | 0 | 0 |  | 0 | 900 | 95760 |  | 0 |  | 0 | 95760 | 25% | 23940 | 119700
1.32 |  |  | Portable light towers | 6ea | 3.5 | MO |  | 0 | 0 |  | 0 | 22440 | 78540 |  | 0 |  | 0 | 78540 | 25% | 19635 | 98175
1.33 |  |  | Generator | 6ea | 3.5 | MO |  | 0 | 0 |  | 0 | 7920 | 27720 |  | 0 |  | 0 | 27720 | 25% | 6930 | 34650
1.34 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.35 |  |  | Support Labour | *During Road Improvements, Quarry Development & Creek Stabiliztion Work. |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.36 |  |  | Heavy duty mechanic | 1ea/shift | 60.8 | DY |  | 0 | 0 |  | 0 | 2640 | 160512 |  | 0 |  | 0 | 160512 | 25% | 40128 | 200640
1.37 |  |  | Welder | 1ea/shift | 60.8 | DY |  | 0 | 0 |  | 0 | 2640 | 160512 |  | 0 |  | 0 | 160512 | 25% | 40128 | 200640
1.38 |  |  | Labourer | 2ea/shift | 121.6 | DY |  | 0 | 0 |  | 0 | 1800 | 218880 |  | 0 |  | 0 | 218880 | 25% | 54720 | 273600
1.39 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.37 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.38 |  |  | Equipment washdown facilites | 1ea - 80'x120' temprorary building , 300mm SOG, 4ea - 4.5 GPM pressure washers w/ 600Gal tanks, 4man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 752453.024 | 752453.024 |  | 0 |  | 0 | 752453.024 | 25% | 188113.256 | 940566.28
1.39 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 21000 | 21000 |  | 0 |  | 0 | 21000 | 25% | 5250 | 26250
1.4 |  |  | PPE; respirators, overalls |  | 50 | EA |  | 0 | 0 |  | 0 | 500 | 25000 |  | 0 |  | 0 | 25000 | 25% | 6250 | 31250
1.41 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.4 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.41 |  |  | Fuel truck & driver | 27,000 liter tanker | 24.5838 | LD |  | 0 | 0 |  | 0 | 685.6 | 16854.6634 |  | 0 |  | 0 | 16854.6634 | 25% | 4213.6659 | 21068.3293
1.42 |  |  |  | *fuel included in all-in rates. | 663763 | liters |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.43 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.44 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 10460537.0762 |  | 0 | 0% | 0 | 10460537.0762 | 25% | 2615134.2691 | 13075671.3453
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | 40 man temporary camp x 5.25mo. | 6384 | MDY |  | 0 | 0 |  | 0 | 493.92 | 3153185.28 |  | 0 |  | 0 | 3153185.28 | 25% | 788296.32 | 3941481.6
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 3% |  |  | 0 | 0 |  | 0 | 10460537.0762 | 313816.1123 |  | 0 |  | 0 | 313816.1123 | 25% | 78454.0281 | 392270.1404
2.03 |  |  | ROAD MAINTENANCE | 1ea Grader 12hrs/day | 152 | DY |  | 0 | 0 |  | 0 | 2677.2 | 406934.4 |  | 0 |  | 0 | 406934.4 | 25% | 101733.6 | 508668
2.04 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.05 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | CONTRACTOR LOA AND TRAVEL | Edm to Dawson City charter flight + DC to Site by charter bus. 1 flight/man every two weeks. | 480 | Round Trip |  | 0 | 0 |  | 0 | 1144 | 549120 |  | 0 |  | 0 | 549120 | 25% | 137280 | 686400
2.08 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.09 |  |  | TRANSPORTATION AND FREIGHT | HDPE pipe & aquadam. | 6 | LD |  | 0 | 0 |  | 0 | 9361.68 | 56170.08 |  | 0 |  | 0 | 56170.08 | 25% | 14042.52 | 70212.6
2.1 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.11 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 10460537.0762 | 209210.7415 |  | 0 |  | 0 | 209210.7415 | 25% | 52302.6854 | 261513.4269
2.14 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS |  | 2% |  |  | 0 | 0 |  | 0 | 10460537.0762 | 209210.7415 |  | 0 |  | 0 | 209210.7415 | 25% | 52302.6854 | 261513.4269
2.15 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.16 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 4897647.3553 |  | 0 | 0% | 0 | 4897647.3553 | 25% | 1224411.8388 | 6122059.1942
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 15358184.4316 | 1535818.4432 |  | 0 |  | 0 | 1535818.4432 | 25% | 383954.6108 | 1919773.0539
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 1535818.4432 |  | 0 | 0% | 0 | 1535818.4432 | 25% | 383954.6108 | 1919773.0539
| TOTAL | [16 empty] | 16894002.8747 | 25% | 4223500.7187 | 21117503.5934

## Pivot Table
Sum of labour cost
type of labour | % labour | Total
Camp Op & Maintenance |  | 630637.056
Engineering |  | 1705077.0278
Equip Maintenance |  | 539904
Equip Op |  | 1488198.6877
Equip Op / Equip Maintenance |  | 730290
Equip Op / Labour |  | 472294.7312
Equip Op / Welders / Labour |  | 293451.338
Labour |  | 75245.3024
Truck Driver |  | 262456.8621
(blank) |  | 0
Grand Total |  | 6197555.0052
| % labour of |  | % labour of
type of labour | all-in rate | Total | total labour
Camp Op & Maintenance |  | 630637.056 | 10.18%
Engineering |  | 1705077.0278 | 27.51%
Equip Maintenance |  | 539904 | 8.712%
Equip Op |  | 1488198.6877 | 24.01%
Equip Op / Equip Maintenance |  | 730290 | 11.78%
Equip Op / Labour |  | 472294.7312 | 7.621%
Equip Op / Welders / Labour |  | 293451.338 | 4.735%
Labour |  | 75245.3024 | 1.214%
Truck Driver |  | 262456.8621 | 4.235%
Grand Total |  | 6197555.0052 | 100%
Sum of labour cost
type of labour |  | Total | labour % of total labour cost
Equip Op |  | 2279900.5885 | 36.79%
Labour |  | 487463.4708 | 7.865%
Truck Driver |  | 262456.8621 | 4.235%
Equip Maintenance |  | 832020 | 13.42%
Camp Op & Maintenance |  | 630637.056 | 10.18%
Engineering |  | 1705077.0278 | 27.51%
Total |  | 6197555.0052 | 100%
* Contingency not included.