## Summary
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton OPEX\[307071-00895-Clinton Creek LCCA-DS Repair 12ea-15012014.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Repair 12 Drop Structures | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 652000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 242000
| 3.01 | EPCM COSTS |  | 89000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 983000
| 4.01 | CONTINGENCY | 25.03% | 246000
|  | TOTAL COSTS |  | 1229000

## Detail Costs
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton OPEX\[307071-00895-Clinton Creek LCCA-DS Repair 12ea-15012014.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Repair 12 Drop Structures | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW | [5 empty] | USE hourly rate:
|  | MTO No.: |  | REVISION: | 0 | [5 empty] | 100
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | SubcontractTotal ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Whitehorse to Dawson City 1,284km. Dawson City to Site approx 110km. Bobcat, Loader. | 1 | EA |  | 0 | 0 |  | 0 | 10000 | 10000 |  | 0 |  | 0 | 10000 | 25% | 2500 | 12500
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Drop Structures (12ea): |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.05 |  |  | Maintenance work | Bobcat & Loader + 6men | 66 | Day |  | 0 | 0 |  | 0 | 8500.5 | 561033 |  | 0 |  | 0 | 561033 | 25% | 140258.25 | 701291.25
1.06 |  |  | Gabion rock material | 10% of original rock volume replaced | 276 | M3 |  | 0 | 0 |  | 0 | 175.0252 | 48306.9577 |  | 0 |  | 0 | 48306.9577 | 25% | 12076.7394 | 60383.6971
1.07 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.08 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.09 |  |  | Equipment washdown equip & labour | Assume existing building of 1ea - 80'x120' temprorary building , 300mm SOG. 1ea - 4.5 GPM pressure washers w/ 600Gal tanks, 2man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 22544 | 22544 |  | 0 |  | 0 | 22544 | 25% | 5636 | 28180
1.1 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 3000 | 3000 |  | 0 |  | 0 | 3000 | 25% | 750 | 3750
1.11 |  |  | PPE; respirators, overalls |  | 20 | EA |  | 0 | 0 |  | 0 | 300 | 6000 |  | 0 |  | 0 | 6000 | 25% | 1500 | 7500
1.12 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.13 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.14 |  |  | Truck & Driver | 27,000 liter tanker | 2 | Load |  | 0 | 0 |  | 0 | 685.6 | 1371.2 |  | 0 |  | 0 | 1371.2 | 25% | 342.8 | 1714
1.15 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.16 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.17 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 652255.1577 |  | 0 | 0% | 0 | 652255.1577 | 25% | 163063.7894 | 815318.9471
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | RV rental, 2men per unit + per diem. 10men x 66 days. | 660 | MDY |  | 0 | 0 |  | 0 | 255 | 168300 |  | 0 |  | 0 | 168300 | 25% | 42075 | 210375
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 5% |  |  | 0 | 0 |  | 0 | 815318.9471 | 40765.9474 |  | 0 |  | 0 | 40765.9474 | 25% | 10191.4868 | 50957.4342
2.03 |  |  | SNOW REMOVAL |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.04 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.05 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | CONTRACTOR LOA AND TRAVEL | 4 return trips x 7 men. Edm to Dawson City (Flight) to Site (Charter Bus). | 28 | Round Trip |  | 0 | 0 |  | 0 | 1184 | 33152 |  | 0 |  | 0 | 33152 | 25% | 8288 | 41440
2.08 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.09 |  |  | TRANSPORTATION AND FREIGHT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.1 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.11 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  |  |  |  | 0 | 0 |  | 0 | 815318.9471 | 0 |  | 0 |  | 0 | 0 | 25% | 0 | 0
2.14 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.15 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.16 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 242217.9474 |  | 0 | 0% | 0 | 242217.9474 | 25% | 60554.4868 | 302772.4342
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 894473.105 | 89447.3105 |  | 0 |  | 0 | 89447.3105 | 25% | 22361.8276 | 111809.1381
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 89447.3105 |  | 0 | 0% | 0 | 89447.3105 | 25% | 22361.8276 | 111809.1381
| TOTAL | [16 empty] | 983920.4155 | 25% | 245980.1039 | 1229900.5194

## Basis of Estimate
BASIS OF ESTIMATE
| PROJECT DETAILS: | Gabion drop structures repair.
| CLIENT: | Assessment and Abandoned Mines
| PROJECT TITLE: | Clinton Creek Site LCCA - Repair 12 Drop Structures
| PROJ # (GBS): | 307071-00895
DOC NUMBER:
| ACCURACY LEVEL: | +/-50%
| DATE: | 2014-03-28
SCOPE OF ESTIMATE:
Construction cost estimate to provide repairs to 12 drop structures. Indirect costs such as camp, monitoring and travel were also included.
REFERENCE DOCUMENTS:
- Email from Stephen Clark, Nov 07, 2013.
KEY QUALIFICATIONS
- All work will be performed over 66 day period in the summer, no down time has been factored into costs.
Utilized Equipment:
- 1ea - bob cat, 1ea - wheel loader.
- All required aggregates will been produced and stock-piled on-site previously.
- Workforce will be flown into Dawson City from Edmonton, AB, then by chartered bus to site.
- All heavy equipment, camp and facilities will be able to cross the river via existing ferry or ice bridge.
- 10 man camp has been allowed for to accommodate all contractor, engineering and owner field personnel for 66 day construction period.
- All equipment, camp and facilities will be able to be demobilized from site after completion of the project.
ASSUMPTIONS OF COST ESTIMATE
- All equipment mobilized to site from Whitehorse, YT through Dawson City.
- Sufficient site preparations have been completed previously to accommodate camp and site facilities.
EXCLUSIONS FROM COST ESTIMATE
- Clearing & grubbing over waste dump excavation area.
- Drill & blast, sorting/screening and load and hauling from quarry to site.
- Dewatering
- Snow removal
- Demolition, removal, disposal and/or relocation of existing structures and facilities.
- Traffic safety and control to existing site road.
- Lost time to severe weather or force majeure.
- Costs related to environmental habitat compensation and social impacts.
- Extended periods of industrial / labour unrest.
- First nations contracts or work agreements.
- All permitting and associated costs.
- Geotechnical investigations and recommendations.
- Environmental monitoring
- Construction insurance
- Escalation
- All Owners costs
- All taxes and duties
QUANTITY DERIVATION
- Material take-offs provided by engineering discipline(s) and the estimator.
COST BASIS
- Earthwork rates derived from minning models and built-up earthwork calculations utiliziting BC Road Builder rates and historical data.
- Rates include all labour and equipment costs to operate and maintain equipment, including all contractor overhead, profit and indirects; supervision, survey, support equipment.
- Diesel fuel rate of $1.60/liter allowed for all earthwork based on Yukon Government - Energy, Mines and Resources, surveyed October 30, 2013.
- Fuel consumption rates and maintainence costs obtained from historic data or interpolated.
LABOUR RATES
- Average operator rate of approximately $50/hr allowed for within all earthwork unit costs. Based on AB CLRA Collective Agreements (2011 - 2015).
- Work will commence using 40hr work week, with 14 days on and 7 days off.
INDIRECTS:
- Contractor indirect costs have been included within all direct costs.
- A 10 man temporary camp has been allowed for the duration of the work. Camp costs were estimated from quotes and historical data base.
- Flights for a 7 man turnaround every two weeks for 66 days has been allowed for site personnel.
- An allowance of 5% of the total direct cost has been included for contractor Temporary Facilities.