## Summary
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton OPEX\[307071-00895-Clinton Creek LCCA-DS Replace 2ea-15012014.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Replace 2 Drop Structures | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 543000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 363000
| 3.01 | EPCM COSTS |  | 91000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 997000
| 4.01 | CONTINGENCY | 24.97% | 249000
|  | TOTAL COSTS |  | 1246000

## Detail Costs
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton OPEX\[307071-00895-Clinton Creek LCCA-DS Replace 2ea-15012014.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Replace 2 Drop Structures | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW | [5 empty] | USE hourly rate:
|  | MTO No.: |  | REVISION: | 0 | [5 empty] | 100
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Whitehorse to Dawson City 1,284km round trip. Dawson City to Site approx 110km. Excavator, Loader. | 2 | EA |  | 0 | 0 |  | 0 | 10000 | 20000 |  | 0 |  | 0 | 20000 | 25% | 5000 | 25000
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Drop Structures (2ea): | Assume 230M3 per drop structure. |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.05 |  |  | Demolish existing drop structure (2ea) |  | 14 | Day |  | 0 | 0 |  | 0 | 9980 | 139720 |  | 0 |  | 0 | 139720 | 25% | 34930 | 174650
1.06 |  |  | Install new drop structure (2ea) | Excavator & Loader + 6men | 28 | Day |  | 0 | 0 |  | 0 | 9980 | 279440 |  | 0 |  | 0 | 279440 | 25% | 69860 | 349300
1.07 |  |  | Geotextile 10oz | Under cobble layer. | 1400 | M2 |  | 0 | 0 |  | 0 | 3.62 | 5068 |  | 0 |  | 0 | 5068 | 25% | 1267 | 6335
1.08 |  |  | Gabion rock material | incl salvage 50% rock. | 230 | M3 |  | 0 | 0 |  | 0 | 175.0252 | 40255.7981 |  | 0 |  | 0 | 40255.7981 | 25% | 10063.9495 | 50319.7476
1.09 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.1 |  |  | Water Management
1.11 |  |  | Aquadam - supply & install | 6' x 100' lg | 1 | EA |  | 0 | 0 |  | 0 | 26000 | 26000 |  | 0 |  | 0 | 26000 | 25% | 6500 | 32500
1.12 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.13 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.14 |  |  | Equipment washdown equip & labour | Assume existing building of 1ea - 80'x120' temprorary building , 300mm SOG. 1ea - 4.5 GPM pressure washers w/ 600Gal tanks, 2man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 22544 | 22544 |  | 0 |  | 0 | 22544 | 25% | 5636 | 28180
1.15 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 3000 | 3000 |  | 0 |  | 0 | 3000 | 25% | 750 | 3750
1.16 |  |  | PPE; respirators, overalls |  | 20 | EA |  | 0 | 0 |  | 0 | 300 | 6000 |  | 0 |  | 0 | 6000 | 25% | 1500 | 7500
1.17 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.18 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.19 |  |  | Truck & Driver | 27,000 liter tanker | 2 | Load |  | 0 | 0 |  | 0 | 685.6 | 1371.2 |  | 0 |  | 0 | 1371.2 | 25% | 342.8 | 1714
1.2 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.21 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 543398.9981 |  | 0 | 0% | 0 | 543398.9981 | 25% | 135849.7495 | 679248.7476
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | RV rental, 2men per unit + per diem. 15men x 60 days. | 900 | MDY |  | 0 | 0 |  | 0 | 255 | 229500 |  | 0 |  | 0 | 229500 | 25% | 57375 | 286875
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 5% |  |  | 0 | 0 |  | 0 | 679248.7476 | 33962.4374 |  | 0 |  | 0 | 33962.4374 | 25% | 8490.6093 | 42453.0467
2.03 |  |  | SNOW REMOVAL | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.04 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.05 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | CONTRACTOR LOA AND TRAVEL | 5 return trips x 15 men. Edm to Dawson City (Flight) to Site (Charter Bus). | 75 | Round Trip |  | 0 | 0 |  | 0 | 1144 | 85800 |  | 0 |  | 0 | 85800 | 25% | 21450 | 107250
2.08 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.09 |  |  | TRANSPORTATION AND FREIGHT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.1 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.11 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 679248.7476 | 13584.975 |  | 0 |  | 0 | 13584.975 | 25% | 3396.2437 | 16981.2187
2.14 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.15 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.16 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 362847.4123 |  | 0 | 0% | 0 | 362847.4123 | 25% | 90711.8531 | 453559.2654
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 906246.4104 | 90624.641 |  | 0 |  | 0 | 90624.641 | 25% | 22656.1603 | 113280.8013
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 90624.641 |  | 0 | 0% | 0 | 90624.641 | 25% | 22656.1603 | 113280.8013
| TOTAL | [16 empty] | 996871.0514 | 25% | 249217.7629 | 1246088.8143

## Basis of Estimate
BASIS OF ESTIMATE
| PROJECT DETAILS: | Gabion drop structures replacement.
| CLIENT: | Assessment and Abandoned Mines
| PROJECT TITLE: | Clinton Creek Site LCCA - Replace 2 Drop Structures
| PROJ # (GBS): | 307071-00895
DOC NUMBER:
| ACCURACY LEVEL: | +/-50%
| DATE: | 2014-03-28
SCOPE OF ESTIMATE:
Construction cost estimate to replace two gabion drop structures. This cost estimate includes labour and equipment to demolish existing drop structures and replacement. Indirect costs such as camp, monitoring and travel were also included.
REFERENCE DOCUMENTS:
- Email from Stephen Clark, Nov 07, 2013
KEY QUALIFICATIONS
- One gabion drop structure can be demolished and replaced in 30 days.
- One drop structure requires 230 cubic meters of gabion rock.
- New gabion rock material will have been stock-piled on site previously.
- Half of the gabion rock from the existing drop structures will be salvageable for re-use.
- All work will be performed in single 12hr shifts over 56 day period in the summer, no down time has been factored into costs.
Utilized Equipment:
- 1ea - 45ton excavator, 1ea - wheel loader.
- Workforce will be flown into Dawson City from Edmonton, AB, then transported to site by chartered bus.
- All heavy equipment, camp and facilities will be able to cross the river via existing ferry.
- 15 man camp has been allowed for to accommodate all contractor, engineering and owner field personnel for 56 day construction period.
- All equipment, camp and facilities will be able to be demobilized from site after completion of the project.
ASSUMPTIONS OF COST ESTIMATE
- All earthwork equipment mobilized to site from Whitehorse YT through Dawson City.
- Sufficient site preparations have been completed previously to accommodate camp and site facilities.
EXCLUSIONS FROM COST ESTIMATE
- Clearing & grubbing over waste dump excavation area.
- Drill & blast, sorting/screening and load and hauling from quarry to site.
- Dewatering
- Snow removal
- Demolition, removal, disposal and/or relocation of existing structures and facilities other than existing drop structures being replaced.
- Road improvements to existing site road.
- Traffic safety and control to existing site road.
- Lost time to severe weather of force majeure.
- Costs related to environmental habitat compensation and social impacts.
- Extended periods of industrial / labour unrest.
- First nations contracts or work agreements.
- All permitting and associated costs.
- Geotechnical investigations and recommendations.
- Construction insurance
- Escalation
- All Owners costs
- All taxes and duties
QUANTITY DERIVATION
- Material take-offs provided by engineering discipline(s) and the estimator.
COST BASIS
- Earthwork rates derived from minning models and built-up earthwork calculations utiliziting BC Road Builder rates and historical data.
- Rates include all labour and equipment costs to operate and maintain equipment, including all contractor overhead, profit and indirects; supervision, survey, support equipment.
- Diesel fuel rate of $1.60/liter allowed for all earthwork based on Yukon Government - Energy, Mines and Resources, surveyed October 30, 2013.
- Fuel consumption rates and maintainence costs obtained from historic data or interpolated.
LABOUR RATES
- Average operator rate of approximately $50/hr allowed for within all earthwork unit costs. Based on AB CLRA Collective Agreements (2011 - 2015).
- Work will commence using 40hrs per week, with 14 days on and 7 days off.
INDIRECTS:
- Contractor indirect costs have been included within all direct costs.
- A 15 man temporary camp has been allowed for the duration of the work. Camp costs were estimated from quotes and historical data base.
- Flights for a 15 man turnaround every two weeks for 56 days has been allowed for site personnel.
- An allowance of 5% of the total direct cost has been included for contractor Temporary Facilities.
- An allowance of 2% of the total direct cost has been included for Environmental Monitoring and Testing.