## Summary
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton OPEX\[307071-00895-Clinton Creek LCCA-Replace 550 m Gabion-Lined Channel.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Replace 550 m of Gabion-Lined Channel (Clinton Options G and H) | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 2883000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 356000
| 3.01 | EPCM COSTS |  | 324000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 3563000
| 4.01 | CONTINGENCY | 25.01% | 891000
|  | TOTAL COSTS |  | 4454000

## Detail Costs
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton OPEX\[307071-00895-Clinton Creek LCCA-Replace 550 m Gabion-Lined Channel.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Replace 550 m of Gabion-Lined Channel (Clinton Options G and H) | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW
|  | MTO No.: |  | REVISION: | 0
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Edmonton to Dawson City 2,519km. Dawson City to Site approx 110km.2ea-345, 1ea-963, 7ea-40ton rock trucks. | 10 | EA |  | 0 | 0 |  | 0 | 18723.36 | 187233.6 |  | 0 |  | 0 | 187233.6 | 25% | 46808.4 | 234042
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.07 |  |  | Gabions |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.08 |  |  | Gabion baskets (3m lg x 1m dp x 0.5m h) | Supply, load, haul, assemble, place | 3800 | EA |  | 0 | 0 |  | 0 | 294.1474 | 1117760 |  | 0 |  | 0 | 1117760 | 25% | 279440 | 1397200
1.09 |  |  | Gabion rock - 100 to 200 mm dia. | Drill & blast, screen & sort, load & haul to site, double handling and place. | 5700 | M3 |  | 0 | 0 |  | 0 | 104.96 | 598272 |  | 0 |  | 0 | 598272 | 25% | 149568 | 747840
1.1 |  |  | Geotextile 10oz | Under cobble layer. | 11000 | M2 |  | 0 | 0 |  | 0 | 3.62 | 39820 |  | 0 |  | 0 | 39820 | 25% | 9955 | 49775
1.1 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.17 |  |  | Water Diversion |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.18 |  |  | Aquadam - supply & install | 6' x 100' lg. | 1 | EA |  | 0 | 0 |  | 0 | 26000 | 26000 |  | 0 |  | 0 | 26000 | 25% | 6500 | 32500
1.19 |  |  | 610mm HDPE DR21 pipe | Trench 1.6m dp, BF 1m cover, supply & install. | 900 | LM |  | 0 | 0 |  | 0 | 980.0724 | 882065.16 |  | 0 |  | 0 | 882065.16 | 25% | 220516.29 | 1102581.45
1.2 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.21 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.22 |  |  | Equipment washdown equip & labour | Assume existing building of 1ea - 80'x120' temprorary building , 300mm SOG. 1ea - 4.5 GPM pressure washers w/ 600Gal tanks, 2man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 22544 | 22544 |  | 0 |  | 0 | 22544 | 25% | 5636 | 28180
1.23 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 3000 | 3000 |  | 0 |  | 0 | 3000 | 25% | 750 | 3750
1.24 |  |  | PPE; respirators, overalls |  | 20 | EA |  | 0 | 0 |  | 0 | 300 | 6000 |  | 0 |  | 0 | 6000 | 25% | 1500 | 7500
1.25 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.26 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.27 |  |  | Fuel truck & driver | 27,000 liter tanker | 1 | LD |  | 0 | 0 |  | 0 | 685.6 | 685.6 |  | 0 |  | 0 | 685.6 | 25% | 171.4 | 857
1.28 |  |  |  | *fuel included in all-in rates. | 27000 | liters |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.29 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.3 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 2883380.36 |  | 0 | 0% | 0 | 2883380.36 | 25% | 720845.09 | 3604225.45
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | RV rental, 2men per unit + per diem. Aquadam & HDPE, drill & blast, crush, load & haul, place gabions. | 183 | MDY |  | 0 | 0 |  | 0 | 255 | 46665 |  | 0 |  | 0 | 46665 | 25% | 11666.25 | 58331.25
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 3% |  |  | 0 | 0 |  | 0 | 3604225.45 | 108126.7635 |  | 0 |  | 0 | 108126.7635 | 25% | 27031.6909 | 135158.4544
2.03 |  |  | SNOW REMOVAL | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.03 |  |  | ROAD MAINTENANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.04 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.05 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | CONTRACTOR LOA AND TRAVEL | Edm to Dawson City charter flight + DC to Site by charter bus. 1 flight/man. | 24 | Round Trip |  | 0 | 0 |  | 0 | 1144 | 27456 |  | 0 |  | 0 | 27456 | 25% | 6864 | 34320
2.07 |  |  | CONTRACTOR LOA AND TRAVEL | Dawson City to Site - 15 passenger shuttle bus. | 45 | Round Trip |  | 0 | 0 |  | 0 | 1011.6 | 45522 |  | 0 |  | 0 | 45522 | 25% | 11380.5 | 56902.5
2.08 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.09 |  |  | TRANSPORTATION AND FREIGHT | HDPE pipe & aquadam. | 6 | LD |  | 0 | 0 |  | 0 | 9361.68 | 56170.08 |  | 0 |  | 0 | 56170.08 | 25% | 14042.52 | 70212.6
2.1 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.11 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 3604225.45 | 72084.509 |  | 0 |  | 0 | 72084.509 | 25% | 18021.1273 | 90105.6363
2.14 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.15 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.16 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 356024.3525 |  | 0 | 0% | 0 | 356024.3525 | 25% | 89006.0881 | 445030.4406
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 3239404.7125 | 323940.4713 |  | 0 |  | 0 | 323940.4713 | 25% | 80985.1178 | 404925.5891
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 323940.4713 |  | 0 | 0% | 0 | 323940.4713 | 25% | 80985.1178 | 404925.5891
| TOTAL | [16 empty] | 3563345.1837 | 25% | 890836.2959 | 4454181.4797