## Summary
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton OPEX\[307071-00895-Clinton Creek LCCA-Replace DS4 Armouring.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Replace Drop Structure 4 Armouring (Clinton Option A) | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 736000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 190000
| 3.01 | EPCM COSTS |  | 93000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 1019000
| 4.01 | CONTINGENCY | 25.02% | 255000
|  | TOTAL COSTS |  | 1274000

## Detail Costs
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Clinton OPEX\[307071-00895-Clinton Creek LCCA-Replace DS4 Armouring.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Replace Drop Structure 4 Armouring (Clinton Option A) | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW
|  | MTO No.: |  | REVISION: | 0
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Edmonton to Dawson City 2,519km. Dawson City to Site approx 110km.2ea-345, 1ea-963, 7ea-40ton rock trucks. | 10 | EA |  | 0 | 0 |  | 0 | 18723.36 | 187233.6 |  | 0 |  | 0 | 187233.6 | 25% | 46808.4 | 234042
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Channel Armouring |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.05 |  |  | Rip-rap - 800 mm dia. | Drill & blast, screen & sort, load & haul to site, double handling and place. | 3400 | M3 |  | 0 | 0 |  | 0 | 139.7 | 474980 |  | 0 |  | 0 | 474980 | 25% | 118745 | 593725
1.06 |  |  | Waste rock | 1ea-D8 & 1ea-345 ex | 3000 | M3 |  | 0 | 0 |  | 0 | 5.22 | 15660 |  | 0 |  | 0 | 15660 | 25% | 3915 | 19575
1.07 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.08 |  |  | Water Diversion |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.09 |  |  | Aquadam - supply & install | 6' x 100' lg | 1 | EA |  | 0 | 0 |  | 0 | 26000 | 26000 |  | 0 |  | 0 | 26000 | 25% | 6500 | 32500
1.09 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.1 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.11 |  |  | Equipment washdown equip & labour | Assume existing building of 1ea - 80'x120' temprorary building , 300mm SOG. 1ea - 4.5 GPM pressure washers w/ 600Gal tanks, 2man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 22544 | 22544 |  | 0 |  | 0 | 22544 | 25% | 5636 | 28180
1.12 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 3000 | 3000 |  | 0 |  | 0 | 3000 | 25% | 750 | 3750
1.13 |  |  | PPE; respirators, overalls |  | 20 | EA |  | 0 | 0 |  | 0 | 300 | 6000 |  | 0 |  | 0 | 6000 | 25% | 1500 | 7500
1.1 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.11 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.12 |  |  | Fuel truck & driver | 27,000 liter tanker | 1 | LD |  | 0 | 0 |  | 0 | 685.6 | 685.6 |  | 0 |  | 0 | 685.6 | 25% | 171.4 | 857
1.13 |  |  |  | *fuel included in all-in rates. | 27000 | liters |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.14 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.15 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 736103.2 |  | 0 | 0% | 0 | 736103.2 | 25% | 184025.8 | 920129
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | RV rental, 2men per unit + per diem. Aquadam & HDPE, drill & blast, crush, load & haul, place gabions. | 94 | MDY |  | 0 | 0 |  | 0 | 255 | 23970 |  | 0 |  | 0 | 23970 | 25% | 5992.5 | 29962.5
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 3% |  |  | 0 | 0 |  | 0 | 920129 | 27603.87 |  | 0 |  | 0 | 27603.87 | 25% | 6900.9675 | 34504.8375
2.03 |  |  | SNOW REMOVAL | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.04 |  |  | ROAD MAINTENANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.05 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.07 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.08 |  |  | CONTRACTOR LOA AND TRAVEL | Edm to Dawson City charter flight + DC to Site by charter bus. 1 flight/man. | 24 | Round Trip |  | 0 | 0 |  | 0 | 1144 | 27456 |  | 0 |  | 0 | 27456 | 25% | 6864 | 34320
2.09 |  |  | CONTRACTOR LOA AND TRAVEL | Dawson City to Site - 15 passenger shuttle bus. | 36 | Round Trip |  | 0 | 0 |  | 0 | 1011.6 | 36417.6 |  | 0 |  | 0 | 36417.6 | 25% | 9104.4 | 45522
2.1 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.11 |  |  | TRANSPORTATION AND FREIGHT | HDPE pipe & aquadam. | 6 | LD |  | 0 | 0 |  | 0 | 9361.68 | 56170.08 |  | 0 |  | 0 | 56170.08 | 25% | 14042.52 | 70212.6
2.12 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.13 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.14 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.15 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 920129 | 18402.58 |  | 0 |  | 0 | 18402.58 | 25% | 4600.645 | 23003.225
2.16 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.17 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.18 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 190020.13 |  | 0 | 0% | 0 | 190020.13 | 25% | 47505.0325 | 237525.1625
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 926123.33 | 92612.333 |  | 0 |  | 0 | 92612.333 | 25% | 23153.0832 | 115765.4162
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 92612.333 |  | 0 | 0% | 0 | 92612.333 | 25% | 23153.0832 | 115765.4162
| TOTAL | [16 empty] | 1018735.663 | 25% | 254683.9157 | 1273419.5787