## Summary
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Wolverine OPEX\[307071-00895-Clinton Creek LCCA-Excavate Rock Drain Sediment.xls]Summary
ESTIMATE - SUMMARY
| CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
| PROJECT TITLE: | Clinton Creek Site LCCA - Excavate Rock Drain Sediment (Wolverine Options B, D and E) | ACCURACY: | +/-50%
| PROJECT No.: | 307071-00895 | AUTHOR: | MW
| MTO No.: |  | REVISION:
| REFERENCE | DESCRIPTION |  | TOTAL COST
| 1 | DIRECT CONSTRUCTION COSTS (see detail sheet for breakdown) |  | 209000
| 2 | INDIRECT COSTS (see detail sheet for breakdown) |  | 48000
| 3.01 | EPCM COSTS |  | 32000
| 3.02 | OWNERS COSTS |  | 0
| 3.03 | ESCALATION |  | 0
|  | SUB TOTAL COSTS |  | 289000
| 4.01 | CONTINGENCY | 24.91% | 72000
|  | TOTAL COSTS |  | 361000

## Detail Costs
U:\YVR\307071\00895_YEMR_ClintonCrk\02_Rpts\11_Eng-Tech_Rpt_and_Studies\307071-00895-00-WR-REP-0001_Rev0\Excel and CAD files\Appendix 3\Wolverine OPEX\[307071-00895-Clinton Creek LCCA-Excavate Rock Drain Sediment.xls]Detail Costs
ESTIMATE - DIRECT/INDIRECT/OTHER CONSTRUCTION COSTS DETAIL
|  | CLIENT: | Assessment and Abandoned Mines | DATE: | 2014-03-28
|  | PROJECT TITLE: | Clinton Creek Site LCCA - Excavate Rock Drain Sediment (Wolverine Options B, D and E) | ACCURACY: | +/-50%
|  | PROJECT No.: | 307071-00895 | AUTHOR: | MW
|  | MTO No.: |  | REVISION: | 0
| Area / WBS | Sub Area | Description | Remarks | Qty | Unit | Mhr/Unit | Mhr Total | Mhr Cost ($) | Material/Unit ($) | Material Total ($) | Subcontract Costs/Unit ($) | Subcontract Total ($) | Other/Unit ($) | Other Total ($) | Allowance % | Allowance ($) | Sub Total ($) | Contingency % | Contingency ($) | Total ($)
DIRECT COSTS
1.01 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.02 |  |  | Equipment Mob / Demob | Edmonton to Dawson City 2,519km. Dawson City to Site approx 110km. 1ea-345ex, 1ea-wheel loader, 1ea-40ton rock truck, 1ea-grader. | 4 | EA |  | 0 | 0 |  | 0 | 18723.36 | 74893.44 |  | 0 |  | 0 | 74893.44 | 25% | 18723.36 | 93616.8
1.03 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.04 |  |  | Excavate Sediment Trap |  | 2000 | M3 |  | 0 | 0 |  | 0 | 15.69 | 31380 |  | 0 |  | 0 | 31380 | 25% | 7845 | 39225
1.05 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.06 |  |  | Water Management |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.07 |  |  | Aquadam - supply & install | 6' x 100' lg. | 2 | EA |  | 0 | 0 |  | 0 | 26000 | 52000 |  | 0 |  | 0 | 52000 | 25% | 13000 | 65000
1.08 |  |  | Pumps, hoses, fuel & maintainence | 150mm submersible | 4 | EA |  | 0 | 0 |  | 0 | 4643.6 | 18574.4 |  | 0 |  | 0 | 18574.4 | 25% | 4643.6 | 23218
1.09 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.1 |  |  | Asbestos Control |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.11 |  |  | Equipment washdown equip & labour | Assume existing building of 1ea - 80'x120' temprorary building , 300mm SOG. 1ea - 4.5 GPM pressure washers w/ 600Gal tanks, 2man hours / day. | 1 | EA |  | 0 | 0 |  | 0 | 22544 | 22544 |  | 0 |  | 0 | 22544 | 25% | 5636 | 28180
1.12 |  |  | Equipment / vehicle heppa filters, |  | 1 | LS |  | 0 | 0 |  | 0 | 3000 | 3000 |  | 0 |  | 0 | 3000 | 25% | 750 | 3750
1.13 |  |  | PPE; respirators, overalls |  | 20 | EA |  | 0 | 0 |  | 0 | 300 | 6000 |  | 0 |  | 0 | 6000 | 25% | 1500 | 7500
1.14 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.15 |  |  | Fuel Transportation | Transport from Dawson City to site (approx 110km one-way). |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.16 |  |  | Fuel truck & driver | 27,000 liter tanker | 0.93333 | LD |  | 0 | 0 |  | 0 | 685.6 | 639.8933 |  | 0 |  | 0 | 639.8933 | 25% | 159.9733 | 799.8667
1.17 |  |  |  | *fuel included in all-in rates. | 25200 | liters |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.18 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
1.19 | [7 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| DIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 209031.7333 |  | 0 | 0% | 0 | 209031.7333 | 25% | 52257.9333 | 261289.6667
INDIRECT COSTS
2.01 |  |  | TEMPORARY CONSTRUCTION CAMP | RV rental, 2men per unit + per diem. | 70 | MDY |  | 0 | 0 |  | 0 | 255 | 17850 |  | 0 |  | 0 | 17850 | 25% | 4462.5 | 22312.5
2.02 |  |  | TEMPORARY FACILITIES AND CONSTRUCTION SITE SERVICES |  | 3% |  |  | 0 | 0 |  | 0 | 261289.6667 | 7838.69 |  | 0 |  | 0 | 7838.69 | 25% | 1959.6725 | 9798.3625
2.03 |  |  | OVERTIME PREMIUM FOR COMPRESSED WORK WEEK | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.04 |  |  | NON-PRODUCTIVE TIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.05 |  |  | SPOT OVERTIME | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.06 |  |  | CONTRACTOR LOA AND TRAVEL | Edm to Dawson City charter flight + DC to Site by charter bus. | 10 | Round Trip |  | 0 | 0 |  | 0 | 1144 | 11440 |  | 0 |  | 0 | 11440 | 25% | 2860 | 14300
2.07 |  |  | HEAVY LIFT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.08 |  |  | TRANSPORTATION AND FREIGHT | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.09 |  |  | CAPITAL SPARE PARTS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.1 |  |  | VENDOR ERECTION SUPERVISION | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.11 |  |  | FIRST FILLS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.12 |  |  | ENVIRONMENTAL ASSESSMENT, MONITORING AND TESTING SERVICES |  | 2% |  |  | 0 | 0 |  | 0 | 261289.6667 | 5225.7933 |  | 0 |  | 0 | 5225.7933 | 25% | 1306.4483 | 6532.2417
2.13 |  |  | GEOTECHNICAL INVESTIGATIONS AND RECOMMENDATIONS |  | 2% |  |  | 0 | 0 |  | 0 | 261289.6667 | 5225.7933 |  | 0 |  | 0 | 5225.7933 | 25% | 1306.4483 | 6532.2417
2.14 |  |  | CONSTRUCTION INSURANCE | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
2.15 |  |  | BUILDING PERMITS | n/a |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| INDIRECT COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 47580.2767 |  | 0 | 0% | 0 | 47580.2767 | 25% | 11895.0692 | 59475.3458
OTHER COSTS
3.01 |  |  | EPCM |  | 10% |  |  | 0 | 0 |  | 0 | 320765.0125 | 32076.5013 |  | 0 |  | 0 | 32076.5013 | 25% | 8019.1253 | 40095.6266
3.02 |  |  | OWNERS COSTS |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
3.03 |  |  | ESCALATION |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| OTHER COST SUB TOTAL | [6 empty] | 0 | 0 |  | 0 |  | 32076.5013 |  | 0 | 0% | 0 | 32076.5013 | 25% | 8019.1253 | 40095.6266
| TOTAL | [16 empty] | 288688.5112 | 25% | 72172.1278 | 360860.6391