## 2016 Data Gaps Analysis
2013 Summary Table | [7 empty] | FY 2016 Status Update
Activity ID | Task | Reclamation Unit | Description | Technical Uncertainties | Technical Assessments Required | Data Gaps Identified in 2013 | Data Gap addressed (Y/N) | Work Completed/Rationale for not completing work (ie. 60% design scaled back to 30% design) | Reference Report | Remaining Gaps
SW-001 | Mapping | Sitewide | Visual Aesthetics mapping for reclamation landscape planning. Provide detailed topography required for design at select locations. | Location of permafrost areas for planning of engineering structures. Existing onsite surface material quality and texture. Existing onsite vegetation status. | Prepare current surface cover mapping; include layers for particle size distributions, existing vegetation type, and density. Multi-spectral satellite imagery to assist with delineation of wet areas and zones of frozen sediment. Need to check whether 2012 aerial photography (which included infrared) is adequate). | Existing utility data; existing above ground and buried pipelines. | Y | Surveyed and inventoried sitewide water conveyance infrastructure (CH2M February 2016b) | CH2M Canada Limited (CH2M). March 2016c. Water Conveyance System Mapping and Inventory, Faro Mine Remediation Project. Technical memorandum. (Final). Prepared for Government of Yukon. March 21. | None for pipelines; still remaining for powerlines, buildings, misc structures; existing waste disposal areas
[8 empty] | Mapping webviewer developed and operational | See CDRM/ Section 2.8 | Routine updates and maintenance as additional data is produced
[6 empty] | Bathymetry surveys; IP Pond, Polishing Pond, Vangorda Pit, Grum Pit. | Y | Bathymetric survey of Cross Valley Dam Pond complete' Bathymetry surveys planned of Intermediate Dam Pond complete June 2016; Vangorda Pit and Grum Pit removed from scope of work. | Aurora Geosciences Ltd. April 2016. Draft Technical Report Hydrographic and Sub-Bottom Profiling Survey – Cross Valley Dam Pond. Prepared for CH2M HILL Canada Limited. April 25.
[6 empty] | Select locations may require surveys in key areas where tree cover may reduce accuracy of LIDAR mapping. | Y | Surveyed all new sample locations | See individual data and field reports
[6 empty] | Geotechnical and chemical sampling location to date. | Y | Surveyed all new sample locations | See individual data and field reports
[6 empty] | Review vegetation regrowth on Faro, Grum, and Vangorda dump sites. | Y | Conducted sitewide Vegetation and Soil survey | CH2M HILL Canada Limited (CH2M). March 2015kk. Vegetation and Soil – 2014 Field Summary Report, Faro Mine Remediation Project Proposal. (Final). Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. CH2M HILL Canada Limited (CH2M). February 2015c. Site-wide Soil Characterization Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 9.
[6 empty] | Nested, comprehensive, fertility/texture data mapped onto surface topography. | N | Work stopped on preparation of Project Proposal |  | Comphrehensive GIS mapping with all data (vegetation/ soils/ chemistry/ etc.) not prepared
SW-002 | Data Management and Chemistry | Sitewide | Incorporate additional historical electronic analytical, geochemical, and geotechnical data into warehouse if acquired. New data added to the database as acquired. | Formatting of available electronic data requires additional processing to incorporate into data warehouse, and data that require processing before being loaded into the database will need QA/QC validation. | Integrate chemical and geotechnical data with GIS for SharePoint lookup. | Uncertain until data compiled and reviewed. | N | Database structures completed; valid location names identified and corrected; valid values for all fields tested and corrected. Systems established for uploading and validating EMLINE data and new electronic data from laboratories. All existing EMLINE data, all CH2M analytical data, soil index testing results obtained since 2012 entered into database | CH2M HILL Canada Limited (CH2M HILL). March 2013g. Data Quality Objective Review Process for Environmental Monitoring at the Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March 29. CH2M HILL Canada Limited (CH2M HILL). August 2013a. Faro Mine Complex Site-wide Sampling Definition 2013-2014, Faro Mine Remediation Project. Technical memorandum. Final. Prepared for Government of Yukon. August 19. Quality Assurance and Quality Control Review and Data Set Build Process, Faro Mine Remediation Project, March 2016 Update | Database needs final QA/QC to remove some data duplication; will need to be updated to include future data as data is collected by other contractors, requires routine updating from EMLINE, and requries instruction manual for use and maintenance
SW-003 | Site Access Roads | Sitewide | Design access roads to provide reliable access to critical site locations during large storms events. | Design criteria for Access Roads; current capacity. Existing culvert capacities and physical condition. | Design flow for culvert and drainages, loading capacity and use, requirements for all-weather access. | Condition survey of existing roads for use in short-term and long-term access. | N | Work stopped on preparation of Project Proposal | N/A | Condition survey of existing roads; determination of what access roads will be retained as part of closure planning
SW-004 | Regional Groundwater Flow Modelling | Sitewide | Prepare a site-wide groundwater flow model of the Faro Mine Area and the Vangorda/Grum Area. This will be two separate models, one for each area. These models will provide estimates of groundwater flow directions, rates, and exchange between the surface water and groundwater systems within the model domain. The groundwater flow models will be used to estimate contaminant loading from groundwater to surface streams, support the design of groundwater interception systems, and evaluate the sensitivity of the performance of various waste rock cover systems on groundwater flow rates and SIS effectiveness. | The magnitude of the water budget components of the Faro Mine and Grum/Vangorda systems. The GoldSim model will provide initial estimates of these quantities. The bedrock topography across the site, the spatial distribution of the hydraulic properties of the weathered rock aquifer and alluvial aquifer systems. The spatial and temporal distribution of hydraulic interaction between the surface water and groundwater systems. | Interpretation and integration of existing site water budget data with information collected during the 2012 field effort to develop a quantitative conceptual model of the site and convert that conceptual model into a numerical groundwater flow model. | The bedrock topography across the site, the spatial distribution of the hydraulic properties of the weathered rock aquifer and alluvial aquifer systems. The spatial and temporal distribution of hydraulic interaction between the GW/SW systems. | N | Site-wide modelling completed; higher resolution grids developed for CVD SIS and for NFRC. No modelling completed for Vangorda/Grum Area - removed from scope of work. | CH2M HILL Canada Limited (CH2M HILL). March 2014e. Cross Valley Dam Seepage Interception System Phase 2, Groundwater Modelling, Faro Mine Remediation Project. Technical memorandum. Draft. Prepared for Government of Yukon. March 28. (Appendix A to Task Authorization 016 Down Valley Interim Hydraulic Upgrades Phase 2 – Basis of Design Report [60% design]) CH2M Canada Limited (CH2M). April 2016c. Fiscal Year 2015 Groundwater Flow Model Development Report, Faro Mine Remediation Project. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. April 5. CH2M Canada Limited (CH2M). March 2016. North Fork of Rose Creek Groundwater Report (Appendix C in Preliminary Final Design Basis Report, North Fork of Rose Creek Realignment Project). Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March 31. | None for Faro Area; No work completed on Vangorda/Grum area
[6 empty] | Collects results of fieldwork for individual areas of interest such as geophysics, drilling, well installation, and aquifer testing to use for the development of a regional GW flow model. | Y | See area-specific investigations | See individual data and field reports, listed in CDRM Appemn
SW-005 | Surface Water Modelling | Sitewide | Developed site-wide hydrological model HEC-HMS in 2012, 2013 including all major conveyance elements and structures. Modeled subcatchments to be used as tool for site-specific remediation activities including diversion designs. Water balancing and support for other disciplines. A number of site specific hydraulic models were also developed to assess the Rose Creek diversion options. Additional site specific hydraulic models will be developed as required. | Some model parameterization components such as infiltration rates under various cover scenarios at some remedial areas on the site such as rock waste dumps are still unknown but will be supplied from efforts in other technical areas such as GW and re-vegetation. Cover types in certain areas will be supplied from assessments in re-vegetation areas. The extent of the model discretization in certain areas such as the waste rock dumps is to be determined as it related to needs of particular diversion designs. The interaction of GW and surface water will be further examined and incorporated into modelling considerations. Uncertainties exist regarding the closure of several conveyance components, RCDC, Vangorda Creek, North Fork Rose Creek and additional opportunities for Grum Interceptor Ditch. These are to be assessed through alternatives review. | Refinement of existing HEC-HMS hydrological model specific to each diversion design need and modelling of design storms specific to each diversion/catchment area. Integration of GW/SW interactions into hydrologic modelling. Some site specific hydraulic modelling is required to provide water surface profiles for some diversion structures. Additional flow monitoring at selected locations and acquisition of physical site data that vary by specific location onsite and diversion objectives is being collected as part of 2013 field efforts. Physical site data including infiltration rates at specific features such as waste rock dumps and under various cover scenarios.Bed and bank materials characterizations to be carried out based on diversion design requirements. Integration of re-vegetation and covers designs into catchment area model descriptions. | Infiltration rates at specific areas including waste rock dumps under various cover scenarios. This will be provided through efforts in GW and re-vegetation discipline through modelling, literature reviews, and review of existing site data. | N | Calibrated Meteorological stations. Work stopped on preparation of Project Proposal | CH2M HILL Canada Limited (CH2M HILL). March 2014m. 2013 Down Valley Interim Hydraulic Upgrades Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28. | Additional flow monitoring stations installed in 2015; requries monitoring; calibration; data compilation. For all stations - record stage data and measured flow during elevated flow conditions; for all stations; dedicated monitoring by knowledgable staff required Use soil data from soils report and getech investigations to estimate infiltration rates, cover type compatability and benefits of applying different covers to reduce infiltration and provide geotechnical stability for regrading.
[6 empty] | Site specific physical data such as bed and bank materials within diversions. | Y | Bathymetric survey of Rock Drain Pond ; Geomorphic assessment and Bed and bank material characterization completed in FCD, NFRC, Vangorda Creek Diversion, Upper Guardhouse Creek and North Wall Interceptor Ditch | CH2M HILL Canada Limited (CH2M HILL). March 2014m. 2013 Down Valley Interim Hydraulic Upgrades Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28. CH2M HILL Canada Limited (CH2M HILL). March 2014d. 2013 Vangorda Creek Diversion Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28. CH2M HILL Canada Limited (CH2M HILL). March 2014m. 2013 Down Valley Interim Hydraulic Upgrades Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28. CH2M HILL Canada Limited (CH2M). March 2015k. Summary of 2014 Field Investigation – Lower Guardhouse Creek Interception FSP Name: 102.4 – Lower Guardhouse Creek Interception. Technical memorandum. Prepared for Government of Yukon. March 19. CH2M HILL Canada Limited (CH2M). March 2015n. Summary of 2014 Field Investigation – Design of a Surface Water Collection Structure for the Emergency Tailings Area FSP Name: 105.2 – Install Emergency Tailings Area Surface Water Collection System. Technical memorandum. Prepared for Government of Yukon. March 9. CH2M HILL Canada Limited (CH2M). March 2015i. Summary of 2014 Field Investigation – Faro Creek Diversion East Valley and Faro Creek Diversion West Valley Interceptor Ditch FSP Name: 102.1 – Faro Creek Diversion (East Valley); 102.2 – Faro Creek Diversion (West Valley Interceptor Ditch). Technical memorandum. Prepared for Government of Yukon. March 18. CH2M Canada Limited (CH2M). March 2016i. North Fork of Rose Creek Hydrology/Hydraulics Report (Appendix B in Preliminary Final Design Basis Report, North Fork of Rose Creek Realignment Project). Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March 31. CH2M Canada Limited (CH2M). April 2016h. Summary of 2015 Field Investigation – West Side and East Side Diversions, Faro Mine Remediation Project. Technical memorandum. Draft. Prepared for Government of Yukon. April.
[6 empty] | Cover types in specific catchment areas. | N | Work stopped on preparation of Project Proposal | CH2M HILL Canada Limited (CH2M HILL). November 2014l. Faro Mine Vegetation and Soils Baseline Report, Faro Mine Interim Works. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. November. (Appendix 6F to the Final Draft Faro Mine Interim Works Project Proposal) CH2M HILL Canada Limited (CH2M). February 2015c. Site-wide Soil Characterization Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 9. | Use soil data from CH2M, November 2014l and individual geotechnical investigations to estimate infiltration rates, cover type compatability and benefits of applying different covers to reduce infiltration and provide geotechnical stability for regrading.
[6 empty] | Sub-catchment delineation in site specific model areas such as waste rock dumps. | Y | Subcatchment areas for WRD and NFRC delineated | CH2M Canada Limited (CH2M). March 2016b. Preliminary Final North Fork Rose Creek Design Basis Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March.
[6 empty] | Conduct field surveys for use in SW modelling; cross sections, floodplains, structures etc. Confirm locations and scope through field reconnaissance. This will be completed for individual activity locations | Y | Completed channel cross section surveys in FCD, NFRC, Upper Guardhouse Creek, Vangorda Creek Diversion, RCD, North Wall Interceptor Ditch, South Fork Rose Creek Installed water level transducers at additional SW stages in FCD, NFRC, SFRC, and RCD Work not completed for VGA/ work stopped | (Report Link), ( CH2M HILL Canada Limited (CH2M). March 2015k. Summary of 2014 Field Investigation – Lower Guardhouse Creek Interception FSP Name: 102.4 – Lower Guardhouse Creek Interception. Technical memorandum. Prepared for Government of Yukon. March 19. (Report Link),( CH2M HILL Canada Limited (CH2M). March 2015n. Summary of 2014 Field Investigation – Design of a Surface Water Collection Structure for the Emergency Tailings Area FSP Name: 105.2 – Install Emergency Tailings Area Surface Water Collection System. Technical memorandum. Prepared for Government of Yukon. March 9. CH2M March 2015i) CH2M HILL Canada Limited (CH2M). December 2015i. Faro Mine Complex Design Flood Manual. Draft Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. December 11.
SW-006 | Site-Wide Groundwater/Surface Water Management Plan | Sitewide | Develop an overall site-wide strategy that considers the GW/SW objectives and key performance indicators (KPI) required to integrate the various onsite GW/SW activities. GW/SW man­agement activities assessed within an adaptive management plan (AMP). | Interactions of the GW and SW components. AMP integration of hydrology/hydraulic, groundwater, aquatics, wetland and terrestrial systems, and socio-economic objectives for water management planning. | Integration of all GW/SW diversion/water quality objectives and KPIs. Integration of aquatics, wetland, terrestrial systems, and socio-economic KPIs. | Objectives and KPIs on a site-wide basis for related disciplines. | N | Site-wide surface water plans were developed and presented to IPRP/ INAC/YG in series of meetings held in 2014 and 2015. Work stopped on VGA | CH2M HILL Canada Limited (CH2M HILL). December 2014a. Faro Mine Complex – 2015 Water Management Plan. Final – For Approval. Prepared for Government of Yukon. December 14. Independent Peer Review Panel (IPRP). February 2015. Technical Memorandum re: Review Comments – Faro Mine Remediation Project Joint Design Team/IPRP Workshop – Faro Mine Remediation Plan. February 10-12, 2015. Independent Peer Review Panel (IPRP). September 2015. Technical Memoradum re: Faro Mine Site Visit June 8th to 10th - Report on Site Visit and Presentations by CH2M HILL. September 8. | Partial agreement from IPRP in response to Water Management Plan. Additional agreement for specific areas required.
SW-007 | Cover Design Surface Analysis | Sitewide | Coarse woody debris as erosion control and revegetation cover support has been proposed; however, source, storage, and implementation have not been assessed. CHRM model results used to design and evaluate alternative covers need to be evaluated fully and tested against current performance on Grum Sulphide Cell. Other unsaturated flow models (SHAW and VADOSE/W) need to be evaluated to model flow and snow/snowmelt effects. Cover infiltration descriptions suggest uncertainty regarding how the tailings cover will work with respect to vegetation cover. | Meso- and micro-topography information is missing from the cover type information and is a critical factor for this ecosystem. Resulting suitability for vegetation types and cover volumes needs to be assessed to provide appropriate topographic and planting opportunities. Vegetation cover types depend on cover depth and microsite variation. Providing topography may require greater cover depths or gentler slopes to allow working of the cover material, which affects the material balance and landform planning. Surface treatments cited in the C&R Plan are not used on maps – DSS, RAS, WDS, and SCS. Must re-evaluate the assumptions for very-low- and low-infiltration covers and locations shown in C&R Plan; compacted till may be adversely affected by freeze-thaw cycles. Consider ET cover design instead of, or in addition to, low infiltration covers for areas where cover material selection is proposed. | Review surface treatment types and reconcile to current reclamation plan. Coarse, woody debris usage needs to be assessed for feasibility. Review CHRM model results with Grum Sulphide Cell performance. Need to review low- and very-low-infiltration cover locations onsite. Application of alternative unsaturated flow model (SHAW or VADOSE/W). ET cover design evaluation as addition to or replacement for low-infiltration covers. Function of cover materials is different for waste rock and tailings. Clarify cover expectations and revegetation planning over tailings for EA Reconciliation of surface treatments from C&R Plan to current mapping of the site. Reconciliation of meso- and micro-topography requirements (for different cover types and revegetation requirements) with available cover material volumes. Review basis of design for Reclamation Landform Unit (RLU) surfaces and amendments, including topography, cover material type, and surface amendments. Analysis will be conducted related to waste rock dumps regrading and resloping related to the impacts of snow accumulation (particularly due to wind loading and wind redistribution) on: Landform design as it pertains to resloping and regrading waste rock dumps, snow loading on the leeward side of landforms, and upslope migration and deposition of snow in depressions on windward faces. The geometry of proposed surface water management channels, conveyance of spring meltwater, snow blockage, and construction approaches that reduce mechanical clearing and provide capacity to keep meltwater contained in the channel. | Assessment of coarse woody debris sources, storage, and application onsite to support this as a basis for reclamation surface design. | N | Work stopped on preparation of Project Proposal Site visit and covers workshop completed in 2015 |  | Most elements of cover design need to be addressed; Cost benefits of limiting infiltration, Cost benfits of reducing inflow to Faro Pit or NFRC required for treatment Continue pore gas and temperature profiling to monitor waste pile maturation. Final selection of cover types; idetification of soil amendment source
[6 empty] | Check on area application of RLU types in current plan; review for new closure surface including ET covers. | N
[6 empty] | Confirmation of very-low-infiltration cover performance and predictions of CHRM model. | N
[6 empty] | Application of alternative unsaturated flow model. | N
[6 empty] | Review ET cover design implications for very-low- and low-infiltration covers. | N
[6 empty] | Bulk density data for proposed cover materials, which are required to relate to soil erosion and vegetation establishment data. Initial soil bulk density is a critical factor in the success of any proposed ET soil cover. | N
[6 empty] | Measure soil-water characteristic curves (SWCC) for representative growth media (till and fines). | N
SW-008 | Integrated Site Closure Plan | Sitewide | Completion of a closure drainage (surface and groundwater sources_ and allied landform plan, then overlaid by cover materials (soils) and revegetation plan. Required to be basis of closure impact and residual risk analysis for site environmental assessment, and to provide footprint information for drainage, access and landform features of the closure landscape to inform construction activities. | Closure plan for the site does not currently exist. A reclamation landform units plan exists in minimal detail, but it does not integrate drainage (or wet landscape) details or specify soil and vegetation prescriptions. | Completion of integrated closure planning will require input from the following technical disciplines: | Planning activities will require integrated plan review meetings for all disciplines, focused workshops on key disturbed/undisturbed interface locations (NFRC, Emergency Tailings Area) and development of ArcView mapping layers for an integrated drainage plan, overlaid by soil prescription and vegetation (wetland and upland) layers. | N | Work has been completed under individual disciplines (groundwater, hydrogeology) and covered in site-specific activities; not compiled into integrated plan Arcview mapping layers not developed Work stopped on preparation of Project Proposal | CH2M HILL Canada Limited (CH2M HILL). December 2014a. Faro Mine Complex – 2015 Water Management Plan. Final – For Approval. Prepared for Government of Yukon. December 14. Independent Peer Review Panel (IPRP). February 2015. Technical Memorandum re: Review Comments – Faro Mine Remediation Project Joint Design Team/IPRP Workshop – Faro Mine Remediation Plan. February 10-12, 2015. Independent Peer Review Panel (IPRP). September 2015. Technical Memoradum re: Faro Mine Site Visit June 8th to 10th - Report on Site Visit and Presentations by CH2M HILL. September 8. | Compilation of existing work required and agreement on Water Management Plan Arcview mapping to be developed
· Hydrology
· Water quality
· Hydrogeology
· Risk assessment
· Waste rock and covers
· Revegetation/reclamation
· Construction sequencing
· Wildlife and fisheries
SW-009 | Revegetation Materials Planning and Sourcing | Sitewide | Sourcing revegetation materials will require a 4- to 5-year lead time to grow plant material and prepare the large volumes of planting material for use exactly when required for erosion control.Seeding materials need to be sourced and checked for reliable quality with respect to weedy seed inclusion and large volumes required for native species and proposed agronomic species. | Helicopter seeding has been proposed for steep revegetation areas; this needs to be assessed for feasibility, cost, seed volume, and timed with regrading and cover material sequencing. Some materials are planned to be whips or cuttings; source areas need to be identified for capacity to provide material and whether the areas have been assessed in the environmental assessment. Additional source areas may be required and must be identified. Methods of collection and planting need to be assessed for large areas planned in annual reclamation increments. Use of legume species for soil nitrogenation and revegetation support. Assessment of capacity for projected vegetation volumes needs to be performed so that material is grown with a 4- to 5-year lead time prior to revegetation requirements. Not clear if facilities outside the province would be required to provide bulk vegetation volumes for annual reclamation. | Review of potential vegetation sources, with preference for (1) First Nations greenhousing or propagation facilities and (2) Yukon-based facilities. Environmental assessment needs to review if vegetation cutting/whip collection areas have been included in assessment. These need to be optimized to map potential donor areas with areas likely to be disturbed during construction and access work. | Identification of potential greenhousing and nursery facilities. Identification of suitable seed sources and cutting/whip sources to be included in the local study area, if required. Identification of seed application methods to be considered in reclaimed surface preparation including helicopter, hydroseeding, or surface application. | N | Work stopped on preparation of Project Proposal |  | All work remaining
SW-010 | Sitewide Soils Mapping | Sitewide | Soils data are currently dispersed in different formats and documents. Need site-wide database of soil quality to provide basis for material movement and balance, and planned reclamation covers. |  | Need to categorize data to help identify problematic high or low levels of Ph, Pb, As, Zn, and coarse fragments. Consolidation of current soils information needs to be augmented with baseline data collected for new borrow areas. | Production of site-wide soil database to house existing data and new baseline data to be collected for new borrow areas. | Y | Completed site-wide soil characterization survey (CH2M February 2015c) | CH2M HILL Canada Limited (CH2M). February 2015c. Site-wide Soil Characterization Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 9.
[6 empty] | Identification of problematic Ph, metals, and coarse fragment levels to assist in allocation of cover materials to reclaimed surface planning. | Y | Compiled results of all borrow investigations ; scope for investigating Tailings Borrow Area West not approved | CH2M HILL Canada Limited (CH2M). March 2015hh. Borrow Baseline Design Criteria Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. | Potential till sources in Faro Mine Area could be further defined; very limited near surface sampling took place at Tailings Borrow Area West
SW-011 | Update 2004 Site-Specific Seismic Hazard Assessment | Sitewide | The seismic hazard assessment was updated in 2013 by Dr. Gail Atkinson (Final Report titled Seismic Hazard Assessment for Faro, YK, April 2, 2013). | None. | None. | None. | Y | Seismic stability Assessment Completed | CH2M HILL Canada Limited (CH2M HILL). February 2013d. Update on the Tectonic Setting of the Faro Mine Complex, Faro Mine Remediation Project. Technical memorandum. Prepared for Government of Yukon. February 12. Atkinson, Gail M., Ph.D., P.Geo. and Assatourians, Karen, Ph.D. April 2013. Seismic Hazard Assessment for Faro, YK. Final Report: April 2. Prepared for CH2MHILL Canada Ltd. April.
SW-012 | Identify Additional Areas with a High Probability of Becoming Contaminated Groundwater Discharge Pathways in the Future | Sitewide | Identify additional areas with a high probability of becoming groundwater discharge pathways in the future as ARD reactions continue to accelerate. Support the development of a long-term monitoring network that will identify areas of degrading groundwater quality and potential ARD pathways to be addressed through the AMP. | Implications of new excavations along toe of existing waste rock dumps associated with trenching and borrow source development. May need to design sump areas to collect seepage along the waste rock perimeter and incorporate in GW/SW interaction model. | Perform GIS analysis comparing current topography with pre-mining topography to identify buried drainages that may concentrate groundwater discharge. | Further investigate areas with a high potential to be future contaminant seepage pathways. | N | Developed Site-wide (Faro Mine Area and RCTA) groundwater model showing flow paths from all Waste Rock Dumps Work stopped in Vangorda Grum Mine Area | CH2M Canada Limited (CH2M). April 2016c. Fiscal Year 2015 Groundwater Flow Model Development Report, Faro Mine Remediation Project. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. April 5. CH2M Canada Limited (CH2M). April 2016e. Groundwater Analysis, Faro Mine Remediation Project. Draft. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. CH2M Canada Limited (CH2M). March 2016b. Preliminary Final North Fork Rose Creek Design Basis Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March. CDRM Appendix | CH2M recently (2016) compiled additional pre-mining topogrraphic maps into 1 mapping file; this needs to be compared with 2012 mapping
SW-013 | Delineation of Permafrost at Faro Mine and Grum/Vangorda Area | Sitewide | The presence of massive or discontinuous permafrost within the groundwater system has a significant influence on groundwater flow directions, rates, and SW/GW interaction. | The design of an effective SIS requires knowledge of permafrost in the immediate area of the system. Permafrost may also alter contaminant migration pathways and require modification to groundwater monitoring network designs. | Perform detailed literature review to located previous studies or field investigations that delineated permafrost extent at the FMC. Proposed geophysical surveys in the vicinity of SIS installations can be expanded to identify the presence of permafrost in those areas. This is the same permafrost survey identified under the regulatory data gaps. | The potential for permafrost to influence the effective operation of the groundwater interception systems. | Y | See area- specific investigations. Probability mapping presented the NFRC DBR report Work stopped on preparation of Project Proposal | CH2M Canada Limited (CH2M). March 2016. Preliminary Final Design Basis Report, North Fork of Rose Creek Realignment Project). Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March 31. | Work completed for NFRC area; not other areas. Compilation of frozen conditions encountered by soil borings and test pits needs to be compiled on site-wide basis
[6 empty] | Evaluate the potential of using multispectral satellite imagery and post-processing to identify areas with a high probability of having near-surface permafrost. | N |  |  | Work not completed on Vangorda/Grum Area
SW-014 | Site-wide Water Balance Model and Piezometer Installation | Sitewide | Develop an integrated GW/SW model that will provide an estimate of the site-wide water balance, contaminant loading, and surface water quality. Install piezometers into the Grum, Vangorda, and Faro waste rock dumps to monitor seasonal groundwater level fluctuations using recording pressure transducers. | Existing model assumptions pertaining to flow/drainage conditions applications and geochemical model for waste rock dumps and tailings. Quality of existing and new data needs to be evaluated and confirmed for appropriate use. Magnitude of fluctuation in groundwater levels driving the geochemical reactions within the waste rock. | Review current model capabilities pertaining to water balance and model functionality. Build mass balance equations in the model to track water throughout the system under different hydrologic conditions and stages of remediation. User interface will be developed that facilitates sensitivity studies, summarizes all the user inputs, and promotes tool functionality. Check of the improved model equations and conduct model runs at different scenarios. Conduct sensitivity analysis on key parameters that influences the water balance and contaminant loading throughout the system. Develop post-processing tools to report results and summarize results of predictive modelling. Incorporate the observed groundwater level fluctuations into the geochemical analysis performed to estimate future seep and groundwater quality. | Update infiltration and cover infiltration data with more accurate data if available. SRK (2006) provided an update to the infiltration rates, more recent data might be available. Information about the tailings location and how they are connected in the water balance. | N | Work stopped on preparation of Project Proposal |  | Update infiltration and cover infiltration data
[6 empty] | Need access to the site hydrologic and analytical data and compile site-wide hydrologic and flow data. Calibrate model with existing field conditions from field data. | N | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD. | CH2M Canada Limited (CH2M). April 2016l. Preliminary Final North Fork Rose Creek Realignment Project Design Basis Report. Prepared for Government of Yukon. | Model inputs will need to be updated as additional surface water quantites and quality become available and change through time
[6 empty] | Magnitude of seasonal groundwater level fluctuation within Faro, Grum and Vangorda waste rock dumps. | Y | Continuous water level monitoring completed in Faro, Grum and Vangorda WRDs | CH2M HILL Canada Limited (CH2M HILL). October 2013b. Waste Rock Dump Monitoring Report. Technical memorandum. Final. Prepared for Government of Yukon. October 29. CH2M HILL Canada Limited (CH2M HILL). March 2014c. 2013 Seep Sampling and Waste Rock Dump Monitoring Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 31. CH2M HILL Canada Limited (CH2M). March 2015b. Summary of 2014 Field Investigation – Site-wide Geochemical Monitoring FSP Name: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Prepared for Government of Yukon. March 31. CH2M Canada Limited (CH2M). April 2016d. Summary of 2015 Field Investigation – Site-wide Geochemical Monitoring, FSP Name: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Draft. Prepared for Government of Yukon. April 15. | Data not compiled or evaluated for VGA
SW-015 | Develop Geochemical Loading Models | Sitewide | Develop individual geochemical models for the waste rock dumps, the Rose Creek Tailings Facility, and the three pit lakes. Integrate into the overall site-wide water balance model to generate a comprehensive predictive water quality model for the site. | Currently do not have possession of geochemical models developed for the waste rock piles and Rose Creek Tailings Facility. Existing modelling did not include three pit lakes. Assume requirement to rebuild geochemical models for waste rock piles, tailings facility, and pit lakes. | Review of the working functions of all current models and submodels. Current model feeds on a series of geochemical submodels for each facility type (that is, WD, pit, TSF), which in turn are based on a series of field and lab tests and assumptions. Field and laboratory tests included oxygen and temperature profiles and static and kinetic laboratory testing. Review additional documents pertinent to the model development may also be necessary (for example, geochemical reports).Spreadsheet database working functions need to be developed and the model needs to be calibrated and compared to the existing geochemical component of the GoldSim model. Exportable outputs need to be developed to export into the GoldSim model. | Anticipate water quality of surface runoff and seepage from waste rock dumps during construction and leaching potential and sediment loading potential of freshly exposed (regraded) waste rock from each of the waste rock dumps. | N | Drilled and install 10 GW, pore gas and thermistor port installations in sitewide WRDs; Completed 3x annual (Spring, Summer and Winter) monitoring of CH2M and Existing SRK WRD installations. Completed site-wide seep sampling and pit lake profiling Drilled and install GW monitoring cluster in north portion of Intermediate Tailings Drilled and installed 2 GW monitoring clusters in the Original Tailings Impoundment at mouth of the ETA canyon Work stropped on preparation of Project Proposal | CH2M HILL Canada Limited (CH2M HILL). October 2013b. Waste Rock Dump Monitoring Report. Technical memorandum. Final. Prepared for Government of Yukon. October 29. CH2M HILL Canada Limited (CH2M HILL). March 2014c. 2013 Seep Sampling and Waste Rock Dump Monitoring Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 31. CH2M HILL Canada Limited (CH2M). March 2015b. Summary of 2014 Field Investigation – Site-wide Geochemical Monitoring FSP Name: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Prepared for Government of Yukon. March 31. CH2M Canada Limited (CH2M). April 2016d. Summary of 2015 Field Investigation – Site-wide Geochemical Monitoring, FSP Name: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Draft. Prepared for Government of Yukon. April 15. CH2M HILL Canada Limited (CH2M). March 2015l. Summary of 2014 Field Investigation – Relocate Oxide Fines to Low-grade Stockpile “C” FSP Name: 104.1 – Relocate Oxide Fines to LGSPC. Technical memorandum. Prepared for Government of Yukon. March 13. CH2M HILL Canada Limited (CH2M). March 2015o. Summary of 2014 Field Investigation – Delineate Main and Intermediate Sulphide Cells for Regrading and Capping Design FSP Name: 106.1 – Regrade and Reslope Main and Intermediate Sulphide Cells. Technical memorandum. Prepared for Government of Yukon. March 13. CH2M HILL Canada Limited (CH2M). March 2015p. Summary of 2014 Field Investigation – Regrade and Reslope Faro Waste Rock Dumps (Upper Surface) FSP Name: 106.2 – Regrade and Reslope Faro Waste Rock Dumps (Upper Surfaces). Technical memorandum. Prepared for Government of Yukon. March 13. CH2M HILL Canada Limited (CH2M HILL). February 2014q. 2013 Cross Valley Dam Seepage Interception System Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 7. CH2M HILL Canada Limited (CH2M). August 2016j. Summary of 2016 Field Investigation Site-wide Geochemical Monitoring, Field Sampling Plan: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Draft. Prepared for Government of Yukon. August 18. | Completion of site-wide geochemical model required for effects assesment (for completion of Project Proposal)
[6 empty] | Update geochemical sub models based on historical and field data to use as inputs to the GoldSim model. | N
[6 empty] | Update model with latest data available for each source included in the model (that is, 33+WRDs, 3 pits, and 2 TSF). | N
Faro Mine Area (Activity Code 100)
101 – Faro Pit Safety Berm
101.1 | Faro Pit Wall Stability Management | Faro Mine WRDs and Faro Pit | Evaluate pit wall stability and consequences of failure | Long term stability of pit walls and long term management requirements. Consequences of pit wall failures - a rapid slide in pit may cause wave that could endanger pumping infrastructure and operating personnel) | Field inspection and evaluation to determine requirements/needs for (1) analytical stability evaluation, (2) instrumentation and monitoring, and (3) slope management including possible stabilization measures. | Requirements/needs for stability evaluation, subsurface information gathering and instrumentation and monitoring | Y | Complete pit wall stability evaluation geological reconnaissance Drill, install and monitor 2 slope inclinometers and vibrating wire piezometers and 2 standpipe piezometers at Faro Creek Diversion along Northeast wall of Faro Pit. Downhole acoustic televiewer observations performed in boreholes before completing installs to characterize bedrock jointing | CH2M HILL Canada Limited (CH2M HILL). March 2014q. Faro Mine Complex 2013 Pit Wall Stability Inspection, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 26. BGC Engineering Inc. (BGC). March 2016. Faro Open Pit Stability Assessment, Site-wide Design Basis Report. Draft. Prepared for CH2M HILL Canada Limited (CH2M HILL). March 18. | Monitoring of inclinometers, piezometers and monuments required, data compiled and evaluated
101.2 | Safety Berm around the Pit | Faro Mine WRDs and Faro Pit | Construct berm around Faro Pit to restrict physical access. | H&S implications regarding the timing of berm construction. Need to allow for ongoing spalling of pit walls; 5-m offsets proposed can be expected to vary. | Identify borrow materials. Evaluate spalling of pit walls. |  | Y | Geological Reconnaissance completed at Faro Pit | CH2M HILL Canada Limited (CH2M). March 2015oo. Summary of 2014 Field Investigation – Faro Pit Safety Berm; FSP Name: Activity 101.2 – Field Reconnaissance for the Faro Pit Safety Berm. Technical memorandum. Draft. Prepared for Government of Yukon. March 12.
102 – Surface Water Diversions
102.1 | Faro Creek Diversion (East Valley) | East Side ARD Collection and Diversions | Relocate existing diversion channel to new alignment up hillside; intercept and convey Faro Creek along the eastern slope of Faro Creek Valley above the existing diversion channel.Evaluate design criteria, need for overflow structure where natural creek meets diversion to spill excess floodwater into pit. Address local SW flow to Faro Pit.Consider alternative of building new diversion along the west side that can potentially flow to North Wall Interceptor/Guardhouse Creek.Design to preliminary design level of detail. | Discontinuous permafrost, ground conditions, channel seepage losses, water quality, interaction of GW and SW, hydraulic analysis, and stability of the pit wall. Management of localized flows captured in existing FCDC drainage area. The existing FCDC will remain but will be revegetated. Local drainage will be captured, but the discharge from the existing FCDC needs to be considered in terms of drainage area and seepage and discharge points for high precipitation events that may overflow the revegetated channel. | Reassess diversion options, preliminary design criteria (C&R Plan, Table 4.1) Review of existing information regarding geotechnical, water quality, pit wall stability, channel stability, seepage, hydrology, hydraulics, assess current channel design capacity, diversion opportunities, and icing potentials. Determination of local SW flow characteristics and drainage area to the existing FCDC and pit area have been carried out. This analysis will be refined. Overflow structure foundation and stability evaluations. Potential hydraulic analysis of structure. Permafrost impacts on design considerations. Riparian and floodplain re-vegetation designs. Hydrologic model analysis for design flows in diversion. Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. | New channel bed and bank material characterizations; additional soils data including more information on presence and extent of permafrost and ice content. Golder report (detailed comparison of alternatives) described test pits along alignment but refusal at shallow depths because of permafrost. | Y | Completed cross section surveys Completed rapid geomorphic assessment Geological reconnaissance of existing diversion and SRK 2009 Proposed diversion alignment Drill 6 borings, install piezometers and thermistor ports along potential FCD alignment Completed 21 surface geophysical transects covering potential FCD alignments Investigated seepage through Faro Valley: Drill and install 3 well clusters Complete aquifer testing and FCD stream flow monitoring | CH2M HILL Canada Limited (CH2M). March 2015i. Summary of 2014 Field Investigation – Faro Creek Diversion East Valley and Faro Creek Diversion West Valley Interceptor Ditch FSP Name: 102.1 – Faro Creek Diversion (East Valley); 102.2 – Faro Creek Diversion (West Valley Interceptor Ditch). Technical memorandum. Prepared for Government of Yukon. March 18. CH2M Canada Limited (CH2M). April 2016g. Summary of 2015 Field Investigation - Faro Valley Seepage Investigation, Faro Mine Remediationn Project, Field Sampling Plan Name: 106.1 – Faro Valley Seepage Investigation. Technical memorandum. Draft. Prepared for Government of Yukon. April 1. CH2M Canada Limited (CH2M). April 2016h. Summary of 2015 Field Investigation – West Side and East Side Diversions, Faro Mine Remediation Project. Technical memorandum. Draft. Prepared for Government of Yukon. April. CH2M Canada Limited (CH2M). September 2016a. Summary of 2016 Field Investigation – Faro Creek Diversion Proposed Realignment, Field Sampling Plan Name: Faro Creek Diversion New Alignment Drilling. Technical memorandum. Draft. Prepared for Government of Yukon. September 5. CH2M HILL Canada Limited (CH2M). August 2016h. Summary of 2016 Field Investigation – Faro Creek Diversion Aquifer Testing, Field Sampling Plan Name: Faro Creek Diversion Aquifer Testing. Technical memorandum. Draft. Prepared for Government of Yukon. August 24. | Develop DTMs using cross section data and input into hydraulic analyses Complete SW discharge measurments in FCD
[6 empty] | Geotechnical data gaps at the new diversion channel alignment include Depth to bedrock | Y
[6 empty] | Soil and rock mass strengths | Y
[6 empty] | Additional flow monitoring data collection at recommended 2013 stations for additional model refinement. | Y | Continuous SW level monitoring transducers deployed |  | Monitor SW and evaluate data;
102.2 | West Valley Extension | East Side ARD Collection and Diversions | Direct clean water from west side of valley around Faro Pit. Minimize seepage losses. | Same as Activity 102.1. | Same as Activity 102.1. | Same as Activity 102.1. | Y | Same as 102.1 | Same as 102.1 | Same as 102.1
102.3 | North Wall Interceptor Ditch | West Side Diversions | Remediate existing North Wall Interceptor ditch (NWID) and discharge to Rose Creek below Cross Valley Dam; improve or construct access. The Upper Guardhouse Creek flows into the NWID. Water from the creek is generally clean but contributes hydraulic load.Design to preliminary design level of detail. | Discontinuous permafrost.Amount of GW/SW interaction. Water quality. Little information available for area, need care to separate from Lower Guard House Creek. Design criteria needs to be evaluated in the context of the overall closure. Soil cover and revegetation plan required for remediated ditch area. Discharge design for section below Cross-valley Dam needs to be determined. Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. | Some site specific hydraulic modelling required to provide water surface profiles. Geotechnical, water quality, channel stability, seepage, hydrology, hydraulics modelling refinements, design storm flows, icing, soil cover, and revegetation options. Limited data have been collected from the UGC and the NVID in terms of site-specific information. The valley slopes are extreme and determining channel capacity and design for erosion control is key. Preliminary information indicates depth of overburden in some areas; uncertain information. Determine impacts of flow on Rose Creek downstream from convergence. Permafrost impacts on design considerations. Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. | Detailed cross section data including channel and floodplain for Upper Guardhouse Creek and NVID for modelling obtained from LiDAR. | Y | Completed channel cross section surveys | CH2M HILL Canada Limited (CH2M). March 2015i. Summary of 2014 Field Investigation – Faro Creek Diversion East Valley and Faro Creek Diversion West Valley Interceptor Ditch FSP Name: 102.1 – Faro Creek Diversion (East Valley); 102.2 – Faro Creek Diversion (West Valley Interceptor Ditch). Technical memorandum. Prepared for Government of Yukon. March 18. CH2M Canada Limited (CH2M). April 2016h. Summary of 2015 Field Investigation – West Side and East Side Diversions, Faro Mine Remediation Project. Technical memorandum. Draft. Prepared for Government of Yukon. April.
[6 empty] | Channel bed and bank materials characterizations for modelling. | Y | Completed rapid geomorphic assessment
[6 empty] | Assess area below Cross Valley Dam for discharge design requirements to Rose Creek – flow management and design requirements. | N | Work stopped on preparation of Project Proposal |  | Assess area below Cross Valley Dam for discharge design requirements to Rose Creek – flow management and design requirements.
[6 empty] | Geotechnical data gaps at the new diversion channel alignment includes the following: | Y | Excavated 5 test pits and completed geological reconnaisance. Further characterization not required for Conceptual Design of Diversion
Depth to bedrock
Soil and rock mass strengths
[6 empty] | Presence and extent of permafrost | Y | Not observed during test pit excavations or field reconnaissance. Down Valley Tailings design and construction reports indicated permafrost was present at the downstream end of the diversion.
102.4 | Lower Guardhouse Creek | RCTA | Intercept seepage from mill and stockpiles. Direct water to Faro Pit by pipeline (ETA Activity 105). Install GW and SW monitoring network.Improve or construct access road to the NW Dump near Upper Guardhouse Creek. Remove waste rock between W8 and W10 on Upper Guardhouse Creek. Design to preliminary design level of detail. | Seepage rates, water quality, interception potential, long-term performance of interception. Design criteria provided in the C&R Plan, Table 4.3, require definition and linkage to seepage management and water quality. SW contribution to flows. Hydraulic modelling to contain design flow rates. Establish final design flow rate estimates and integrate evaluation of GW and SW. Evaluate GW interception based on monitoring results. Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. | Refinement of hydrologic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Establish design flow rate estimates and integrate evaluation of GW and SW. Evaluate GW interception based on monitoring results. Seepage rates, water quality, interception potential, and long-term performance of interception. Design criteria provided in the C&R Plan, Table 4.3, require definition and linkage to seepage management and water quality. | Detailed cross section survey data including channel and floodplain areas; channel bed and bank materials characterizations; soils data including permafrost; historical channel ice data, flow monitoring, and water profile data (surface elevations). | Y | Completed geological reconnaissance Completed specific conductivity survey Completed periodic flow and water quality monitoring and at GDHSCK and SRK-FD01 Work stopped on preparation of Project Proposal Need to more fully develop conceptual closure plan to evaluate intended use | CH2M HILL Canada Limited (CH2M HILL). March 2014c. 2013 Seep Sampling and Waste Rock Dump Monitoring Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 31. CH2M HILL Canada Limited (CH2M). March 2015b. Summary of 2014 Field Investigation – Site-wide Geochemical Monitoring FSP Name: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Prepared for Government of Yukon. March 31. CH2M Canada Limited (CH2M). April 2016d. Summary of 2015 Field Investigation – Site-wide Geochemical Monitoring, FSP Name: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Draft. Prepared for Government of Yukon. April 15. | Need to more fully develop closure plan to evaluate intended use.
[6 empty] | Additional flow monitoring data for model calibration and validation. | Y |  |  | Cross section surveys if closure plan requires use during construction or post closure
[6 empty] | Depth to bedrock and aquifer properties in area of planned seepage collection system. | N |  |  | Leakage from NWID into LGC needs to be evaluated (dilution of impacted seepage)
[6 empty] | Geotechnical data gaps includes: | N
[6 empty] | Depth to bedrock | N
[6 empty] | Soil and rock mass strengths | N
[6 empty] | Presence and extent of permafrost | N
[6 empty] | Permeability of soil and rock | N
[6 empty] | Effectiveness of current system and need for enhancement. | N |  |  | Geomorphic Assessment Required
103.1 | Install Pump in Existing Wells, Piping, Heat Tracing | Faro WRDs and Pit | Reduce effects of contaminant yield from Zone II Pit. Maintain water level in Zone II Pit to maintain gradient towards the pit, away from NFRC. (New well-constructed in FY 2012). | Access and maintenance of year-round pumping system with minimal O&M costs. | Automate operations. | Detail field conditions of pipeline | Y | New well constructed by CH2M in 2012 Zone II pumping well operated and monitored by site Care and Maintenance Operator Water conveyance inventory included documentation of Zone II pipeline | CH2M HILL Canada Limited (CH2M HILL). November 2012g. Task Authorization 007 Summary of Zone II Drilling Activities, Faro Mine Remediation Project. Technical memorandum. Draft. Prepared for Karen Furlong/Government of Yukon (YG). November 1. CH2M Canada Limited (CH2M). March 2016c. Water Conveyance System Mapping and Inventory, Faro Mine Remediation Project. Technical memorandum. (Final). Prepared for Government of Yukon. March 21.
[6 empty] | Record operating data (pumping rate, water level, operation duration, etc.) | Y
104 – Oxide Fines and Low-grade Ore
104.1 | Relocate Oxide Fines to Low-grade Ore Stock Piles (LGSP) C | Faro WRDs and Pit | Relocate oxide fines to LGSP C to reduce contamination from these sources to GW and SW. Alternative – Relocate oxide fines to the sulphide cells as a levelling (cushion) layer below the synthetic cover. | Volume of material to be relocated and covered. Foundation conditions of LGSP C (water table, and geotechnical properties) Constructability implications (for example, requirements for specialized equipment or operating procedures). Under the alternative to relocate oxide fines to the sulphide cells, geochemical compatibility of oxide fines with sulphide waste. | Refined volume of oxide fines material to be relocated and covered. Final landform design options, including water management plan – both LCSP C and sulphide cells. Optimize removal and consolidation to reduce footprint and costs; minimize environmental risk (for example, constructability, minimize disturbance). Alternatives Assessment – Relocate oxide fines to LGSP C versus to sulphide cells. | Oxide Fines Stockpile: characterize material types, geochemical and geotechnical properties down to the original topography as well as better definition of the areal extent of the oxide fines | Y | Drilled 1 boring in Oxide Fines Stockpile and install GW monitoring well, thermistor port and pore gas ports Excavated 3 test pits in Oxide Fines Stockpile | CH2M HILL Canada Limited (CH2M). March 2015l. Summary of 2014 Field Investigation – Relocate Oxide Fines to Low-grade Stockpile “C” FSP Name: 104.1 – Relocate Oxide Fines to LGSPC. Technical memorandum. Prepared for Government of Yukon. March 13.
[6 empty] | LGSP C: Characterize Foundation stability, material gradation, GW characteristics and trafficability. | Y | Excavated test pit and collected shallow surface samples in LGSP C
[6 empty] | Estimate material volumes in Oxide Fines Stockpile | N | Preliminary evaluation of results corroborate depths determined from pre-mining topography Work stopped on preparation of Project Proposal |  | Need to complete written evaluation
[6 empty] | Estimate material volumes in Plant Site Area – Better delineation to assess both the horizontal and vertical (depth below surface) extent of these materials. | N | Work stopped on preparation of Project Proposal |  | Estimate material volumes in Plant Site Area – Better delineation to assess both the horizontal and vertical (depth below surface) extent of these materials.
[6 empty] | For alternative to relocate oxide fines to sulphide cells, geochemical compatibility of oxide fines with sulphide waste. | N | Work stopped on preparation of Project Proposal |  | For alternative to relocate oxide fines to sulphide cells, geochemical compatibility of oxide fines with sulphide waste.
104.2 | Relocate Medium-grade Ore (MGO), Including Brown and Green Oxide Fines (Oxide Fines #1) to LGSP C | Faro WRDs and Pit | Relocate MGO to LCSP C to reduce contamination from these sources to GW and SW. Same issue as above. Alternative – Relocate this waste to the sulphide cells as a levelling (cushion) layer below the synthetic cover. | Foundation conditions of LGSP C (water table and geotechnical properties) Health and safety issues of moving MGO and brown/green oxide fines. Constructability implications (for example, requirements for specialized equipment or operating procedures). If alternative, geotechnical compatibility of MGO with sulphide waste. | Final landform design options – both LGSP C and sulphide cells. Optimize removal and consolidation to reduce footprint and costs; minimize environmental risk (for example, constructability, minimize disturbance). Alternatives evaluation that includes removing MGO to LGSP C versus to sulphide cells. | LGSP C – Foundation stability, material gradation, GW characteristics, and trafficability. | Y | LGSP C – See 104.1 above |  | Complete geological reconnaissance to write up material characteristics
[6 empty] | MGO – Material gradation. | N | Work stopped on preparation of Project Proposal |  | Complete geological reconnaissance to write up material characteristics
[6 empty] | For alternative to relocate MGO to sulphide cells, geochemical compatibility of MGO with sulphide waste, final landform design of sulphide cells (footprint, slope angles, height of capped cell). | N | Work stopped on preparation of Project Proposal |  | Geochem testing to evaluate potential placement into Faro Pit
104.3 | Cover and Revegetate LGSP A | Faro WRDs and Pit | Reduce contamination from these sources to GW and SW. Alternative – Relocate this waste to the sulphide cells as a levelling layer for the synthetic cover or consolidate in LGSP C. | Implications for cover design if capped material generates heat. Grum Sulphide Cell is already capped with a very-low-infiltration cover that needs monitoring and possibly instrumentation. Need to maximize capping design and performance information for LGSP sites by closely monitoring results of existing GSC cover work. Proposed reclamation surface is rough and loose; however, the field investigation concluded that the microtopography is bad for plateau areas because it promotes ponding and infiltration. | Infiltration modelling (cover optimization); VADOSE/W, SLIDE (slope stability); TEMP/W; and re-evaluate design criteria in the C&R Plan, Table 4.6. Evaluate SW management – energy/erosion potential. Geochemical compatibility of low-grade ore with sulphide waste needs to be assessed in terms of potential leachability. Health and safety issues of moving low-grade ore. | Review RLU planning basis with the Waste Pile and Tailings Discipline Team, | N | Completed vegetation and soil survey (CH2M March 2015z), (CH2M February 2015c) Work stopped on preparation of Project Proposal | CH2M HILL Canada Limited (CH2M). March 2015kk. Vegetation and Soil – 2014 Field Summary Report, Faro Mine Remediation Project Proposal. (Final). Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. CH2M HILL Canada Limited (CH2M). February 2015c. Site-wide Soil Characterization Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 9. | Complete geological reconnaissance to write up material characteristics, aerial extent, volume
[6 empty] | Cover and revegetation trial for LGSP reclamation to be recommended in the project proposal. | N
[6 empty] | Existing site water balance versus water balance after final grading needs to be evaluated to determine surface and GW impacts. | N
[6 empty] | Water/sediment management plans: Drainage plan, sedimentation ponds/wet landscape options, existing stockpile topography; and final landform design options. | N
[6 empty] | Design life reduction of the membrane due to conditions (temperature/caustic gas production). | N
[6 empty] | Water table location and fluctuation. | N
104.4 | Cover and Revegetate LGSP C | Faro WRDs and Pit | Reduce contamination from these sources to GW and SW. | Implications for cover design if capped material generates heat or caustic gas is produced. | Infiltration modelling (cover optimization); VADOSE/W, SLIDE (slope stability); TEMP/W; and re-evaluate design criteria in the C&R Plan, Table 4.6. Evaluate SW management – energy/erosion potential. | Review RLU planning basis with Waste Pile and Tailings Discipline; consider a revegetation trial on this kind of slope/material. | N | Excavated 1 test pit in LGSP C Completed vegetation and soil survey Work stopped on preparation of Project Proposal | CH2M HILL Canada Limited (CH2M). March 2015l. Summary of 2014 Field Investigation – Relocate Oxide Fines to Low-grade Stockpile “C” FSP Name: 104.1 – Relocate Oxide Fines to LGSPC. Technical memorandum. Prepared for Government of Yukon. March 13. CH2M HILL Canada Limited (CH2M). March 2015kk. Vegetation and Soil – 2014 Field Summary Report, Faro Mine Remediation Project Proposal. (Final). Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. CH2M HILL Canada Limited (CH2M). February 2015c. Site-wide Soil Characterization Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 9. | Complete geological reconnaissance to write up material characteristics, aerial extent, volume
|  |  |  | Grum Sulphide Cell is capped with a very-low-infiltration cover needs monitoring, and possibly instrumentation. Need to maximize capping design and performance information for LGSP sites by closely monitoring results of existing GSC cover work. |  | Existing site water balance versus water balance after final grading needs to be evaluated to determine surface and GW impacts. | N
|  |  |  | Design life reduction of the membrane due to conditions (temperature/caustic gas production). |  | Water/sediment management plans: Drainage plan, sedimentation ponds/wet landscape options, existing stockpile topography; and final landform design options. | N
|  |  |  | Proposed reclamation surface is rough and loose; however, the field investigation concluded that the microtopography is bad for plateau areas because it promotes ponding and infiltration. |  |  | N
105 – Emergency Tailings Area
105.1 | Remove Tailings to Rose Creek Tailings Facility | Mill and ETA | Remove tailings to Rose Creek Tailings Facility to reduce contaminant loading to GW and SW. | Constructability Implications (for example, requirements for specialized equipment or operating procedures). | Excavation plan that includes sequencing and hydrology and sediment management. Hydrology and GW/SW interaction of closure configuration. Alternatives Assessment – Relative merits of removing tailings and underlying impacted soils versus leaving tailings in place and covering. For example, removal of the tailings could drain the wetland upgradient (SE of ETA). Alternatives Assessment – Relative merits of removing contaminated soils downgradient from the Access Road versus leaving in place. | Suitable disposal location for tailings and underlying impacted soils. | Y | Drilled one boring through ETA tailings into native overburden Drilled two borings through mine access road to bedrock Advanced six seismic CPT soundings | CH2M HILL Canada Limited (CH2M). March 2015m. Summary of 2014 Field Investigation – Relocate ETA Tailings to Rose Creek Tailings Area FSP Name: 105.1 – Remove Tailings to Rose Creek Tailings Facility. Technical memorandum. Prepared for Government of Yukon. March 9.
|  |  | Alternative – Leave the tailings in place and cover; channelize flow of major seeps (for example, X23) in granular trenches to a seepage collection point (part of 105.2 below). | Under alternative to leave tailings in place, geotechnical condition of Mine Access Road as a (pervious) solids retaining structure. |  | Quantity of contaminated fill to be removed downgradient from the Access Road. | N
105.2 | Install GW and SW Collection Systems | Mill and ETA | Intercept contaminated GW and SW before discharge into the Rose Creek Tailings Area. A low head concrete dam will be constructed at the entrance of the topographic “funnel” south of the Access Road. Since there is little soil cover at this location, it will be mainly a surface water collection system with the concrete structure founded on bedrock. Construct diversion ditches, sump, and pumping stations for diversion of waters from ETA during construction. Pipe to Faro Pit. | Define bedrock surface. Quantify site water budget. Hydrogeologic assessment: seepage interception (funnel and gate) design options. | Foundation evaluation for concrete dam structure, Concrete dam stability: Seepage and stability | Detailed cross section survey data including potential channel and floodplain areas. | N | Some topography survey completed through survey of geophysical lines Work stopped on preparation of Project Proposal | CH2M HILL Canada Limited (CH2M). March 2015n. Summary of 2014 Field Investigation – Design of a Surface Water Collection Structure for the Emergency Tailings Area FSP Name: 105.2 – Install Emergency Tailings Area Surface Water Collection System. Technical memorandum. Prepared for Government of Yukon. March 9.
[6 empty] | Potential channel bed and bank materials characterizations and floodplain cover characterization. | N | Work stopped on preparation of Project Proposal
[6 empty] | Bedrock contact delineation in Mill Canyon and Old Faro Creek immediately downgradient from the WRD. Aquifer property information in the Mill Canyon area. | N | Work stopped on preparation of Project Proposal
[6 empty] | Rate of GW and SW inflow from Mill Building Site. Rate of GW and SW inflow from Mill Creek Canyon. | Y | Some surface water estimates X23, FCS4, monitoring well levels available for review Installed stilling wells and water level transducers at two SW locations | CH2M HILL Canada Limited (CH2M HILL). October 2013b. Waste Rock Dump Monitoring Report. Technical memorandum. Final. Prepared for Government of Yukon. October 29. CH2M HILL Canada Limited (CH2M HILL). March 2014c. 2013 Seep Sampling and Waste Rock Dump Monitoring Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 31. CH2M HILL Canada Limited (CH2M). March 2015b. Summary of 2014 Field Investigation – Site-wide Geochemical Monitoring FSP Name: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Prepared for Government of Yukon. March 31. CH2M Canada Limited (CH2M). April 2016d. Summary of 2015 Field Investigation – Site-wide Geochemical Monitoring, FSP Name: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Draft. Prepared for Government of Yukon. April 15.
[6 empty] | Alluvial aquifer thickness and bedrock topography south of the Mine Road. | Y | Two borings drilled through Mine Access Road; Completed geological reconnaissance Test Pit completed near ETA collection sump; Geophysical surveys completed | CH2M HILL Canada Limited (CH2M). March 2015n. Summary of 2014 Field Investigation – Design of a Surface Water Collection Structure for the Emergency Tailings Area FSP Name: 105.2 – Install Emergency Tailings Area Surface Water Collection System. Technical memorandum. Prepared for Government of Yukon. March 9.
105.3 | Cover and Revegetate ETA | Mill and ETA | Determine appropriate closure cover for ETA after tailings closure option is chosen (remove or leave in place). | Closure cover depends on the decision regarding the final disposal of tailings. | Closure surface configuration and capping materials need to be designed (if applicable). Cover soil availability and type needs to be determined. | SW flow calculations. | Y | See 105.2 | See 105.2
|  |  | Tie revegetation plan in to existing adjacent vegetation at the toe of the Faro waste rock piles. | Existing vegetation needs to be characterized – will be affected by tailings removal due to impoundment of water in this area. Revegetation footprint could then be larger than the ETA. | Appropriate vegetation cover to fit in with existing adjacent vegetation. Area needs to be assessed and planned. | Detailed cross section survey data including potential channel and floodplain areas; potential channel bed and bank material characterizations and floodplain cover characterization. | N | See 105.2
|  |  | This is a high-visibility area adjacent to the site access point and, therefore, requires proactive planning for the reclamation surface. | Potential impact on North Fork Rose Creek downstream of the rock drain needs to be considered in revegetation and contour planning. | Failure modes and effects analysis of various ETA SIS configurations (for example, failure of active pumping). | Integration of SW and GW modelling approaches and results. | N | Work stopped on preparation of Project Proposal
[6 empty] | Existing vegetation and soils need to be characterized to assess impact of remediation. | Y | Completed vegetation and soil survey | CH2M HILL Canada Limited (CH2M). March 2015kk. Vegetation and Soil – 2014 Field Summary Report, Faro Mine Remediation Project Proposal. (Final). Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. CH2M HILL Canada Limited (CH2M). February 2015c. Site-wide Soil Characterization Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 9. | Existing vegetation and soils need to be characterized to assess impact of remediation.
[6 empty] | Type and quantity of borrow materials required for regrading and revegetation (depends on design alternative selected). | Y | See borrow investigation sections (400 code activities) | See borrow investigation sections (400 code activities) | See borrow investigation sections (400 code activities)
106 – Waste Rock Dumps
106.1 | Regrade and Reslope Main and Intermediate Sulphide Cells | Faro WRDs and Pit | Consolidate smaller piles of highly reactive material into larger dumps where practical.Predictive modelling (geochemical, hydrologic, and GW/SW interaction) and monitoring program to provide basis for AMP.Alternative – consolidate oxide fines and MGO to sulphide cells as cushioning layer below liner if alternative assessments for those areas warrant doing so. | Chemical compatibility of sulphide cells with other fine grained materials to be capped under very low infiltration liners. Use fines as a cushioning layer for the liner. Delineation of sulphide cell footprint. Suitability of regraded/resloped waste surface to serve as foundation for cover. | Optimize regrading/resloping plan. Develop sediment control plan.Assess GW and SW interaction in affected foundation areas. Assess geotechnical stability of regraded/resloped waste.Assess suitability of regraded/resloped waste surface to serve as cover foundation. Confirm delineation of sulphide cell footprint. For alternatives that include relocating oxide fines and/or MGO to sulphide cells, optimize regrading/resloping plan and use of fines as cushioning layer for the liner. | Confirmation of sulphide cell footprint. | Y | Excavated 12 test pits; no clear delineation of sulfide cells Drilled boring through Main Dump and completed with pore gas and thermistor ports | CH2M HILL Canada Limited (CH2M). March 2015o. Summary of 2014 Field Investigation – Delineate Main and Intermediate Sulphide Cells for Regrading and Capping Design FSP Name: 106.1 – Regrade and Reslope Main and Intermediate Sulphide Cells. Technical memorandum. Prepared for Government of Yukon. March 13. | Data evaluation and analysis required
[6 empty] | Physical characteristics, including gradation of waste rock and any other materials that would form the foundation for the cover (necessary to design cushion layer for very low infiltration cover). | Y
106.2 | Regrade and Reslope Waste Rock Dumps (upper surfaces) | Faro WRDs and Pit | Reduce infiltration in the plateaued upper surface of the dumps. | SW, GW, and geochemical modelling are not well integrated. IPR provided recommendations for review; enhanced modelling is underway to estimate the effectiveness of remediation over time and the application of adaptive management principals. | Update/integrate previous modelling (hydrology, water balance, and geochemical). Develop surface water management plan during and after construction. | Geotechnical characteristics of waste rock and soils. | Y | Excavated seven test pits. | CH2M HILL Canada Limited (CH2M). March 2015p. Summary of 2014 Field Investigation – Regrade and Reslope Faro Waste Rock Dumps (Upper Surface) FSP Name: 106.2 – Regrade and Reslope Faro Waste Rock Dumps (Upper Surfaces). Technical memorandum. Prepared for Government of Yukon. March 13. | Data evaluation and analysis required
|  |  | Construct geotechnically stable landforms. | Location or application of wet landscape features, such as retention ponds/wetlands to retain flood flows and reduce the hydrograph peakiness. | Optimize regrading/resloping plan.
|  |  | Alternative - Consider infiltration galleries to manage 100-year flood conditions. | Destination of surface water runoff from waste rock plateau. | Establish cut/fill volumes for/from outside sources (that is, need for calc-silicate waste rock for drainage material on tailings; addition of material from Haul Road).
|  |  |  | Implications of using infiltration galleries to minimize runoff/sediment erosion. | Develop sediment control plan.
Assess borrow materials (till).
Assess potential locations for large scale waste rock processing facilities to generate appropriately graded borrow.
106.3 | Regrade and Reslope Waste Rock Dumps (perimeter slopes) | Faro WRDs and Pit | Construct geotechnically stable landforms.Minimize erosion of fine grained sediment. Provide robust means to convey storm flows down slopes (failure modes and effects analysis).Alternative: Where possible, use “hybrid” option; combination of talus slopes and revegetated benches. Selective use of infiltration galleries will reduce the potential for erosion (for example, talus slopes). | SW, GW, and geochemical modelling are not well integrated. IPR provided recommendations for review; enhanced modelling in underway to estimate the effectiveness of remediation over time and the application of adaptive management principals. Destination of surface water runoff from waste rock plateau.Implications of using infiltration galleries to minimize runoff/sediment erosion. | Update/integrate previous modelling (hydrology, water balance, and geochemical).Develop surface water management plan during and after construction. Develop sediment control plan.Develop final landform design under the following considerations:Optimizes regrading/resloping;Defines final footprint of the waste rock dumps (for example, shift waste rock laterally to areas with a larger buffer zone between the toe of the slope and downgradient water bodies);Considers Rose Creek stream realignment;Incorporates existing talus slopes for energy dissipations, and;Flattening the waste rock slope upgradient from the S-Wells will cover the seepage interception system and result in the covering Rose Creek (stream realignment considerations). Pulling the material up will be more expensive and technically challenging.Establish cut/fill volumes for/from outside sources (for example, need for calc-silicate waste rock for drainage material on tailings; addition of material from Haul Road, etc.).Assess the potential for using foundation material as borrow in areas where till or organics will be covered by resloped waste pile. Under alternative design option, evaluate “hybrid” closure resloping and regrading geometries – combination of leaving existing talus slopes, adding benches, and selective revegetation. Determine if hybrid combination of talus slopes and benches is suitable for revegetation and if stakeholders will approve.Assess impacts of expanding beyond area covered by current EA (for example, lateral shift of some waste rock material to the SW of the S-Wells may result in disturbance outside of current EA footprint). | Geotechnical and geochemical characteristics of waste rock that will be exposed as a result of regrading/resloping. | Y | See 106.2 | See 106.2 | Data evaluation and analysis required
[6 empty] | Volume of foundation materials at toe of waste rock dumps suitable for borrow. | N | Completed geolocial reconnaissance Excavated seven test pits Drilled and excavated approximately 21 other locations around toe of WRD slopes under other investigations | CH2M HILL Canada Limited (CH2M). March 2015q. Summary of 2014 Field Investigation – Regrade and Reslope Faro Waste Rock Dumps (Toe of Slope) FSP Name: 106.3 – Regrade and Reslope Faro Waste Rock Dumps (Toe of Slope). Technical memorandum. Prepared for Government of Yukon. March 13. CH2M HILL Canada Limited (CH2M). March 2015t. Summary of 2014 Field Investigation – Install Zone II Outwash Collection System FSP Name: 107.4 – Install Zone II Outwash Collection System. Technical memorandum. Prepared for Government of Yukon. March 2. CH2M HILL Canada Limited (CH2M). March 2015u. Summary of 2014 Field Investigation – Install S-Wells Groundwater Collection System FSP Name: 107.5 – Install S-Wells Groundwater Collection System. Technical memorandum. Prepared for Government of Yukon. March 19. CH2M HILL Canada Limited (CH2M). March 2016j. North Fork Rose Creek Geotechnical Report. Draft. Prepared for the Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March 31. | Data evaluation and analysis required
[6 empty] | Locations of suitable areas for infiltration galleries to help control surface runoff and erosion. | Y
[6 empty] | Ecosystem services analysis required to assess options for North Fork Rose Creek (downstream of rock drain) undisturbed reaches, with respect to resloping and cover on adjacent waste rock areas and hydrology of area depending on tailings removal or capping. | N | Work stopped on preparation of Project Proposal |  | Ecosystem services analysis required
106.4 | Cover and Revegetate East Sulphide Waste | Faro WRDs and Pit | Consolidate the smaller piles of highly reactive material into the larger dumps where practical, reduce infiltration, and revegetate. | Effectiveness, reliability, and performance of covers in short term and long term for stability, erosion protection, and reduction of infiltration. Very high-cost item for project. | Infiltration modelling, impacts to GW and SW. Assess design criteria in the C&R Plan, Table 4.9. Cover optimization and identification of source material; optimization of short- and long-term vegetative performance is critical. Consideration of wildlife requirements (habitat and/or exclusion) in cover vegetation design. | Need to review RLU planning basis to determine cover volume and suitability. | N | Completed vegetation and soil survey Worked stopped on project Proposal | CH2M HILL Canada Limited (CH2M). March 2015kk. Vegetation and Soil – 2014 Field Summary Report, Faro Mine Remediation Project Proposal. (Final). Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. CH2M HILL Canada Limited (CH2M). February 2015c. Site-wide Soil Characterization Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 9. | Data evaluation and analysis required
|  |  | Alternative – Subaqueous deposition of sulphidic wastes in Faro Pit. |  |  | Existing site water balance versus water balance after final grading needs to be evaluated to determine surface and GW impacts. | N | Advanced boring through east sulphide cell and completed with GW monitoring well, thermistor and pore gas ports. Work stopped on project proposal | CH2M HILL Canada Limited (CH2M). March 2015b. Summary of 2014 Field Investigation – Site-wide Geochemical Monitoring FSP Name: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Prepared for Government of Yukon. March 31. | Data evaluation and analysis required
106.5 | Cover and Revegetate Main and Intermediate Sulphide Cells | Faro WRDs and Pit | Maximize ET potential of the cover. Minimize energy of runoff from covers and surrounding areas to limit erosion of fine grained sediment. | Proposed reclamation surface is rough and loose; however, the field investigation concluded that the microtopography is sub-optimal for plateau areas as it promotes ponding and infiltration. | Cover optimization and identification of source material; optimization of short- and long-term vegetative performance is critical. Consideration of wildlife requirements (habitat and/or exclusion) in cover vegetation design. | Same as Activity Code 106.1. | N | See 106.1 |  | Data evaluation and analysis required
106.6 | Place Cover on Remaining Waste Rock and Revegetate | Faro WRDs and Pit | Reduce infiltration in the dumps; construct geotechnically stable landforms; maximize diversion of uncontaminated run off from covers and surrounding areas; and revegetate disturbed areas on all dump areas. Revegetation information for steep waste rock areas with loose cover is not provided; feasibility of applying covers to 2:1 slopes and revegetating needs to be considered to confirm that this is a viable RLU. | Additional technical considerations addressed under 106.1A/B. | Steep (2:1) slopes for waste rock are not feasible from a cover and revegetation perspective. Loose cover material faces three issues: how to apply it, how to keep it from working down into the waste rock surface and no longer providing a vegetation support, and how to prevent it from being eroded by surface water. Cover optimization and identification of source material; optimization of short- and long-term vegetative performance is critical. Consideration of wildlife requirements (habitat and/or exclusion) in cover vegetation design. | Review RLU planning basis with Waste Pile and Tailings Discipline Team to provide basis for access, cover material type and available volume. | N | Completed vegetation and soil survey Worked stopped on preparation of project Proposal |  | Data evaluation and analysis required
[6 empty] | Existing site water balance vs. water balance after final grading needs to be evaluated to determine surface and GW impacts. | N |  |  | Data evaluation and analysis required
106.7 | Cover and Revegetate Mt. Mungly (E&W) and Southwest Pit Wall Dump | Faro WRDs and Pit | Apply low-infiltration covers to the Mt. Mungly waste dumps (East and West) and the Southwest Pit Wall Dump. Revegetation information for steep waste rock areas with loose cover is not provided; feasibility of applying covers to 2:1 slopes and revegetating needs to be considered to confirm that this is a viable RLU. |  | Cover optimization. Detailed regrading plans, Reclamation Landform Unit (RLU) specifications.Steep (2:1) slopes for waste rock are not workable from a cover and revegetation perspective. Loose cover material faces three issues: how to apply it, how to keep it from working down into the waste rock surface and no longer providing a vegetation support, and how to keep it from being eroded by surface water. Cover optimization and identification of source material; optimization of short- and long-term vegetative performance is critical.Consideration of wildlife requirements (habitat and/or exclusion) in cover vegetation design. | Need to review RLU planning basis with Waste Pile and Tailings Discipline Team. | N | Completed vegetation and soil survey Worked stopped on preparation of project Proposal | CH2M HILL Canada Limited (CH2M). March 2015kk. Vegetation and Soil – 2014 Field Summary Report, Faro Mine Remediation Project Proposal. (Final). Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. CH2M HILL Canada Limited (CH2M). February 2015c. Site-wide Soil Characterization Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 9. | Data evaluation and analysis required
[6 empty] | Existing site water balance vs. water balance after final grading needs to be evaluated to determine surface and GW impacts. | N |  |  | Data evaluation and analysis required
107 - Faro Groundwater
107.1 | Upgrade North Fork Rose Creek | East Side ARD Collection and Diversions | Protect North Fork of Rose Creek from potential sources of contamination. Divert from Faro waste rock piles. Increase capacity to 1:500 year event at 81 m3/sec and manage the PMF 384 m3/sec. Remove the NFRD and build new channel. | Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. Soil and permafrost conditions, geotechnical conditions, seepage rates, channel stability, flow, seepage, seepage management, contaminate source loading. Location of diversion relative to toe of waste piles, stability of piles, and effects on diversion. Uncertain as to final alignment. NFRC noted to be prone to rockfall hazards (Section 4.6.2) but this is not planned for in consideration of moving the creek channel and replacement of floodplain areas. (Source: C&R Plan Chapter 4). In addition, aquatic assessment recommends more structures and features for fish habitat and reclamation of riparian areas and banks, but there are no details in the Source: C&R Plan. (Chapter 8). The inclusion of Faro diversion as upstream tributary is not yet decided. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. Some site specific hydraulic modelling required to provide water surface profiles.Review design criteria, PMP, PMF and water quality estimates. Channel design needs to provide low infiltration, long-term performance and a floodplain to handle the PMF. Establish final alignment and floodplain characteristics.Geotechnical, water quality, channel stability, seepage, hydrology, hydraulics modelling refinements, design storm flows, icing, soil cover, and re-vegetation options. Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area.Rockfall issues appear to be a natural hazard in headwaters area and a construction hazard when working with the Faro Mine waste rock piles. If Rose Creek is planned to be reconstructed with a liner, then consideration needs to be given to where it is best located in the valley to protect it from rock fall and seepage/GW from the waste rock slopes. Riparian areas in the floodplain need to be an integral part of channel planning. Permafrost impacts on design considerations. Potential Faro diversion as tributary input depends on outcome of Faro diversion evaluations. | Hydrologic and hydraulic model to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results; detailed cross section survey data, bed and bank materials characterizations. Soils data (geotech) ice data, flow data, and water profile data (surface). Additional flow monitoring data collection at Station “R7” for model calibration and validation. | Y | Completed surface geophysical transects across NFRC Completed GW/SW interaction potentiomanometer study upstream of rock drain Completed geological reconnaissance / bed and bank material characterization Completed cross section surveys Completed terrain hazard assessment GW/SW interaction potentiomanomenter study downstream of rock drain Geotechnical Investigation - Drilling, piezometer and thermistor installation, test pitting, surface geophysical surveys, ground temperature monitoring Groundwater Investigation - Aquifer testing, Slug testing, Water Level monitoring, Groundwater sampling Completed rapid geomorphic assessment Completed tracer dilution study, cross section surveys | CH2M HILL Canada Limited (CH2M HILL). March 2014m. 2013 Down Valley Interim Hydraulic Upgrades Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28. CH2M HILL Canada Limited (CH2M). February 2014q. 2013 Cross Valley Dam Seepage Interception System Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 7. CH2M HILL Canada Limited (CH2M). March 2015r. Summary of 2014 Field Investigation – Upgrade North Fork Rose Creek FSP Name: 107.1 – Upgrade North Fork Rose Creek. Technical memorandum. Prepared for Government of Yukon. March 19. CH2M HILL Canada Limited (CH2M). March 2016j. North Fork Rose Creek Geotechnical Report. Draft. Prepared for the Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March 31. CH2M HILL Canada Limited (CH2M). March 2015jj. Geology and Terrain – Preliminary Baseline Report, Faro Mine Remediation Project Proposal. Final. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. CH2M HILL Canada Limited (CH2M). March 2015t. Summary of 2014 Field Investigation – Install Zone II Outwash Collection System FSP Name: 107.4 – Install Zone II Outwash Collection System. Technical memorandum. Prepared for Government of Yukon. March 2. CH2M HILL Canada Limited (CH2M). March 2015u. Summary of 2014 Field Investigation – Install S-Wells Groundwater Collection System FSP Name: 107.5 – Install S-Wells Groundwater Collection System. Technical memorandum. Prepared for Government of Yukon. March 19. CH2M Canada Limited (CH2M). March 2016b. Preliminary Final North Fork Rose Creek Design Basis Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March. CH2M Canada Limited (CH2M). April 2016h. Summary of 2015 Field Investigation – West Side and East Side Diversions, Faro Mine Remediation Project. Technical memorandum. Draft. Prepared for Government of Yukon. April. CH2M Canada Limited (CH2M). March 2016i. North Fork Rose Creek Hydrology/Hydraulics Report. Draft. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March 31.
|  |  | Divert from Faro waste rock piles. Increase capacity. |  |  | Integrated planning required for the NFRC channel and valley area (including riparian and ponded areas), in conjunction with activities to reslope waste rock pile and remove all or part of haul road; need to weigh against possible cut-off wall construction. | Y
|  |  | Design to preliminary design level of detail. |  |  | Ecosystem Services analysis required to quantify creek protection options for cut-off wall, creek liner, remove rock drain, and realign creek. | Y
|  |  | Requires final selection of preferred alternative through an alternatives assessment. |  |  | Impact of rerouting creek beds to reduce contaminated GW impact or construction of slurry walls that may cause daylighting of GW. | Y
107.2 | North Fork Rose Creek Cut-off Wall | East Side ARD Collection and Diversions | Protect NFRC from contamination. Construct cut-off wall and isolate creek from GW interception. | Location for placing wall; effectiveness, requirements for pumping (volume, duration, construction materials, and timing for pumping, and automation). Potential for bypassing cutoff and contaminating GW. | Optimize location for accessibility, short term, and long term performance; evaluate construction materials; reduce cost; and maximize GW cutoff effectiveness. | Hydrologic and hydraulic modeling to provide influent SW flow data and elevations. | Y | Design Concept Changed - See 107.1 | CH2M Canada Limited (CH2M). March 2016b. Preliminary Final North Fork Rose Creek Design Basis Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March.
[6 empty] | Integration of SW and GW modelling approaches and results. | Y
[6 empty] | Detailed cross section survey data and bed and bank material characterizations. | Y
[6 empty] | Soils data (geotechnical), ice data, flow data, and water profile data (surface elevations). | Y
[6 empty] | Bedrock contact delineation. | Y
107.3 | Relocate Zone II Outwash Material to Intermediate Sulphide Cell | East Side ARD Collection and Diversions | Remove outwash material to Intermediate Sulphide Cell to reduce contaminant loading to NFRC and underlying aquifer; and construct access roads. | Stability of upgradient waste rock slope under current condition and during materials relocation. | Assessment of volumes of Zone II Outwash materials and underlying impacted soils to relocate. | Volume of materials, including underlying impacted soils to relocate. | Y | Design concept changed - See 107.1 Excavated four test pits (3 in outwash, 1 in upgradient Waste Rock Slope) Drill, install and develop 8 monitoring wells | CH2M Canada Limited (CH2M). March 2016b. Preliminary Final North Fork Rose Creek Design Basis Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March. CH2M HILL Canada Limited (CH2M). March 2015t. Summary of 2014 Field Investigation – Install Zone II Outwash Collection System FSP Name: 107.4 – Install Zone II Outwash Collection System. Technical memorandum. Prepared for Government of Yukon. March 2. CH2M HILL Canada Limited (CH2M). March 2015s. Summary of 2014 Field Investigation – Relocate Zone II Outwash Material to Intermediate Sulphide Cell FSP Name: 107.3 – Relocate Zone II Outwash Material to Intermediate Sulphide Cell. Technical memorandum. Prepared for Government of Yukon. March 19.
|  |  | Alternative - Cover in place. | Volume depth of affected materials that will need to be relocated. | Geotechnical assessment of upgradient waste rock slope under current conditions and during relocation activities. | Stability of upgradient waste rock slope | N |  |  | WRD Slope stability evaluation required
[5 empty] | Final landform design that incorporates upgradient waste rock dump. | Leaching characteristics of Zone II Outwash Material | Y
[5 empty] | Alternatives Assessment - Relocate outwash material versus cover in place. |  |  | Scope of work has changed based on NFRC DBR
107.4 | Install Zone II Outwash Collection System | East Side ARD Collection and Diversions | Intercept seepage from the Zone II Outwash Area; reduce contaminant loading to the NFRC and underlying aquifer. | Configuration of bedrock surface. Distribution of aquifer properties. Magnitude and distribution of surface water/groundwater interaction between the NFRC and the underlying alluvial aquifer. Extent of GW contamination in the deeper portions of the aquifer. Response of aquifer system to GW pumping.Magnitude of site water budget components. Geochemical conditions within the aquifer and potential for well fouling. Number of wells required for effective interception. Need for permeable trench and cut-off walls. Number and spacing of extraction wells; permeable trench location. Estimate GW flow and contaminant mass loading from extraction system (average and peak). | Develop three-dimensional numerical GW flow model. Investigate various alternative configurations of SIS design to optimize efficiency and minimize cost. Define bedrock surface. Define distribution of aquifer properties. Determine three dimensional extent of GW contamination. Quantify site water budget. Define degree and pattern of surface water/groundwater interaction. | Spatial distribution of alluvial aquifer thickness in outwash zone. | Y | Drill, install and develop 8 monitoring wells. Complete packer testing in bedrock. Complete stream stage monitoring. Complete surface geophysical transect. Design concept changed - See 107.1 | CH2M Canada Limited (CH2M). March 2016b. Preliminary Final North Fork Rose Creek Design Basis Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March. CH2M HILL Canada Limited (CH2M). March 2015t. Summary of 2014 Field Investigation – Install Zone II Outwash Collection System FSP Name: 107.4 – Install Zone II Outwash Collection System. Technical memorandum. Prepared for Government of Yukon. March 2.
[6 empty] | Spatial distribution of bedrock topography in outwash zone. | Y
[6 empty] | Hydraulic properties of the backfill materials in Zone II Pit. | Y
[6 empty] | Spatial and temporal extent of GW/SW interaction between the alluvial aquifer and the NFRC. | Y
[6 empty] | Horizontal GW flow patterns in the bedrock aquifer. | Y
[6 empty] | Three-dimensional distribution of contaminants near the proposed GW interception system. | Y
[6 empty] | Extent of hydraulic connection between the Zone II Pit and the outwash area, and the GW flux originating in the vicinity of the pit. | Y
107.5 | Install S-wells GW Collection System | East Side ARD Collection and Diversions | Upgrade and complete existing GW SIS. Provide for permanent pumps, piping, power, and access. | Configuration of bedrock surface. Distribution of aquifer properties. Response of aquifer system to GW pumping. Magnitude of site water budget components. Geochemical conditions within the aquifer and potential for well fouling. Number of wells required for effective interception. Need for cut-off wall. | Develop three-dimensional numerical GW flow model. Investigate various alternative configurations of SIS design to optimize efficiency and minimize cost. | Alluvial aquifer thickness and the hydraulic properties of the alluvial and bedrock aquifers north of the SIS. | Y | Design concept changed - See 107.1 Drill, install and develop 6 monitoring wells Install and monitor 16 streambed piezometers for GW/SW interaction study Complete one seismic refraction geophysics line | CH2M HILL Canada Limited (CH2M). March 2015u. Summary of 2014 Field Investigation – Install S-Wells Groundwater Collection System FSP Name: 107.5 – Install S-Wells Groundwater Collection System. Technical memorandum. Prepared for Government of Yukon. March 19. CH2M Canada Limited (CH2M). March 2016b. Preliminary Final North Fork Rose Creek Design Basis Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March.
[6 empty] | Aquifer properties of the deep weathered bedrock aquifer in the vicinity of the existing SIS. | Y
[6 empty] | Alluvial aquifer properties between existing SIS and the NFRC. | Y
[6 empty] | Bedrock topography in the vicinity of the existing SIS. | Y
[6 empty] | Spatial and temporal extent of GW/SW interaction between the alluvial aquifer and the NFRC. | Y
107.6 | S-Wells GW Collection (part of ADM to capture future concentrated zones near source) | East Side ARD Collection and Diversions | Shallow and deep aquifer interception systems were constructed in 2009. Final component is installation of cut-off wall if monitoring indicates shallow aquifer sump and deep aquifer pumping wells do not provide sufficient capture. | Evaluation of adequacy of shallow and deep aquifer pumping wells to provide sufficient capture of contaminated GW. Method of installation of the cut-off wall; location of bedrock, extent of wall required, and requirements for additional wells. | Three-dimensional GW flow model; incorporate most recent operational data to estimate effectiveness of existing SIS and system enhancements. Conduct optimization study to maximize the capture of contaminated GW flow and cost. | GW seepage will be addressed at this site by the activities recommended under Activity Code 107.5. | Y | See 107.5 | See 107.5
108 - Faro Miscellaneous
108.1 | Reclaim Unnecessary Roads | Sitewide | Prevent long-term erosion and breach crossings to prevent blockage. | Road areas will require specific reclamation plans in keeping with required surface drainage plans and surrounding reclamation prescriptions. | Assessment needs to be made about culverts and crossings to be breached and resloped, and drainages restored. Previous closure prescription is to scarify road surfaces and revegetate, but no information available on quality of road construction materials. | Require assessment of road material quality. | N
[6 empty] | Require assessment for basis of design of road reclamation – revegetation or swale/channel formation as part of surface drainage plan. | N | Worked stopped on Project Proposal |  | Assessment of roads; existing conditions; RPP plans for roads
108.2 | Reclaim Zone II Outwash Area | Faro WRDs and Pit | Cover and revegetate Zone II Outwash Area after installation of collection system to provide stable creek floodplain. Alternative design: Cap in place. | Configuration of outwash collection system and final placement of NFRC after rock drain is removed will dictate the cover and revegetation plan surface. Revegetation of this area is not currently considered within the reclamation plan but needs to be tailored to location of NFRC (if moved) and to existing valley vegetation. | Once location of reconfigured NFRC is planned; need to assess loss of current vegetation cover and what can be salvaged and moved to other locations for soil and vegetation. Area may be covered by waste rock if NFRC is moved. | Assess current vegetation cover. | Y | Conduct sitewide Vegetation and Soil survey | CH2M HILL Canada Limited (CH2M). March 2015kk. Vegetation and Soil – 2014 Field Summary Report, Faro Mine Remediation Project Proposal. (Final). Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. CH2M HILL Canada Limited (CH2M). February 2015c. Site-wide Soil Characterization Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 9.
[6 empty] | Assess current soil type and quality. | Y | Design Concept Changed - See 107.1
[6 empty] | Locate stockpiling or direct placement areas. | Y
[6 empty] | Confirm availability of suitable cover material. | Y
[6 empty] | Confirm availability of suitable riparian plant species. | Y
108.3 | Decontaminate and Demolish Buildings | Mill and ETA | The existing mill, administrative buildings, and surrounding infrastructure will be removed to mitigate potential long-term safety hazards. Extent of contamination of surfaces through plant is unknown. | Sampling for ACM and other designated substances may not be substantive enough to be useful for decommissioning purposes. Areas around buildings that are not tested may need to be treated as designated or ACM substances. Extent of process materials (rock and others) in pipelines, equipment, vessels, and holding areas is not extensively documented. Requirement to remove extensive volumes of this material will complicate decommissioning. Site plans, surveys, Material Safety Data Sheets, and other information involving plant construction and makeup are not currently available. A review of laydown areas in close proximity to the plant (boneyards) has not been completed. Implications and cost for decommissioning has not been evaluated. Options to revegetate and reclaim the site as part of the natural landscape after decommissioning need to be evaluated. Site survey required. | Site visit to identify items that might have been missed. Follow up sampling may be required. Address safety concerns with any of the onsite buildings and to clear areas for safe access to complete other assessments that may be required. Perform site utility surveys. Use ground penetrating radar (GPR) if necessary for decommissioning and to understand H&S risks during work. Determine and obtain permits required to perform demolition. Analyze existing structures (plans if available) to determine less costly design for removal, decontamination, transport, and recycling or placement in a landfill. Hold discussions with Care and Maintenance staff to identify potential underground structures. Review and catalogue mill drawings. | Obtain, review, and catalogue site and building as-built plans and other construction documentation. | Y | Compiled and scanned available as-built plans and construction documentation
[6 empty] | Determine if sufficient sampling has been performed to mitigate costs for abatement of materials assumed to contain designated substances due to lack of information to the contrary. | N | Work stopped on preparation of Project Proposal
[6 empty] | Building and waste materials quantification. | N |  |  | Building and waste materials quantification.
[6 empty] | Waste disposal recommendations. | N |  |  | Waste disposal recommendations.
[6 empty] | Salvage assessment and evaluation of transportation cost to ship scrap to markets. | N |  |  | Salvage assessment and evaluation of transportation cost to ship scrap to markets.
[6 empty] | Utility and site surveys. | N |  |  | Utility and site surveys.
[6 empty] | Confirm availability of suitable cover material. | N | See borrow investigation sections (400 code activities) | CH2M HILL Canada Limited (CH2M). March 2015hh. Borrow Baseline Design Criteria Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. | Cover analysis and agreement of final cover design is requried
[6 empty] | Assess suitable revegetation cover and cover microtopography. | N | Work stopped on preparation of Project Proposal |  | Assess suitable revegetation cover and cover microtopography.
[6 empty] | Extent of contamination is not certain. | N |  |  | Extent of contamination is not certain.
[6 empty] | Appropriate cover type and revegetation plan needs to be assessed for this area for long-term liability management. | N |  |  | Appropriate cover type and revegetation plan needs to be assessed for this area for long-term liability management.
[6 empty] | Determine if portions of foundations may be covered and revegetated. Determine available cover material types and volumes and appropriate revegetation plan. | N |  |  | Determine if portions of foundations may be covered and revegetated. Determine available cover material types and volumes and appropriate revegetation plan.
108.4 | Relocate Contaminated Soil from Mill Site Area and Cover (rudimentary) | Mill and ETA | Remove hazardous materials and contaminated soil from Plant Site Area. Regrade Mill Area, cover, and revegetate. | Characterize contaminants, identify contamination levels, determine volume of material excavation; volume and source of backfill. | Determine appropriate location for an onsite landfarm for hydrocarbon contaminant treatment. | Extent of soil metals and hydrocarbon contamination and acid generating soils (lateral and vertical) near the Vehicle Maintenance Complex, Emergency Generator Area, Mill Diesel Tank, and Waste Oil Tank. | N | Work stopped on preparation of Project Proposal |  | Extent of soil metals and hydrocarbon contamination and acid generating soils (lateral and vertical) near the Vehicle Maintenance Complex, Emergency Generator Area, Mill Diesel Tank, and Waste Oil Tank.
|  |  |  | Concentration threshold criteria for soil removal. | Specific revegetation prescription required, especially because this area is a candidate for an ET cover. | GW flow directions. | Y |  | CH2M Canada Limited (CH2M). April 2016c. Fiscal Year 2015 Groundwater Flow Model Development Report, Faro Mine Remediation Project. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. April 5.
[5 empty] | Hold discussions with Care and Maintenance staff to identify potential underground structures. | Extent of associated GW contamination. | N |  |  | Extent of associated GW contamination.
[6 empty] | Assess suitable cover material quality. | N |  |  | Assess suitable cover material quality.
[6 empty] | Assess potential for ET vegetation cover, or appropriate revegetation prescription. | N |  |  | Assess potential for ET vegetation cover, or appropriate revegetation prescription.
108.5 | Relocate Contaminated Soil from Faro Lube Shack and Tank Farm Area and Cover (rudimentary) | Faro WRDs and Pit | Remove hazardous materials and contaminated soil from the Plant Site Area. Regrade Mill Area, cover, and revegetate. | Characterize contaminant levels, determine volume of material excavation; volume and source of backfill. | Determine appropriate location for onsite landfarm for hydrocarbon contaminant treatment. | Determine permitting requirements | N |  |  | No work done on permitting
|  |  |  | Concentration threshold criteria for soil removal. | Specific revegetation prescription required, especially because this area is a candidate for an ET cover. | Extent of soil hydrocarbon contamination (lateral and vertical) near the Lube Shack and Tank Farm Area. | N | Two test pits completed to augment delineation performed by Gartner Lee (2005) | CH2M HILL Canada Limited (CH2M). March 2015v. Summary of 2014 Field Investigation – Relocate Contaminated Soil from Faro Lube Shack and Tank Farm Area and Cover FSP Name: 108.5 – Relocate Contaminated Soil from Faro Lube Shack and Tank Farm Area and Cover. Technical memorandum. Prepared for Government of Yukon. March 12. Gartner-Lee Limited (GLL). June 2006. Anvil Range Mine – 2015 Investigation of Hydrocarbon-Contaminated Soils. June. | Extent of soil hydrocarbon contamination (lateral and vertical) near the Lube Shack and Tank Farm Area.
[5 empty] | Hold discussions with Care and Maintenance staff to identify potential underground structures. | GW flow directions. | Y | Site-wide modelling completed showing flowpaths | CH2M Canada Limited (CH2M). April 2016c. Fiscal Year 2015 Groundwater Flow Model Development Report, Faro Mine Remediation Project. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. April 5.
[6 empty] | Extent of associated GW contamination. | N | Not expected that special covers; other than rudimentary covers, would be required for area. All contamination expected to be moving to either RCTA or to Faro Pit |  | Extent of associated GW contamination.
[6 empty] | Assess suitable cover material quality. | N | See borrow investigation sections (400 code activities) |  | Assess suitable cover material quality.
[6 empty] | Assess potential for ET vegetation cover, or appropriate revegetation prescription. | N |  |  | Assess potential for ET vegetation cover, or appropriate revegetation prescription.
Tailings Area (Activity Code 200)
201- Dams
201.1 | Dewater Intermediate Tailings Area | RCTA | Current concept is for a dry revegetated surface on top of a cover over all the tailings surfaces. Evaluate potential for backfilling the Intermediate Pond with coarse granular (for example, processed waste rock) or dewatered (dry) tailings prior to installing cover and revegetation of cover. Revegetated surface and surface runoff will be isolated from tailings porewater. | Geochemical and geotechnical characteristics of tailings slimes and sediments. | Evaluation of tailings consolidation and the need for the waste rock trafficability layer to act as a drainage layer. | Rheologic parameters of tailings to evaluate pumpability and thickening characteristic. Geotechnical information for the area within 500m of the Intermediate Dam. | Y | (1) agreed upon closure approach does not require this information | CH2M HILL Canada Limited (CH2M). March 2015ff. Alternative Development Status Report. Draft. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 6. CH2M HILL Canada Limited (CH2M HILL). November 2012e. Alternatives Evaluation and Risk Analysis for the Rose Creek Tailings Area, Faro Mine. Prepared for Yukon Government. November.
|  |  |  | Volume of sediment. | Evaluation of the depth of freezing within the fine zone of the Intermediate Tailings Area and the implications for trafficability. | Geotechnical parameters (for example, undrained shear strength, depth of tailings, and porewater pressure). | Y | Drilled 5 borings and advanced 12 CPT soundings in Intermediate Tailings Installed and monitored 5 thermistor ports in intermediate tailings Advanced 8 CPT soundings in intermediate dam pond Completed bathymetric survey with subbottom profiling Data requirements for 30% design reduced from that required for 60% design | CH2M HILL Canada Limited (CH2M). March 2015x. Summary of 2014 Field Investigation – Dewater and Cover Intermediate Tailings Area FSP Name: 201.1 – Dewater and Cover Intermediate Tailings Area. Technical memorandum. Prepared for Government of Yukon. March 13. CH2M HILL Canada Limited (CH2M). March 2015z. Summary of 2014 Field Investigation – Construct New Side Channel and Side Channel Dike FSP Name: 201.5 – Construct New Side Channel and Side Channel Dike. Technical memorandum. Prepared for Government of Yukon. March 13. CH2M HILL Canada Limited (CH2M HILL). November 2012e. Alternatives Evaluation and Risk Analysis for the Rose Creek Tailings Area, Faro Mine. Prepared for Yukon Government. November. RCTA Alternatives Analysis CH2M HILL Canada Limited (CH2M). August 2016c. Summary of Fiscal Year 2015 – 2016 Field Investigations – CVD and ID Pond Field Data Report. Technical memorandum. Prepared for Government of Yukon. August 25. Aurora Geosciences. 2016b. Technical Report. Hydrographic and Sub-Bottom Profiling Survey – Intermediate Dam Pond. Prepared for CH2M HILL. August 12. CH2M HILL Canada Limited (CH2M). March 2015ff. Alternative Development Status Report. Draft. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 6. CH2M HILL Canada Limited (CH2M HILL). March 2014i. Task Authorization 015 Cross Valley Dam Seepage Interception System Phase 2 – Basis of Design Report, Faro Mine Remediation Project. Draft. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28. (60% design)
|  |  |  | Dewatering characteristics. | Time for consolidation to occur. Assess need for accelerated consolidation (for example, wick drains or similar). | Consolidation characteristics of tailings to enable prediction of tailings porewater expelled, rate of consolidation, and total depth of consolidation (to model drainage above tailings). | Y
|  |  |  | Sediment control and method of removal. |  | Seepage/water balance to determine design requirements of the backfilled pond area adjacent to the Intermediate Dam and options for actively managing tailings seepage by sump dewatering. | Y |  |  | Continue to monitor GW levels; impoundment levels at ID and CVD, pumped volumes to IWTS. Compile for water balance analysis.
[6 empty] | Possible requirement for processing waste rock for the trafficability layer to enable function as a drainage layer. | Y
[6 empty] | Evaluation of freezing profile. | Y
201.2 | Dewater Cross-valley Dam Pond | RCTA | Dewater the pond by pumping the water to the Faro Pit. Current concept is to retain the Cross Valley Dam, but to keep the Cross Valley Pond drained. Remove sludge and sediments to (1) facilitate construction of the Intermediate Tailings Dam raise and (2) to create a surface that can be revegetated. Collections systems to be installed downstream of the Intermediate Dam within the CVP area. | Chemical and physical characteristics of sludge and sediments; volume of sediment; dewatering characteristics; method for controlling surface and groundwater during excavation. Sediment control and method of removal. | Methods of dewatering, treatment as required, and discharge of treated water. Methods of sludge removal, stabilization/drying of sludge, transportation of sludge, and sludge disposal at the existing sludge pond north of tailings impoundment. Stability of Intermediate Tailings Dam (seepage and piping, and drawdown slope stability) after dewatering of the Cross Valley Impoundment. | Volume of sludge and sediment to be removed at Cross Valley Dam Pond. [Previous investigation by Ecometrix (Report titled Investigation on Zinc Controls at the Cross Valley Pond – Faro Mine Complex dated October 2010 was to investigate zinc concentrations in pond water, sludge and porewater in the CVP. Chemical testing was performed and lime demand estimated. The study did not characterize the volumes of sludge] | Y | Completed bathymetric survey with subbottom profiling Advanced 3 CPT soundings and 8 sonic borings | Aurora Geosciences. 2016a. Technical Report. Hydrographic and Sub-Bottom Profiling Survey – Cross Valley Dam Pond. Prepared for CH2M HILL. August 22. CH2M Canada Limited (CH2M). August 2016c. Summary of FY 2015 Field Investigations – CVD and ID Pond Field Data Report, Field Sampling Plan Name: CVP and ID Pond CPT and Sonic Sampling. Technical memorandum. Prepared for Government of Yukon. August 15.
[6 empty] | Conduct geochemical and treatability testing as necessary [Ecometrix report has some information]. Rheologic parameters of sediment to evaluate pumpability and thickening characteristics) | Y
201.3 | Retain Cross-valley Dam | RCTA | To keep Cross Valley Pond as emergency storage facility and to capture any potential contaminated seep water. To allow flood water to egress from the Intermediate Dam spillway into the Cross Valley Pond, then exit through a new PMF spillway at the Cross Valley dam, and then enter the Rose Creek downstream from the Cross Valley Dam. | Removal of Cross Valley Dam needs to be further evaluated. IRP recommends Cross Valley Pond be retained. Requires evaluation of Cross Valley Dam stability and spillway requirements (hydrology, hydraulics, and foundation conditions. Location and foundation conditions for downstream SIS will need evaluation. | Identify operational failure scenarios in which the Cross-valley Pond would be used if retained. Evaluate the potential effectiveness of treatment that would be provided under those scenarios. Flood routing (hydraulics) study: Route flow through pond and spillway at right abutment of Cross Valley Dam. Flood routing/dissipation in area downstream from Cross Valley Dam before floodwater discharges into Rose Creek If Cross Valley Dam is retained, dam stability evaluations: Seepage and slope stability Liquefaction potential and mitigation Deformation analyses (seismic) Slope protection Geotechnical instrumentation | Foundation conditions for new PMF Spillway and low level outlet. | N | Completed surface geophysical surveys at CVD spillway Excavated test pit in CVD Spillway | CH2M Canada Limited (CH2M). April 2016f. Summary of 2015 Field Investigation – Construct Intermediate Dam Spillway, Faro Mine Remediation Project, Field Sampling Plan Name: 201.6 Construct Intermediate Dam Spillway. Technical memorandum. Draft. Prepared for Government of Yukon. April. CH2M HILL Canada Limited (CH2M). January 2015b. Cross Valley Dam Seepage Interception System Test Pit Data Summary, Faro Mine Remediation Project. Technical memorandum. Draft. Prepared for Government of Yukon. January 30. | Investigation needs to be conducted for CVD spillway
[6 empty] | Hydrologic and hydraulic model to provide influent SW flow data and elevations as well as routing and velocity data for spillway to Rose Creek. | N |  |  | Hydrualic model development
201.4 | Raise Intermediate Dam (ID) | RCTA | To pass – without overtopping – floods larger than the 500-year return event and up to the Probable Maximum Flood (PMF) and route through new spillway. Consider dam stability and contaminated groundwater collection. Based on preliminary hydrologic analyses, an Intermediate Dam raise to El 1052 m (about 2.6m raise) is estimated | Dam stability during PMF (flooding) and maximum credible earthquake (MCE) (seismic) events; requirements to modify internal drain and filters (will no longer have Cross Valley Dam water against downstream slope); liquefaction potential and seismic slope stability. Need to finalize/verify the amount of dam raise. | Flood routing (hydraulic) study to determine optimum dam raise in conjunction with spillway configuration and size. Dam stability evaluations: Seepage and slope stability Internal filter and drain system adequacy Liquefaction potential and mitigation Deformation analyses (static and seismic) Borrow material considerations Slope protection Geotechnical instrumentation Design of dewatering and excavation requirements for regrading tailings, including contaminated groundwater collection. | Borrow material sources and borrow material characteristics (dike and dam embankment materials, filter/drain material, slope protection, tailing covers). Assume that Cross Valley Dam will be drained with no tailwater against the downstream slope. | Y | See borrow investigation sections (400 code activities)
[6 empty] | Tailings permeability for dewatering (assumed to be covered under the Tailings Cover task). | Y | Drilled 5 borings and advanced 12 CPT soundings in Intermediate Tailings | CH2M HILL Canada Limited (CH2M). March 2015x. Summary of 2014 Field Investigation – Dewater and Cover Intermediate Tailings Area FSP Name: 201.1 – Dewater and Cover Intermediate Tailings Area. Technical memorandum. Prepared for Government of Yukon. March 13. CH2M HILL Canada Limited (CH2M). March 2015z. Summary of 2014 Field Investigation – Construct New Side Channel and Side Channel Dike FSP Name: 201.5 – Construct New Side Channel and Side Channel Dike. Technical memorandum. Prepared for Government of Yukon. March 13. | Analysis of CPT data required
[6 empty] | Hydrologic and hydraulic model to provide influent SW flow data and elevations as well as routing and velocity data. | N |  |  | Hydrualic model development
201.5 | Construct New Side Channel and Side Channel Dike | RCTA | In 2012, CH2M HILL performed an alternatives evaluation for flood routing of the Rose Creek through the Rose Creek tailings area. The evaluations are documented in the CH2M HILL report titled “Conclusions from Rose Creek Tailings Area Alternatives Evaluation” dated November 2012. This report details the evaluation of three different alternatives to route flood flows through the RCTA, and the risk analyses that were performed to form the basis for selecting a preferred alternative. The preferred alternative entailed the use of a single, large, armoured channel (the side channel) located immediately adjacent (north) of the Rose Creek Diversion (RCD) into which flood flows greater than the 500-year flood will be channeled. Flood flows in the side channel would then be routed through a new PMF Spillway at the right abutment of the Intermediate Dam. | Foundation conditions for new side channel dike. Thickness and nature of tailings under the dike as well as the side channel bottom footprint. Stability and integrity of the existing Rose Creek Diversion dike | Side channel dike stability evaluations: Seepage and slope stability Internal filter and drain system adequacy Liquefaction potential and mitigation Deformation analyses (static and seismic) Borrow material considerations Slope protection Geotechnical instrumentation Design of dewatering and excavation requirements for tailings below the side channel, or means for stabilizing/confining it in place. | Subsurface information (foundation conditions) along the RCDC dike. | Y | Drilled 5 borings and advanced 12 CPT soundings in Intermediate Tailings Installed and monitored 5 thermistor ports in intermediate tailings | CH2M HILL Canada Limited (CH2M). March 2015x. Summary of 2014 Field Investigation – Dewater and Cover Intermediate Tailings Area FSP Name: 201.1 – Dewater and Cover Intermediate Tailings Area. Technical memorandum. Prepared for Government of Yukon. March 13. CH2M HILL Canada Limited (CH2M). March 2015z. Summary of 2014 Field Investigation – Construct New Side Channel and Side Channel Dike FSP Name: 201.5 – Construct New Side Channel and Side Channel Dike. Technical memorandum. Prepared for Government of Yukon. March 13.
201.6 | Construct Intermediate Dam Spillway | RCTA | Route the peak flood flows large enough to erode the fuse plug without overtopping the Intermediate Tailings Dam. Construct new spillway in bedrock at the north abutment of Intermediate Tailings Dam. Consider alternative of passing design flood over the top of a hardened embankment. Operational considerations: SW assumed to be clean (long-term) and gravity drain; SW to be collected initially for monitoring and possible treatment GW to be collected in waste rock layer underneath till cover and pumped for treatment | Optimize dam raise with spillway design (size, location, invert, overflow length, and location of tailings. Design criteria require review. | Flood routing (hydraulics) study: PMF flood Flow velocity Scour criteria Incorporate potential for ice flows in flood routing For concrete control structure, perform seepage analyses to evaluate uplift forces and to design underdrain, uplift, or both Flow routing downstream from Intermediate Dam including channelization and erosion protection Potential for winter flows and ice blockages | Subsurface conditions for spillway: | Y |  | CH2M HILL Canada Limited (CH2M HILL). March 2014m. 2013 Down Valley Interim Hydraulic Upgrades Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28. | Discussion of bypass spillway, directing overflow from Intermediate pond around the CVP to discharge to Rose Creek.
[6 empty] | Rock mass quality | Y | Drilled 7 borings into bedrock Completed packer testing Installed and developed 2 pumping wells and 3 piezometers Completed surface geophyscial surveys | CH2M Canada Limited (CH2M). April 2016f. Summary of 2015 Field Investigation – Construct Intermediate Dam Spillway, Faro Mine Remediation Project, Field Sampling Plan Name: 201.6 Construct Intermediate Dam Spillway. Technical memorandum. Draft. Prepared for Government of Yukon. April. CH2M HILL Canada Limited (CH2M). March 2015aa. Summary of 2014 Field Investigation – Construct Intermediate Dam Spillway FSP Name: 201.6 – Construct Intermediate Dam Spillway. Technical memorandum. Prepared for Government of Yukon. March 13. | Aquifer tests in pumping wells
[6 empty] | Erosion resistance | Y
[6 empty] | Permeability (to evaluate uplift and seepage under concrete control spillway structure) | Y
[6 empty] | Subsurface conditions for energy structure/modifications downhill from the spillway. | Y
[6 empty] | Hydrologic and hydraulic model to provide influent SW flow data and elevations as well as routing and velocity data for spillway. PMF handling has been assessed previously and considerable information is available. Flooding information should be incorporated into any new hydraulic models developed. | N |  |  | Hydrualic model development
201.7 | Stabilize Secondary Dam by Densifying Foundations for East Limb Embankment | RCTA | Mitigation against liquefaction and dam instability during MCE. Also include embankment stability under all other loading conditions and erosion protection during PMF flooding. | Most cost-effective seismic mitigation: Extent of liquefaction and slope instability Appropriate methods of ground improvement | Pseudo-static LE analyses to evaluate different stabilization alternatives. Two-dimensional (FLAC2D) dynamic/seismic analyses to more appropriately determine the cyclic shear stresses in the embankments for liquefaction assessments and mitigation design (shortcoming of the previous liquefaction assessment was using SHAKE91 [a one-dimensional analysis] for two-dimensional geometry). Use FLAC2D to evaluate seismic deformation to optimize mitigation options. Criteria for acceptable deformations must be established first. | Subsurface information covering the full length (for example, filling the gaps, of the East Limb of Secondary Dam) (existing borings tend to be clustered with gaps greater than 500 m between clusters). | Y | Drilled and installed 3 well pair clusters with provision for downhole GPX Completed downhole and surface geophysical surveys Completed pump testing and groundwater monitoring at well clusters | CH2M Canada Limited (CH2M). March 2016b. Preliminary Final North Fork Rose Creek Design Basis Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March.
[6 empty] | Shear wave velocity (Vs) information. Liquefaction assessments will be more reliable with direct measurement of Vs instead of estimating these values from correlations with SPT blowcounts. | Y
202 - Tailings Cover
202.1 | Cover Intermediate Tailings Area | RCTA | Prevent direct contact by wildlife with the tailings and minimize contaminated runoff. Current concept is for a dry revegetated surface on top of a cover over complete intermediate tailings surfaces. The Intermediate Pond will be filled with coarse granular (for example, processed waste rock) or dewatered (dry) tailings prior to installing cover and revegetation of cover. | The condition of the surface of the tailings within the tailings area varies by season. These conditions limit when and where equipment can successfully work on the tailings surface. Behavior of cover surface over long term after adding large fill thickness in pond area. | Determine settlement/differential settlement predictions; determine stability assessments (for example, edge effects during construction); hydrology, energy dissipation features; TEMP/W drainage, slope stability, and settling assessments; design of basal support layer (waste rock or geogrid); manage risks associated with differential settlement especially in area of energy dissipation features. Determine cover placement method, depth of cover material, suitable surface cover material and microtopography features. Revegetation cover design requires consideration of ET or other cover requirements. | Hydrologic and hydraulic model to provide influent SW flow data and elevations as well as routing and velocity data in relation to swales. Erosive and conveyance characteristics of swales materials and vegetative cover. | N | Work on Project Proposal and Cover Design Stopped | CH2M HILL Canada Limited (CH2M). March 2015x. Summary of 2014 Field Investigation – Dewater and Cover Intermediate Tailings Area FSP Name: 201.1 – Dewater and Cover Intermediate Tailings Area. Technical memorandum. Prepared for Government of Yukon. March 13. CH2M HILL Canada Limited (CH2M). March 2015z. Summary of 2014 Field Investigation – Construct New Side Channel and Side Channel Dike FSP Name: 201.5 – Construct New Side Channel and Side Channel Dike. Technical memorandum. Prepared for Government of Yukon. March 13. See borrow investigation sections (400 code activities) | Hydrologic and hydraulic model to provide influent SW flow data and elevations as well as routing and velocity data in relation to swales. Erosive and conveyance characteristics of swales materials and vegetative cover.
[6 empty] | Source of base granular drainage material, filter compatible layer and final cover. Implications of geochemistry (leachability, decomposition of waste rock above tailings). |  |  |  | Source of base granular drainage material, filter compatible layer and final cover. Implications of geochemistry (leachability, decomposition of waste rock above tailings).
[6 empty] | Determine if material from NFRD the best source or can “less useful” waste rock be used. |  |  |  | Determine if material from NFRD the best source or can “less useful” waste rock be used.
[6 empty] | Thickness of growth media (water balance). |  |  |  | Thickness of growth media (water balance).
[6 empty] | Energy dissipation structure design and risks. |  |  |  | Energy dissipation structure design and risks.
[6 empty] | Ultimate contouring of tailings impoundment and the dynamics of any future intermediate pond (emergent vegetation). |  |  |  | Ultimate contouring of tailings impoundment and the dynamics of any future intermediate pond (emergent vegetation).
[6 empty] | Feasibility of sump in WR pore space adjacent to the Intermediate Dam to store tailings porewater covered with till/clay revegetated layer. |  |  |  | Feasibility of sump in WR pore space adjacent to the Intermediate Dam to store tailings porewater covered with till/clay revegetated layer.
202.2 | Place Covers on Original and Secondary Impoundments and Revegetate | RCTA | To prevent direct contact by wildlife and birds with the tailings and to minimize contaminated runoff. | Detailed design of capture and conveyance measures; requirements for accessibility; cover stability; and long-term vegetation stability; differential and total settlement. | Surface hydrology (swales, ditching, and energy dissipation features); GW/SW interaction. | Need to assess mesotopographic and microtopographic features for tailings cover, and assess available cover material volumes and appropriate vegetation plan. | N | Work stopped on preparation of Project Proposal | None | Need to assess mesotopographic and microtopographic features for tailings cover, and assess available cover material volumes and appropriate vegetation plan.
|  |  |  | Current revegetation design includes use of agronomic grass species, out of keeping with revegetation of the contiguous Rose Valley area and may be an issue for further revegetation and development of an ET cover. | Microtopography and mesotopography determination, growth medium characterization in tailings cover material, vegetation type and application method. | Need to assess optimal cover material types in different areas of tailings cover to facilitate drainage of porewater and separation of clean SW from seepage areas. |  |  |  | Need to assess optimal cover material types in different areas of tailings cover to facilitate drainage of porewater and separation of clean SW from seepage areas.
[5 empty] | Integrated assessment of geotechnical and vegetation cover (agronomic or native) issues for the tailings pond is needed to inform cover design. | Lysimeter installation required in dry consolidated and wet unconsolidated (but due to be drained) tailings materials. |  |  |  | Lysimeter installation required in dry consolidated and wet unconsolidated (but due to be drained) tailings materials.
[6 empty] | Cover and revegetation trial required for the tailings surface. |  |  |  | Cover and revegetation trial required for the tailings surface.
[6 empty] | Revegetation plan and evapotranspirative aspect of the cover design. |  |  |  | Revegetation plan and evapotranspirative aspect of the cover design.
[6 empty] | Energy dissipation structure and implications for revegetation planning. |  |  |  | Energy dissipation structure and implications for revegetation planning.
[6 empty] | Microtopography and landforming. |  |  |  | Microtopography and landforming.
203 - Rose Creek Diversion
203.1 | Upgrade Rose Creek Diversion Upstream from Fuse Plug | RCTA | The Rose Creek Diversion upstream from the fuse plug and downstream from the convergence of the North and South Forks of Rose Creek currently has capacity for the 674 m3/sec PMF based on the cross-sectional area between the Secondary Dam and the hillside. The upgrade is required to stabilize the existing embankments. Perform modifications to pass the PMF through upstream portion of RCDC, including widening and/or deepening of the channel. Provide erosion protection of channel sideslopes and channel bottom. Design to preliminary design level of detail. | Stability of the channel banks need to be addressed. Design of new approximately 400m overflow weir in the location of the existing fuse plug/overflow weir needs to be are discussed in separate activity below and must be considered for design of the RCD upstream of the overflow weir. Rose Creek Diversion Channel needs to increase capacity; stability of the channel banks needs to be addressed. Existing channel carries salmon and is considered a navigable water. Assess changing elevation of channel with respect to tailings and effects on seepage and contamination. Icing of channel resulting in reduction of flow capacity during high flow events. Assess icing related risks. Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. Some site specific hydraulic modelling required to provide water surface profiles. Permafrost impacts on design considerations. Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. Geotechnical, water quality, channel stability, seepage, hydrology, hydraulics modelling refinements, design storm flows, icing, soil cover, and re-vegetation options. Existing channel carries salmon and is considered a navigable water. Assess changing elevation of channel with respect to tailings and effects on seepage and contamination. South slope stability: Rock cut slope stability Assess permafrost issues and potential stability issues Assess potential for channel blockages due to the follow: (1) debris flows, or south slope slides, (2) icing problems, and (3) minor slope failures (during smaller floods) and vegetation. | Additional flow monitoring data collection at stations in place. | Y | Instrumented two stream stages (X10, RCSG-4) with continuous monitoring transducers Completed 2 channel cross section surveys | CH2M HILL Canada Limited (CH2M). March 2015dd. Summary of 2014 Field Investigation – Site-wide Surface Water Monitoring FSP Name: SW-005 – Site-wide Surface Water Monitoring. Technical memorandum. Prepared for Government of Yukon. March 31. CH2M HILL Canada Limited (CH2M). March 2015y. Summary of 2014 Field Investigation – Upgrade Rose Creek Diversion FSP Name: 201.3 – Upgrade Rose Creek Diversion. Technical memorandum. Prepared for Government of Yukon. March 13. | Continue to monitor SW stations
[6 empty] | Rock mass strengths and soil strengths to assess cut slope stability of south slope. | N | Cross section data available; USC test resutlts | CH2M HILL Canada Limited (CH2M). March 2015bb. Summary of 2014 Field Investigation – Erosion Dissipation Structure FSP Name: 203.2 – Erosion Dissipation Structure. Technical memorandum. Prepared for Government of Yukon. March 13. | Geomorphic Assessment Required
[6 empty] | Debris flow potential. | N
[6 empty] | Potential for icing. | Y |  | CH2M HILL Canada Limited (CH2M HILL). November 2012e. Alternatives Evaluation and Risk Analysis for the Rose Creek Tailings Area, Faro Mine. Prepared for Yukon Government. November.
[6 empty] | Quarry sources for large angular riprap. | Y | See borrow investigation sections (400 code activities) | CH2M HILL Canada Limited (CH2M). March 2015hh. Borrow Baseline Design Criteria Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March.
[6 empty] | Infiltration rates for any tributary covers. | Y | Regional surface water modelling and Site-wide GW modelling have provided sufficient information for Concept Design | CH2M Canada Limited (CH2M). March 2016b. Preliminary Final North Fork Rose Creek Design Basis Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March.
[6 empty] | Cover material in catchment area. | Y | Regional surface water modelling and Site-wide GW modelling have provided sufficient information for Concept Design
203.2 | Construct Erosion Dissipation Structure | RCTA | Construct an erosion dissipation layer on tailings cover downstream from a new overflow weir. Flood water will flow from the erosion dissipation structure into a new side channel that will run parallel and immediately next to the Rose Creek Diversion. | Potential backwater conditions require hydraulic modelling to evaluate whether the flood can pass the lower channel without overtopping the dike or intermediate dam. | Review of current PMP and PMF estimates. Erosion potential, water quality, stability, hydrology, hydraulics, and construction materials (riprap sources). Assessment of the design of the energy dissipation structures and settlement of underlying material. | Hydrologic and hydraulic model to provide influent SW flow data including velocities, erosive forces, and elevations. | N | Completed geological reconnaissance | CH2M HILL Canada Limited (CH2M). March 2015bb. Summary of 2014 Field Investigation – Erosion Dissipation Structure FSP Name: 203.2 – Erosion Dissipation Structure. Technical memorandum. Prepared for Government of Yukon. March 13. | Hydrologic and hydraulic model to provide influent SW flow data including velocities, erosive forces, and elevations.
[6 empty] | Foundation strength: natural versus tailings area. Define extent of waste materials (assume it will be removed). | N |  |  | Foundation strength: natural versus tailings area. Define extent of waste materials (assume it will be removed).
[6 empty] | Detailed topographic survey data, potential bed and bank material characterizations. | Y | Sufficient topographic data available for Concept Design; bed and bank material characterization required | CH2M HILL Canada Limited (CH2M HILL). November 2012e. Alternatives Evaluation and Risk Analysis for the Rose Creek Tailings Area, Faro Mine. Prepared for Yukon Government. November. | Potential bed and bank material characterizations.
[6 empty] | Flow data, and water profile data (surface elevations). | N | See 203.1 |  | Flow data, and water profile data (surface elevations).
[6 empty] | Borrow sources for riprap. | Y | See borrow investigation sections (400 code activities) | CH2M HILL Canada Limited (CH2M). March 2015hh. Borrow Baseline Design Criteria Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March.
203.3 | North Fork Rock Drain, Create Channel | RCTA | Create channel through rock drain by either (1) installation of a culvert (trenchless installation or by cut and cover), or by breaching the road embankment to create a notch for the channel. | Determine the concept for rock drain [complete rock drain removal vs. creating a channel (notch) through the rock drain vs. installing a large culvert (trenchless installation or cut and cover)]. | Geotechnical, hydrology, and hydraulics for passing flow through new channel section and erosion potential. | Geotechnical data along new alignment, including excavatability, permeability, erosion potential, etc. | Y | Completed surface geophysical surveys across NFRC upstream and downstream of Rock Drain Drilled 2 borings at the downstream toe of the Rock Drain Advanced 1 boring through the Rock Drain (CH15-107-MW035) | CH2M HILL Canada Limited (CH2M HILL). March 2014m. 2013 Down Valley Interim Hydraulic Upgrades Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28. CH2M HILL Canada Limited (CH2M). March 2016j. North Fork Rose Creek Geotechnical Report. Draft. Prepared for the Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March 31.
|  |  | To restore the North Fork of Rose Creek and protect from potential sources of contamination. | Large undertaking will remove primary access route from Faro and Vangorda/Grum sites. Key issues are slope stability, maintenance of access, geochemical conditions, sedimentation, and constructability. Effects on wildlife, including resident grayling must be integrated into design. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. | Geochemical properties of Haul Road embankment (rock drain) for use as borrow source at the tailings dam. | Y
|  |  | Restore the North Fork of Rose Creek and protect it from potential sources of contamination. | The extent of effects on fish and fish habitat are unknown. | Fisheries and fish habitat reviews are required to determine the quality and quantity of fish habitat that would be incorporated into design. | Rock drain hydraulic characteristics. | Y | Performed tracer test through the Rock Drain Collected weekly water level elevation surveys at NF1 and NF2
|  |  | Design to preliminary design level of detail. | Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. | Permafrost impacts on design considerations.
|  |  | (Coordinate with Activity Code 107.1) |  | Re-vegetation requirements.
Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. Rock drain may have some flood attenuation capacity that can be incorporated in hydrological evaluations.
203.4 | Construct New Overflow Weir | RCTA | Replace existing fuse plug/overflow section with a new overflow weir. Weir will be hardened to resist erosion. | Design criteria and functionality of the overflow weir. | Hydrology, hydraulics, erosion potential, and functional parameters associated with the overflow weir. Design of the overflow weir embankment including seepage and slope stability, and erosion protection. | Hydrologic and hydraulic model to provide influent SW flow data and elevations and erosion/load information for the design of the fuse plug. | N |  |  | Hydrologic and hydraulic model to provide influent SW flow data and elevations and erosion/load information for the design of the fuse plug.
|  |  |  | Length and configuration of overflow weir required. | Hydrology, hydraulics, and erosion potential. | Detailed cross section survey data. | Y | Completed 2 channel cross section surveys | CH2M Canada Limited (CH2M). March 2015n. Summary of 2014 Field Investigation – Upgrade Rose Creek Diversion FSP Name: 201.3 – Upgrade Rose Creek Diversion. Technical memorandum. Prepared for Government of Yukon. March 13.
|  |  |  | Embankment and foundation conditions for overflow weir. | Evaluation of foundation conditions for overflow weir. | Soils data (geotechnical), ice data, flow data, and water profile data (surface elevations). | Y | Advanced 2 borings into bedrock | CH2M HILL Canada Limited (CH2M). March 2015cc. Summary of 2014 Field Investigation – Construct New Overflow Weir FSP Name: 203.4 – Construct New Overflow Weir. Technical memorandum. Prepared for Government of Yukon. March 13.
[6 empty] | Quarry sources for fuse plug material. | Y | See borrow investigations (400 area activities)
203.5 | Upgrade Rose Creek Diversion Downstream from Fuse Plug | RCTA | Provide adequate freeboard to enable the RCDC to pass the flow of Rose Creek on a year-round basis for all flows up to the 500-year flood event. Provide adequate freeboard to enable the RCDC to pass the flow of Rose Creek on a year-round basis for all flows up to the 500-year flood event. | Significant leakage from the channel in its current configuration – 30% at low flow. | Geotechnical, hydrology, hydraulics, and erosion potential. Repairs and improvements to the channel and the dike, riprap modifications, steep channel section, portions of the dike may be raised and/or buttressed to mitigate settlement or loss of freeboard. Rose Creek Diversion dike stability: Seepage and slope stability Internal filter and drain system adequacy Liquefaction potential and mitigation Deformation analyses (static and seismic) Borrow material considerations Slope protection Geotechnical instrumentation | Hydrologic and hydraulic model to provide influent SW flow data and elevations. | N |  |  | Hydrologic and hydraulic model to provide influent SW flow data and elevations.
|  |  |  | The relationship defining flows related to the RCDC and the ID spillway. |  | Detailed cross section survey data, bed and bank material characterizations. Flow data, and water profile data (surface elevations). | Y | Instrumented two stream stages (X10, RCSG-4) with continuous monitoring transducers Completed 2 channel cross section surveys Completed geological reconnaissance of RCD | CH2M HILL Canada Limited (CH2M). March 2015dd. Summary of 2014 Field Investigation – Site-wide Surface Water Monitoring FSP Name: SW-005 – Site-wide Surface Water Monitoring. Technical memorandum. Prepared for Government of Yukon. March 31. CH2M Canada Limited (CH2M). 2015q. Summary of 2014 Field Investigation – Erosion Dissipation Structure FSP Name: 203.2 – Erosion Dissipation Structure. Technical memorandum. Prepared for Government of Yukon. March 13.
|  |  |  | The settlement of the RCDC dike upstream of the Intermediate Tailings Dam. |  | Relationship determination between the RCDC flows, water surface elevations, and the raising/flow requirements in the Intermediate Tailings Dam spillway. | Y | Drilled installed and developed six monitoring well clusters along the RCDC dike crest Completed aquifer testing at monitoring well clusters Deployed and monitored water level transducers at monitoring well clusters | CH2M HILL Canada Limited (CH2M). February 2014q. 2013 Cross Valley Dam Seepage Interception System Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 7. CH2M HILL Canada Limited (CH2M). March 2014m. 2013 Down Valley Interim Hydraulic Upgrades Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28.
[6 empty] | Seepage losses from RCDC. | Y
203.6 | Construct a Fish Bypass (ladder) | RCTA | Replacement of existing drop structures in the downstream portion of the RCDC with a larger fish bypass system. | Fish surveys indicate fish bypass ladder not required |  |  | Y | Fisheries report indicates that ladder is not requried | Environmental Dynamics Inc. (EDI). March 2015a. Arctic Grayling Telemetry & Fish Habitat Investigations, Faro Mine, 2012-2014. (Final). Prepared for CH2M HILL Canada Limited (CH2M HILL). March 25.
203.7 | Revegetate Riparian and High Bank Areas | RCTA | Erosion control and habitat (fish and wildlife) require vegetated surfaces to work concurrently with engineered diversion structures. |  | Locate appropriate soils for growth medium. Complete revegetation design for riparian areas and associated wetlands. | Characterize source and availability of soil cover materials. | Y | See borrow investigations (400 area activities) | None
[5 empty] | Design soil and vegetation covers based on engineering design for creek, to enhance geotechnical design. | Characterize vegetation community for riparian revegetation. | Y
204 – Groundwater Collection
204.1 | Construct Intermediate Dam Cut-off Wall | CVD | Install grout cut-off wall to bedrock in the area of the Intermediate Tailings and Cross Valley dams to direct water either to a central sump or directly into a pipeline; water will be pumped to Faro Pit or directly to the WTP. | Foundation information is not available for the area between the Intermediate Tailings and Cross Valley dams. Data show subsurface at the cross valley and downstream location consist of loose alluvium. Cut-off wall would be located downstream from Cross Valley Dam if Cross Valley Dam is retained. | Assessment of cut-off wall design required. Optimization and detailed design will need to be done during the detailed engineering design phase. Before completion of the cut-off wall and trench, a monitoring system will be installed both upgradient and downgradient from the collector system. | Potential interaction with SW. | Y | Design Concept Changed to DS of CVD | See CDRM Section 9 | Requirements depend on selection of CVD SIS cut-off location
[6 empty] | Bedrock contact delineation. | Y | Design Concept Changed to DS of CVD
204.2 | Construct Intermediate Dam Interception Trench (changed to CVD SIS) | CVD | Direct water either to a central sump or directly into a pipeline; water will be pumped to the Faro Pit or directly to the WTP during the treatment period of the year (early spring to early winter). | Configuration of bedrock surface. Distribution of aquifer properties. Response of aquifer system to GW pumping. Magnitude of site water budget components. Geochemical conditions within the aquifer and potential for well fouling. Number of wells required for effective interception. Need for permeable trench and cut-off walls. Effectiveness of collector trench and need for additional GW wells extending to bedrock. | Develop three-dimensional numerical GW flow model. Investigate various alternative configurations of GW interception design to optimize efficiency and minimize cost. Use GoldSim model or other model to provide boundary conditions for the GW flow model. Estimate GW flow and contaminant mass loading from extraction system (average and peak). This approach is also required if SIS is constructed downstream from Cross Valley Dam. | Potential interaction with SW. | Y | Design Concept Changed to DS of CVD | CH2M HILL Canada Limited (CH2M HILL). March 2013m. Cross Valley Dam Interception System Investigation Data Report Faro Mine Remediation Project. Technical memorandum. Draft. Prepared for Government of Yukon. March 28. CH2M HILL Canada Limited (CH2M). February 2014q. 2013 Cross Valley Dam Seepage Interception System Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. February 7. CH2M HILL Canada Limited (CH2M). January 2015b. Cross Valley Dam Seepage Interception System Test Pit Data Summary, Faro Mine Remediation Project. Technical memorandum. Draft. Prepared for Government of Yukon. January 30. | Remaining gaps depends on final location of CVD SIS; if not positioned as designed, then needs to be re-evaluated
[6 empty] | Extent of hydraulic connection between the alluvial aquifer and Rose Creek downstream from the Cross Valley Dam. | Y
[6 empty] | Bedrock topography in the vicinity of the GW interception system downstream from the Cross Valley Dam. | Y | Design Concept Changed to DS of CVD | CH2M HILL Canada Limited (CH2M HILL). March 2014i. Task Authorization 015 Cross Valley Dam Seepage Interception System Phase 2 – Basis of Design Report, Faro Mine Remediation Project. Draft. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28. (60% design)
[6 empty] | Aquifer properties of both the alluvial and weathered bedrock aquifers along the interception system alignment, including areas on the northeast and southwest extents of the valley fill aquifer. | Y
[6 empty] | Delineation of the alluvial aquifer thickness, bedrock topography, and aquifer properties downgradient from the planned GW interception system. | Y
205 - Miscellaneous Closure Activities
205.1 | Construct New Polishing Pond near the New Faro Area WTP | Mill / ETA |  |  | None. Not required |  | Y | Design of Replacement WTP does not rely on Polishing pond | CH2M HILL Canada Limited (CH2M HILL). January 2013e. WTP Design Definition Report, Faro Mine Remediation Project. Final. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. January 21
Vangorda/Grum Area (Activity Code 300)
301 - Vangorda Pit
301.1 | Pit Wall Stability (new activity) |  | Evaluate pit wall stability including stability of slopes above the access road ramp where pipeline is located. This is a new activity. | Long term stability of pit walls. Consequences of pit wall failures (slide in pit may cause wave that could endanger pumping infrastructure and operating personnel) | Field inspection and evaluation to determine requirements/needs for (1) analytical stability evaluation, (2) instrumentation and monitoring, and (3) slope management including possible stabilization measures. Slope stability analysis. | Requirements/needs for stability evaluation, subsurface information gathering and instrumentation and monitoring. | Y | Completed geological reconnaissance VGA removed from project proposal scope | CH2M HILL Canada Limited (CH2M). March 2014q. Faro Mine Complex 2013 Pit Wall Stability Inspection, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 26.
301.2 | Construct Safety Berms (Vangorda Pit) |  | Construct the safety berms around Vangorda Pit. Construct an access road along the alignment of the berm. | Construction and design optimization will be completed during the detailed engineering process. | Surface hydrology (drainage ditches) and sediment control (retention/settling ponds). |  | Y | VGA removed from project proposal scope | None
301.3 | Reslope and Cover Vangorda Pit Waste Rock Piles |  | Regrade smaller waste rock dumps in the southeastern portion of Vangorda Pit. Cover with till – ET cover. Revegetate areas within days of sloping. Construct rock drains/ditches to prevent seeps from daylighting and ponding on revegetated surfaces. | Pit walls are retrogressing in some areas; slope instability issues. Potential of rockfalls. | Equipment access and foundation conditions. | Cover material volumes. | Y | VGA removed from project proposal scope | None
|  |  |  | Water level fluctuation in pit (risk of flooding revegetated areas and killing vegetation). | Water level fluctuations, pit wall stability. | Cover microtopography and revegetation plan.
|  |  |  | Geotechnical and geochemical variability of deposit. | Appropriate cover material volumes and revegetation planning. | Geochemical and geotechnical characterization of waste piles within the open pit.
|  |  |  | Available subsurface information. |  | Slope stability study and analysis of pit walls.
|  |  |  | Location and number of seeps that could daylight on revegetated surface. |  | Evaluate requirements for slope stability monitoring (install inclinometers actively survey pit walls during construction, or bore holes if needed).
302 - Vangorda Dump
302.1 | Reslope Vangorda Waste Dump (plateau area) |  | Decrease infiltration through the dump, prevent dust generation and migration, and prevent direct uptake by wildlife. Control SW runoff. | Geotechnical properties and geochemical variability of waste. Runoff volumes, efficient and reliable control structures. | Optimize resloping plan. Develop surface water management plan during and after construction. | Geotechnical and geochemical characteristics of waste rock and soils. | Y | VGA removed from project proposal scope | None
302.2 | Reslope Vangorda Waste Dump (perimeter slopes) |  | Construct geotechnically stable landforms that are consistent with long-term revegetation plans. | Conveyance of surface water runoff down the dump slopes without eroding cover. Failure modes and effects analysis of water conveyance channels (that is, ice jam). | Develop final landform design under the following considerations: Optimized resloping Toe of slope is constrained by creeks in several areas; limited opportunities for downgradient sediment management. Protection of the stream channel immediately to the south of the toe of the Vangorda WR Dump. Develop surface water management plan during and after construction. Develop sediment control plan. Assess foundation conditions to allow for sediment collection ditch. Optimize seepage interception along toe of slope (currently appears to be part way up the slope). | Stability of 2.7:1 slope for erosion revegetation (slope facing creek). | Y | Vangorda Grum mine area removed from project proposal scope | None
Geotechnical and geochemical characteristics of waste rock that will be exposed as a result of regarding/resloping.
Reactivity of regraded waste rock for sediment management and long term revegetation.
302.3 | Place Low-infiltration Cover on Vangorda Waste Rock and Revegetate |  | Place low-infiltration cover on Vangorda Waste Rock dump and revegetate. | Allowable infiltration through cover, optimization of cover versus seepage interception and treatment. | Cut and fill optimization. | Final topography of waste dump. | Y | Vangorda Grum mine area removed from project proposal scope | None
|  |  |  | Proposed reclamation surface is rough and loose; however, field investigation concluded that microtopography is bad for plateau areas because it promotes ponding and infiltration. | Infiltration modelling/cover optimization. | Sediment characteristics (geochemical and geotechnical) of material to be exposed during cut/fill (especially erodible fines).
[5 empty] | Need to review RLU planning basis with Waste Pile and Tailings Discipline Team. | Cover material needs to be identified for source and quality.
Existing site water balance versus water balance after final grading needs to be evaluated to determine surface and GW impacts.
Evaluate till stockpile as a potential borrow source.
Sediment control, especially on freshly covered slopes.
302.4 | Place Very Low Infiltration Cover Over Baritic Fines |  | Prior to regrading waste rock, cover baritic fines stockpiled on the northeastern side of the dump with a very-low-infiltration cover. Slope waste rock upslope of the fines and cover with a low-infiltration cover. Alternative – Relocate baritic fines to sulphide cell as bedding layer for very low infiltration line. Only feasible if baritic fines have not migrated/leached excessively into the underlying waste rock. | Clear delineation of limits of baritic fines/cover suitability and short-term and long-term performance. | Infiltration modelling/cover optimization. | Need geotechnical information for baritic fines to evaluate capping design and possible relocation. | Y | Vangorda Grum mine area removed from project proposal scope | None
|  |  |  | If alternative design: Chemical compatibility of baritic fines with material in sulphide cell. | Sediment control and management of contaminated water (primarily surface contact water). | Evaluation of possible contamination of waste rock below baritic fines due to leaching of baritic fines.
Accurate delineation for baritic fines (conflicting areas and volumes).
Sediment control plans during construction (if moved: relocate toward centre of Sulphide Cell rather than toward slope of waste rock pile).
302.5 | Place Very Low Infiltration Cover over Main Dump Sulphide Cell |  | To decrease infiltration through the dump and to prevent dust migration and direct uptake by wildlife. Alternative 1 – Consider consolidating baritic fines on sulphide cell as finer (cushion) layer at liner contact. Alternative 2 – Design 2:1 slopes for impervious liner and develop 3:1 or flatter slopes outside the liner to facilitate revegetation. | Allowable infiltration through cover; optimization of cover versus seepage interception and treatment. If Alternative 1: Chemical compatibility of baritic fines with material in sulphide cell | Cut and fill optimization and infiltration modelling/cover optimization. Lessons learned from capping Grum Sulphide Cell. Need to monitor processes ongoing in that cover and requirement for liner. Merits of very low infiltration cover need to be assessed. Additional monitoring (for example, lysimeters and monitoring wells). Design evaluations of Alternatives 1 and 2. | Cover material volumes need to be assessed for this area. | Y | Vangorda Grum mine area removed from project proposal scope | None
Cover microtopography and revegetation plan needs to be assessed.
[6 empty] | Gradation of waste rock (relates to necessity for cushion layer below cap). |  | Installed CH12-014-MW013 Vangorda Grum mine area removed from project proposal scope
303 - Vangorda Creek Diversion
303.1 | Construct New Vangorda Diversion |  | Potential revegetation of the diversion and adjacent areas needs to be assessed. To permanently realign Vangorda Creek around Vangorda Pit to minimize leakage into pit and provide a safe setback for the diversion away from the pit slope. Vangorda diversion is a component of the MTP and detailed design will be completed. | The existing final design for the permanent realignment of the Vangorda Creek Diversion was performed by others; energy dissipation, erosion prevention measures and intake structure were incorporated into the final design. Potential revegetation of the diversion and adjacent areas needs to be assessed. Energy dissipation design elements especially along steep sections. Erosion protection requirements. Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. Design flows have been selected. The exact alignment and hydraulic design are still uncertain. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. Some site specific hydraulic modelling required to provide water surface profiles. Physical hydrologic/hydraulic modelling is required for final design. Alignment, energy dissipation, routing, gradient, materials, cost, geotechnical conditions, hydrology, hydraulics, erosion potential, and potential revegetation to manage erosion. Impacts on downstream Dixon Creek will need to be considered in the selected design. Re-vegetation to manage erosion needs to be included in design basis to assess cover materials and vegetation species required. Permafrost impacts on design considerations. Diversion design to final level including channel and floodplain geometry, stability and catchment area. | Geotechnical data and soils data collection along final route only in the case the route alignment will change from the current SRK alignment. | N | Drill 3 borings along proposed VCD alignment (SRK 2010), complete as standpipe piezometers Complete surface geophysical survey transects at SRK proposed VCD alignment Topographic Survey of SRK's proposed VCD alignment Fluvian geomorphic assessment of Vangorda creek Inspect Meteorological stations (CH2M March 2014d) Reconnaissance of SRK's proposed VCD alignment (CH2M March 2014d) Vangorda Grum mine area removed from project proposal scope | CH2M HILL Canada Limited (CH2M). March 2014d. 2013 Vangorda Creek Diversion Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28.
[6 empty] | The final alignment has not been selected. | N | Vangorda Grum mine area removed from project proposal scope
[6 empty] | Revegetation planning for channel stabilization and riparian area erosion control. | N
[6 empty] | Additional flow monitoring data being collected in 2013/14 for Vangorda, data to be coincident with precipitation data collected at existing meteorological stations (the Grum Dump) for additional model calibration and validation. | Y | Instumented and monitored additional stream stages (V2, V8) with continuous monitoring transducers | CH2M HILL Canada Limited (CH2M). March 2014d. 2013 Vangorda Creek Diversion Field Investigation Data and Analysis Report, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 28.
303.2 | Upgrade Runoff Interceptor Ditch to Dixon Creek |  | Divert uncontaminated surface runoff from the northeast side of the Vangorda to the south and into Dixon Creek via the Dixon Creek Diversion. Upgrade channel to pass the 500-year storm. Place filter material and riprap sized for the flows in the channel, to prevent erosion. Design to preliminary design level of detail. | Seepage rates, water quality, interception potential, long-term performance of interception. Design criteria provided in Table 4.3 require definition and linkage to seepage management and water quality. Erosion protection requirements. Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. Some site specific hydraulic modelling required to provide water surface profiles. Geotechnical, hydrology, hydraulics, and erosion potential. Permafrost impacts on design considerations. The GW/SW interaction is particularly important because of the seepage issue. Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. Geotechnical, water quality, channel stability, seepage, hydrology, hydraulics modelling refinements, design storm flows, icing, soil cover, and re-vegetation options. | Flow data, and water profile data (surface elevations). | N | Vangorda Grum mine area removed from project proposal scope | None
[6 empty] | Availability of flow data in Dixon Creek upstream from the confluence of Dixon Creek with Shrimp Creek. | N
[6 empty] | Subsurface conditions: | N
[6 empty] | Permeability | N
[6 empty] | Permafrost occurrence | N
[6 empty] | Erodability of base material | N
304 - Grum Pit
304.1 | Pit Wall Stability |  | Evaluate pit wall stability specifically the alluvium/colluviums slope at east wall of Grum Pit. Perform stability evaluation and install slope movement instrumentation (prisms) | Long term stability of pit walls and management requirements. Consequences of pit wall failures (slow movements of large volume of material may impact available storage in pit and a rapid slide in pit may cause wave that could endanger pumping infrastructure and operating personnel) | Slope stability assessment: Development of analytical slope stability model Calibration with measured slope movements Assessment of margin of safety against slope failure | Rate and magnitude of alluvium/colluvium soil slope movement | Y | Geological reconnaissance and survey monument installation | CH2M HILL Canada Limited (CH2M). March 2014q. Faro Mine Complex 2013 Pit Wall Stability Inspection, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 26.
304.2 | Construct Safety Berms (Grum Pit) |  | Restrict access to human and wildlife for safety purposes. | Acceptable methods for providing safer barricades that will not be snow covered and ineffective. | Safety berms around Grum Pit and polishing ponds in the slot. | Sufficient geotechnical data. |  |  | None
305 - Grum Interceptor Ditch
305.1 | Divert Grum Interceptor Ditch away from Grum Pit |  | Interceptor ditch will be diverted away from Grum Pit. Design to preliminary design level of detail. | Foundation conditions along Access Road next to the proposed ditch alignment and at the earth dam proposed at headworks. Characteristics of overburden at the trapezoidal interceptor channel and cut slots at pit bench crest and at the south end of Grum Pit. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. Some site specific hydraulic modelling required to provide water surface profiles. Geotechnical, hydrology, hydraulics, and erosion potential. Interceptor will be diverted away from Grum Pit. Permafrost impacts on design considerations. Re-vegetation requirements. Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. | Soils data (geotechnical), ice data, flow data, and water profile data (surface elevations). | N | Vangorda Grum mine area removed from project proposal scope | None
305.2 | Construct Algae Filter at Slot Cut in Grum Pit |  | YG discontinued algal treatment in 2012. It will not be resumed. Grum Pit water will be treated in the Faro WTP. | [5 empty] | None
306 - Grum Waste Dump
306.1 | Reslope and Regrade Grum Waste Dump and Pull Back Crest |  | Reduce infiltration in the plateaued upper surface of the dumps. Construct geotechnically stable landforms. Minimize energy of runoff from covers and surrounding areas. Revegetate disturbed areas on all dump areas. | SW, GW, and geochemical modelling are not well integrated. IPR provided recommendations for review. Enhanced modelling is underway to estimate the effectiveness of remediation over time and the application of adaptive management principals. | Update and integrate previous modelling (hydrology, water balance, and geochemical) to optimize ET model and erosion reduction. Develop surface water management plan during and after construction. Consider infiltration galleries to facilitate surface water management Optimize regrading/resloping plan considering final footprint constraints; evaluate option of expanding the toe. Development sediment control plan. Assess borrow materials (till). | Geotechnical and geochemical characteristics of waste rock and soils, including those that will be exposed as a result of regrading/resloping. | N | Installed CH12-014-MW011, CH12-014-MW012 Vangorda Grum mine area removed from project proposal scope | None
[6 empty] | Volume of foundation materials at toe of waste rock dumps suitable for borrow. | N | Vangorda Grum mine area removed from project proposal scope
[6 empty] | Locations of suitable areas for potential infiltration galleries to help control surface runoff and erosion. | N
306.2 | Place Very Low Infiltration Cover on Grum Sulphide Cell |  | Control infiltration to significantly reduce the amount of water entering the surface of the waste (less than 0.5% of the mean annual precipitation). | No lysimeters are installed to monitor infiltration. It is difficult (nearly impossible) to determine the effectiveness of the existing cover without installing new instrumentation. Must conduct detailed lessons learned exercise for the Grum sulphide cover to optimize cover design going forward. | Cell already capped. Need to evaluate the performance of the cap for stability, reducing infiltration, and reducing contaminate discharge. | . | Y | Vangorda Grum mine area removed from project proposal scope | None
|  |  | Bottom third of waste pile remains at high slope angle; SW appears contaminated; and need long term plan for SW disposition. |  | Final waste pile geometry and disposition of SW.
306.3 | Place Vegetative Cover on Grum Waste Dump and Revegetate |  | Control infiltration and maintain vegetation growth. | Optimum cover and vegetative materials. | Evaluate performance of annual rye seeding, root and leaf density, and ability to continue with revegetation of deeper-rooted species/whips and cuttings into surface. | Data on seeding versus barley performance. |  | Vangorda Grum mine area removed from project proposal scope | None
|  |  | Cover the Main Dump with a rudimentary cover that has the minimum thickness of soil needed to allow plant growth. | Cover layer has been packed smooth, which may contribute to runoff and drilling issues, and create issues for planting and successful growth of shrub and tree species planned for further revegetation activities. | Continue evaluation of vegetation performance to provide information for soil cover composition, topography, and vegetation cover on other proposed, very low infiltration covers. | Review of planned further revegetation efforts. Continued review of vegetation performance over next 5 years. | Y
|  |  |  | Revegetation of drainage-related structures does not appear to be in the plan, but would assist with erosion control. | Evaluate performance of drainage structures without vegetative cover. | Review of revegetation planning to align with planning for other landforms.
|  |  |  | Location and quality of borrow material. |  | Review of soil cover physical and geochemical characteristics.
307 - Grum Overburden Dump
307.1 | Reslope Grum Overburden Dump and Revegetate |  | The Grum Overburden Dump is the primary source of glacial till borrow material; after all borrow material at the dump has been removed, the area will be regraded and revegetated. Potential integration of final excavated area for use as storage for emergency pit water management. | Appropriate configuration for terrestrial wildlife. Sediment control. Need to understand the contribution of surface texturing (ripping versus vertical or horizontal rilling) to sediment movement off-slope and moisture retention in soils. Current revegetation trial appears to have used graded phyllite (ore) rather than glacial till. Need to understand geochemical and textural impact, because this is not the planned material for other cover areas. | Infiltration modelling; VADOSE/W; SLIDE (slope stability), and TEMP/W (freeze-thaw). Review sediment data from Grum OB Dump toe ditches and review literature regarding rill design. Need to assess geochemical and textural impact of using phyllite rather than glacial till as vegetation cover substrate. Develop surface water management plan during and after construction. Optimize regarding/resloping plan. Develop sediment control plan. Evaluate disposition of treatment plant sludge as potential subgrade material for liner or disposal in Grum Pit. | Foundation conditions along dump perimeter are not defined. | Y | Vangorda Grum mine area removed from project proposal scope | None
308 - Grum Ore Transfer Pad
308.1 | Regrade, Cover and Revegetate Ore Transfer Pad |  | Cover pad with very low infiltration cover, seed, and allow to revegetate naturally. Construct a temporary sediment collection ditch to divert runoff from the revegetated ore transfer pad away from a nearby stream until the vegetation has established. Alternative – Consider consolidation or complete removal of the geochemically reactive fines (typically less than 1-m thick) and exposure of underlying phyllite waste rock that could be exploited as a potential borrow source | Infiltration rates through cover. Appropriate configuration for terrestrial wildlife. Sediment control. Proposed reclamation surface is rough and loose; however, the field investigation concluded that microtopography is bad for plateau areas because it promotes ponding and infiltration. If the thin layer of sulphidic fines is removed and the underlying phyllite is exploited, it will be necessary to develop appropriate closure scenario. Could potentially include development of constructed wetland. Impact on surrounding wetland areas needs to be assessed. | Infiltration modelling (cover optimization); surface hydrology, energy dissipation swales; and TEMP/W. Need to review RLU planning basis with Waste Pile and Tailings Discipline Team, and plan a revegetation trial on this kind of slope/material. Evaluate the potential for consolidation or complete removal due to limited thickness of geochemically reactive fines. Evaluate phyllite as potential borrow source for low visibility areas or as vegetation growth medium. | Revegetation trial required ore transfer pad covers and slopes, especially where hydrocarbon-contaminated or sludge materials may be applied. |  | Vangorda Grum mine area removed from project proposal scope | None
Cover material needs to be identified for source and quality.
[6 empty] | Need to assess impact of ore transfer pad on adjacent pond and wetland complex. | Y
Determine rationale for capping without consolidation.
Geotechnical characterization of ore transfer waste material (gradations, angularity, and hardness).
Thickness of geochemically reactive fines.
309 - Vangorda/Grum Groundwater
309.1 | Install Grum GW Collection and Cut-off Walls |  | Capture contaminated GW seeping from the Grum Waste Rock Dump. Optimization and detailed design will be performed during the detailed engineering design phase. If monitoring indicates insufficient capture of contaminated GW, a cut-off wall and permeable collector trench will be constructed along the Access Road. Pumps would be installed in the collector trench to direct water to the Central Pond. | Pre-mining land surface topography and bedrock topography, subsurface material properties within and beneath Grum WRD, and areas where future seepage from the WRD may occur. | Condition of the Access Road below Grum Dump (construction vehicle access). Pads for pumping wells and clear pipeline alignments. Evaluate central pond foundation in vicinity of Grum Creek crossing. Pump wells and pipelines. House primary discharge pump in a heated enclosure on the side of the central holding pond. Install GW monitoring wells between and downgradient from the pumping wells. Evaluate GW flow directions and GW quality at existing and planned monitoring well and piezometer locations. Develop three-dimensional numerical GW model of the Vangorda/Grum Area to simulate GW levels and GW flow directions. This model will also be used to forecast performance of the Grum WRD SIS under different assumed configurations to optimize interception efficiency and minimize cost. This model will aid in forecasting metal loading to the SIS. | Bedrock surface topography, pre-mining land surface topography, spatial distribution of hydrostratigraphic units, and saturated thickness within and beneath Grum WRD and along the associated proposed SIS corridor. |  | Vangorda Grum mine area removed from project proposal scope | None
Reliable XYZ locations of existing monitoring and operational infrastructure in the Grum Area.
[6 empty] | Seasonal gaining versus losing reaches along Vangorda Creek between Vangorda and Grum WRDs. | Y
GW monitoring network in Grum Area to provide sufficient early warning triggers in accordance with the AMP. GW flow directions near proposed SIS corridor and near the Grum WRD toe.
Subsurface hydraulic properties along and upgradient from the proposed SIS corridor.
309.2 | Install VWRD Seepage Collection System |  | Minimize contaminant loading with covers to decrease infiltration and subsequent seepage. A conceptual design for a GW collection system will be developed. |  | Seepage collection system in place at the Vangorda Waste Rock Dump consists of French drains to funnel the seepage into a collection ditch that discharges to Little Creek Pond. More active collection of GW seepage from the VWRD is currently not required but may become necessary in the future if contaminant concentrations increase significantly. | Addressed under Activity Code 309.6. |  |  | None
309.3 | Install Vangorda GW Collection System |  | Capture contaminated GW seeping from the Vangorda WRD. | Pre-mining land surface topography and bedrock topography, subsurface material properties within and beneath Vangorda WRD, and areas where future seepage from the WRD may occur | Evaluate GW flow directions and GW quality at existing and planned monitoring well and piezometer locations. | Bedrock surface topography, pre-mining land surface topography, spatial distribution of hydrostratigraphic units, and saturated thickness within and beneath Vangorda WRD. |  | Vangorda Grum mine area removed from project proposal scope | None
[5 empty] | Develop three-dimensional numerical GW model of the Vangorda/Grum Area to simulate GW levels and GW flow directions. This model will also be used to forecast performance of the Vangorda WRD SIS under different assumed configurations to optimize interception efficiency and minimize cost. This model will aid in forecasting metal loading to the SIS. | Reliable XYZ locations of existing monitoring and operational infrastructure in the Vangorda Area. | Y
Robust GW monitoring network in Vangorda Area to provide sufficient early warning triggers in accordance with the AMP. GW flow directions near proposed SIS corridor and near the Vangorda WRD toe.
Subsurface hydraulic properties along and upgradient from the proposed SIS corridor.
310 - Vangorda/Grum Miscellaneous
310.1 | Remove Culverts, Decommission, and Revegetate |  | Breach all culverts and crossings, and revegetate the disturbed areas. Not yet determined whether haul road should be used as source of cover material; quality needs to be tested. | The flattening and revegetation of the haul road sideslope is currently under review. | Remove culverts (includes 10 major culverts in the North Fork River drainage). | Flow requirements for redesigned conveyance components. |  | Vangorda Grum mine area removed from project proposal scope | None
|  |  |  | Will need to develop a sediment control and SW management plan for the work. | Decommission embankments. |  | Y
|  |  |  | Possible source material for covers may be incorporated in haul road, but need to core road to check. | Remove/flatten safety berms.
|  |  |  | Removal of haul road across entire Rose Creek valley needs to be assessed. | Reclaim by hydroseeding each dump site, breached area, and area of disturbance to eliminate the potential need for hauling and placing topsoil.
310.2 | Demolish Buildings (treatment plant and the steel culvert over Grum Portal) |  | Remove existing buildings and infrastructure that will not be required after closure to mitigate potential long-term safety hazards. Extent of contamination of surfaces through buildings is unknown. Demolish buildings along with their foundations. Only the contaminated foundation components will be removed for proper disposal while the clean foundations will be covered in place (some may be buried within the toe of the Resloped waste rock dump) and revegetated. Prior to any demolition works, a full inspection will be conducted on all site buildings to identify all hazardous waste, salvageable materials, and structural safety concerns. A solid waste management plan will be developed and a list of permits prepared. | Sampling for ACM and other designated substances may not be substantive enough to be useful for decommissioning purposes. Areas around the buildings that are not tested may need to be treated as designated or ACM substances. Site plans, surveys, Material Safety Data Sheets, and other information involving plant construction and makeup are not currently available. Options to revegetate and reclaim the site as part of the natural landscape after decommissioning need to be evaluated. Remove existing buildings that will not be needed after closure and that would be a long-term safety hazard. Revegetate site and reclaim as part of a landscape plan. | Obtain, review, and catalogue site plans and other construction documentation for competitive procurement. Depending on EBA’s scope, obtain a demolition execution approach through a structural engineer. Site visit to identify items that may have been missed. Follow up sampling may be required. Address safety concerns with onsite buildings to clear areas for safe access to complete other assessments that may be required. Perform site utility surveys. Use GPR if necessary for decommissioning and to understand H&S risk during work. Retain a demolition contractor to assist in scrap assessment. Determine and obtain permits required to perform demolition. | Sufficient sampling to mitigate costs for abatement of materials assumed to contain designated substances due to lack of information to the contrary. |  | Completed inventory of water conveyance infrastructure Vangorda Grum mine area removed from project proposal scope | CH2M HILL Canada Limited (CH2M). February 2016b. Water Conveyance System Mapping and Inventory, Faro Mine Remediation Project. Technical memorandum. Prepared for Government of Yukon. February 1.
Process material quantification.
Waste disposal recommendations.
[6 empty] | Salvage assessment. | Y
Utility and site surveys.
Assess suitable cover material quality.
Assess potential for ET vegetation cover, or appropriate revegetation prescription.
Specific revegetation prescription required, this area is a candidate for an ET cover.
310.3 | Remove WTP Settling Pond |  | Construction of the new single WTP at the Faro Mine makes the current settling pond unnecessary. Sludge will be dredged to the Grum Pit using the new dredge system with conveyance in the existing pipeline and a new section into the pit opposite the pump barge. | Closure and disposal requirements for material below the pond. Settling ponds have had leakage issues in the past. | After the water treatment settling pond is cleaned of sludge, the berm should be breached. Breach, riprap, and cover the Water Treatment Settling Pond after the new plant is operational. Breach the dams at the Sheep Pad Ponds (built to capture sediment from the Grum Interceptor Ditch before discharging into Vangorda Creek); the pad ponds do not need to be covered. | Subsurface conditions below the settling pond. | Y | Vangorda Grum mine area removed from project proposal scope | None
310.4 | Remove Contaminated Soils (Fuel Lube Station) |  | Remove hazardous materials and contaminated soil at the site that could cause a long-term impact on the surrounding environment. | Volume of material excavation; volume and source of backfill. Concentration threshold criteria for soil removal. | The C&R Plan, Table 6.13, outlines design criteria. | Extent of soil hydrocarbon contamination (lateral and vertical) near the Lube Shack and Tank Farm. |  | Vangorda Grum mine area removed from project proposal scope | None
[6 empty] | GW flow directions. | Y
Extent of associated GW contamination.
310.5 | Construct Bioremediation Cell |  | Treat hydrocarbon contaminated soil. | Location of landfarm is to be determined; likely on a waste rock dump near mill buildings. | The C&R Plan, Table 6.13, outlines design criteria. |  | Y | Vangorda Grum mine area removed from project proposal scope | None
310.6 | Reclaim Roads |  | Prevent long-term erosion and breach crossings to prevent blockage. | Road areas will require specific reclamation plans in accordance with required surface drainage plans and surrounding reclamation prescriptions. | There is currently no specific prescription for road revegetation or information about road material quality to predict vegetation success. | Require assessment of road material quality for use as cover materials or requirements for revegetation. | Y | Vangorda Grum mine area removed from project proposal scope | None
|  |  | Culverts and crossings will be breached and resloped and drainages restored. Scarify road surfaces and revegetate. |  |  | Require assessment for basis of design of road reclamation – revegetation or swale/channel formation as part of surface drainage plan.
310.7 | Little Creek Pond |  | The C&R Plan does not provide for the Little Creek Dam, but notes that it may be used. It is assumed that the dam will be used as part of closure. | The need for this structure is undefined and will be determined based on the need for SW and GW collection and storage. The dam is considered a low-hazard dam; therefore, it has a small spillway (500-year event). C&R Plan states that the future of the LCP is yet to be determined, but it will probably not continue to function as a collection pond for seepage from the Vangorda Waste Rock Dump. The C&R Plan suggests that the LCP might be used as a polishing pond for the WTP | Initial review indicates polishing pond in conjunction with a new WTP not required. If retained, review of geologic mapping and as‑built information. Engineering analyses: Spillway capacity Seepage analysis Slope stability including pseudostatic (seismic) stability | Embankment and foundation properties (strength and permeability). |  | Vangorda Grum mine area removed from project proposal scope | None
[6 empty] | Piezometric conditions in the dam and the foundation. | Y
Erosion protection (riprap) requirements for wave action (assuming that a pond will need to be retained).
400 - Site Wide Activities
401 - Haul Road
401.1 | Remove Culverts, Decommission, and Revegetate |  | Breach all culverts and crossings, and revegetate the disturbed areas. Not yet determined whether the haul road should be used as a source of cover material; quality needs to be tested. The flattening and revegetation of the haul road sideslope is currently under review. Will need to develop a sediment control and SW management plan for the work. | Rockfall issues appear to be a natural hazard in valley areas and are construction hazards in dealing with the Faro Mine waste rock piles and high Haul Road berms. Value of reconstruction of valley areas after Haul Road material removal needs to be assessed. Possible source material for covers may be incorporated in Haul Road, but need to sample road materials to confirm. Removal of Haul Road across entire Rose Creek Valley needs to be assessed. | Remove culverts (includes 10 major culverts in the North Fork River drainage). Decommission embankments. Remove or flatten safety berms. Reclaim by hydroseeding each dump site, breached area, and area of disturbance to eliminate the potential need to haul and place topsoil. Integrated planning required for the NFRC valley area (including riparian and ponded areas), in conjunction with activities to reslope the waste rock pile and remove all or part of the haul road. | Dump or cover materials resulting from decommission of haul road not yet assessed in revegetation and reclamation planning; need to study and report back into waste rock and cover inventory. | Y | Scope of work needs to be re-evaluated | None
401.2 | Alternative analysis for retention of haul road |  | To provide route for Vangorda pipeline to WTP at Faro, Haul Road may be retained. | Need to assess potential interim 10-15 year impact to wildlife and fish during interim works; then perpetual impact as part of closure surface. Approx 800,000 m3 of waste rock from the Haul Road was planned for cover on the Rose Creek Tailings Facility. | Alternatives analysis required for retention of Haul Road impact on material balance, fish and wildlife access. Assess whether portion of haul road can be used as borrow source. | Require wildlife and fisheries alternatives analysis. |  | Scope of work needs to be re-evaluated. Design basis specifies installation of culvert at haul road. | CH2M Canada Limited (CH2M). March 2016b. Preliminary Final North Fork Rose Creek Design Basis Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March.
[6 empty] | Require material balance review. | N |  |  | Scope of work needs to be re-evaluated
Require analysis of rock drain retention options for fish passage in NFRC.
401.3 | Construct Haul Road Access from Vangorda to RCTA |  | Breach all culverts and crossings, and revegetate the disturbed areas. The flattening and revegetation of the haul road sideslope is currently under review. Will need to develop a sediment control and SW management plan for the work. |  | Construct temporary haul roads. Not clear if haul road access alignment has been assessed in the environmental assessment. Need to check if undisturbed areas will be affected by construction; assess and plan for conservation and reclamation of area. | Review of new haul road access area inclusion in environmental assessment, and basis of reclamation design required for affected area. | N | Vangorda Grum mine area removed from project proposal scope | None | Review of new haul road access area inclusion in environmental assessment, and basis of reclamation design required for affected area.
401.4 | Construct Cross-Site Mine Water Pipeline |  | A new HDPE cross-site pipeline will be constructed on the Haul Road to convey Vangorda/Grum-area water to the new Faro WTP. This pipeline will also have a branch to the Faro Pit for temporary storage. It will be operated only during the warm season (e.g. May-Sept) and will be dewatered prior to winter. Cleanout will by pigging. For protection from the elements as well as from traffic damage and vandalism, it is expected to either be buried shallowly or have fill placed over it. | Detailed alignment up from Vangorda and Grum Pits and along the Haul Road. Design Capacity (preliminary design capacity is 2,000 USgpm). | Determine final alignment. Determine final design capacity. | Subsurface conditions along alignment. | N | Conceptual design developed. Vangorda Grum mine area removed from project proposal scope | CH2M HILL Canada Limited (CH2M HILL). January 2013b. Power Point Presentation: Faro WTP Schematic Design Report Draft Submission. January 25. | Scope of work needs to be re-evaluated
[6 empty] | Source of fill if covered rather than buried | N
402 - Water Treatment
402.1 | Construct new Faro Water Treatment Plant and Piping |  | Design and build new WTP and pipelines to treat contaminated wate. (design completed to ~90% level under TAR 13) | C&R Plan includes potential for two new WTPs, Faro Area and Vangorda/Grum Area. YG has decided to construct a single WTP located in the southwest corner area of the Faro Mill Yard. The plant will initially not have filters and will discharge through the CVP. A new pipeline will be constructed on the Haul Road to transport Vangorda/Grum-area water to the new WTP or to the Faro Pit for temporary storage (See Activity Code 301.2). Vangorda/Grum-area water will be collected and stored in the Vangorda and Grum Pits and will be pumped through this pipeline during the warmer months, e.g. May – September. On-site borrow source for backfill and for concrete aggregate is uncertain. | Determine source(s) of on-site borrow for backfill and concrete aggregate. | Availability and suitability of on-site borrow for backfill and concrete aggregate. | Y | See Borrow Investigation Sections (400 series activities) | See site-wide borrow tasks. CH2M HILL Canada Limited (CH2M HILL). March 2014b. Faro Water Treatment Plant Geotechnical Design Report Addendum, 2013 Borrow Source and Quarry Investigation, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 31.
|  |  |  | Effluent discharge limits is critical to WTP filter system design. | Evaluation of concentrations based on a risk assessment and treatment technology-specific achievable basis. | Discharge limits for treated water including sulphate/TDS. | N | Expired water license used as design basis. No new discharge limits developed
|  |  |  | Treatment effectiveness achievable by a new HDS/filtration system (ability to consistently meet discharge limits). | Use 2012 pilot test results to assess potential performance required from the future filtration system. | Performance of new WTP in comparison to potential new discharge requirements |  |  |  | Datagaps remain
|  |  |  | Design and operating parameters for achieving optimum WTP performance. | Evaluation of WTP performance without filters in comparison to potential new discharge requirements. | Filter system design and operating parameters.
|  |  |  | If site discharge limits require very low effluent concentrations, an advanced treatment process may be required in addition to filtration. If sulphate discharge is regulated, NF/RO treatment may be required. | Evaluate discharge limits relative to treatment performance expected for the HDS/filtration process. | Need for sulphide addition, NF/RO, or other advanced water treatment process to meet discharge limits. |  |  |  | Datagaps remain
|  |  |  | Precipitation and scale formation in pipelines is unknown but likely if waters allowed to oxidize or sources waters blended. | Review chemical composition of water to be piped and possible different waters to be combined in pipelines. Geochemical modelling. | Potential for precipitate formation and scaling in water collection and conveyance pipelines. | N | No scope was authorized to evaluate future water chemistries that could be combined in pipelines. |  | Datagaps remain
Design features needed to mitigate problems from precipitation and scaling.
|  |  |  | Sludge disposal capacity in Faro Pit now that it will also store sludge produced from treatment of Vangorda/Grum-area water. | Calculate annual net water balance of water collected and conveyed to new WTP (GoldSim modelling). Calculate estimated annual sludge production and solids volume conveyed to Faro Pit as well as final in-situ storage volume over time. | Quantity requirements and capacities for water and sludge storage in Faro Pit. | N | Water storage volume requirements evaluated using GoldSim modelling. Estimated thickener underflow waste volume. | Discussed in Section 2.5 CH2M HILL Canada Limited (CH2M HILL). March 2014b. Faro Water Treatment Plant Geotechnical Design Report Addendum, 2013 Borrow Source and Quarry Investigation, Faro Mine Remediation Project. Final. Prepared for Government of Yukon and Government of Canada as represented by Aboriginal Affairs and Northern Development Canada. March 31. | Datagaps remain
|  |  |  | The appropriateness and effectiveness of sludge disposal in the pits. | Assessment of sludge dissolution, fate, and effects on water chemistry. | Geochemical stability of sludge deposited in Faro Pit. | N | Faro pit lake profiling and sampling completed annually | CH2M Canada Limited (CH2M). April 2016c. Fiscal Year 2015 Groundwater Flow Model Development Report, Faro Mine Remediation Project. P repared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. April 5. CH2M Canada Limited (CH2M). April 2016d. Summary of 2015 Field Investigation – Site-wide Geochemical Monitoring, FSP Name: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Draft. Prepared for Government of Yukon. April 15. CH2M HILL Canada Limited (CH2M). March 2015b. Summary of 2014 Field Investigation – Site-wide Geochemical Monitoring FSP Name: SW-015 – Site-wide Geochemical Monitoring. Technical memorandum. Prepared for Government of Yukon. March 31. CH2M HILL Canada Limited (CH2M HILL). March 2013r. Data Quality Evaluation Report, 2012 Groundwater, Surface Water and Seep Water, Faro Mine Remediation Project. Final. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March 14. | Geochemical stability of sludge deposited in Faro Pit needs to be evaluated
402.2 | Polishing Pond |  | Construct new Polishing Pond near the new Faro Area WTP. CH2M HILL has determined that a polishing pond is not required following construction of the HDS treatment facilities. | None – not required |  |  |  | No longer planned or required | None
402.3 | Construct Vangorda WTP and Piping |  | A single WTP located in the area of the Faro Mill will be constructed. Piping route evaluated under separate activity. | None – not required
403 - Borrow Area Development
403.1 | Develop and Decommission Faro Borrow Sources | Sitewide | Identify all necessary borrow sources and develop plans to rehabilitate borrow areas. Impact on fish and terrestrial habitats, habitat compensation and contamination in Haul Road granular sources. |  | Some assessments completed on borrow sources. Good quality armour rock is hard to find. Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan. | Delineation of sources d/s of tailings area. Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan. | Y |  | See specific areas below
403.2 | Develop and Decommission Faro Borrow Sources – Granular Soil | Sitewide | Identify all necessary granular borrow sources and develop plans to rehabilitate borrow areas. Expand Rose Creek borrow site. New – Intermediate Dam spillway. Potential – east of North Fork of Rose Creek. Could be developed in connection with relocation of NFRC. | Impact on fish and terrestrial habitat and habitat compensation. Quality and quantity of borrow material is undefined or poorly defined. Limiting EA issues associated with various potential sources. | Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan. Delineation of sources downstream of tailings area. | Amount and quality/composition of material that has been used since the estimates were developed. | Y | Excavated test pits Drilled borings Completed Surface Geophysics | CH2M HILL Canada Limited (CH2M). March 2015hh. Borrow Baseline Design Criteria Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. CH2M HILL Canada Limited (CH2M). March 2016j. North Fork Rose Creek Geotechnical Report. Draft. Prepared for the Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March 31.
[6 empty] | Geochemical/geotech parameters | Y
[6 empty] | Delineation of sources. Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan. | Y
403.3 | Develop and Decommission Faro Borrow Sources – Low Permeability | Sitewide | Identify necessary granular borrow sources and develop plans to rehabilitate borrow areas. Rose Creek Haul Road. Expand tailings borrows. | Potential Areas: East of North Fork of Rose Creek; could be developed in connection with relocation of NFRC Between Faro Waste Rock Dump and original Tailings Impoundment East of Fresh Water Supply Reservoir Impact on fish and terrestrial habitat and habitat compensation Quality and quantity of borrow material is undefined or poorly defined. Limiting EA issues associated with various potential sources. | Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan. Delineation of potential borrow sources d/s of RCTA. | Amount and quality/composition of material that has been used since the estimates were developed. | Y | Excavated test pits Drilled borings Completed Surface Geophysics | CH2M HILL Canada Limited (CH2M). March 2015hh. Borrow Baseline Design Criteria Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. CH2M HILL Canada Limited (CH2M). March 2016j. North Fork Rose Creek Geotechnical Report. Draft. Prepared for the Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March 31.
[6 empty] | Geochemical/geotech parameters. | Y
[6 empty] | Delineation of sources. Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan. | Y
403. 4 | Develop and Decommission Haul Road as a Borrow Source | Sitewide | Haul Road material to be used to cover tailings area, contouring, and regarding. | Quality and quantity of borrow material is undefined or poorly defined. | Investigations to date on the Haul Road have been minimal and inconsistent. |  | Y | Reviewed construction and current conditions Advanced a boring through the haul road near the rock drain | CH2M HILL Canada Limited (CH2M HILL). March 2014e. Cross Valley Dam Seepage Interception System Phase 2, Groundwater Modelling, Faro Mine Remediation Project. Technical memorandum. Draft. Prepared for Government of Yukon. March 28. (Appendix A to Task Authorization 016 Down Valley Interim Hydraulic Upgrades Phase 2 – Basis of Design Report [60% design]) CH2M Canada Limited (CH2M). March 2016b. Preliminary Final North Fork Rose Creek Design Basis Report. Prepared for Government of Yukon and Government of Canada as represented by Indigenous and Northern Affairs Canada. March. | Entire length of Haul Road not evaluated;
403.5 | Develop and Decommission Vangorda-Grum Granular Borrow Areas | Sitewide | Identify necessary borrow sources and develop plans to rehabilitate borrow areas. Impact on fish and terrestrial habitats and habitat compensation. | Impact on fish and terrestrial habitats and contamination in Haul Road granular sources. Quality and quantity of borrow material is undefined or poorly defined. Limiting EA issues associated with various potential sources | Some assessment completed on borrow sources. Environmental assessment not completed for borrow areas – vegetation and rare plant surveys are required. Reclamation planning for borrow sources needs to be included in the revegetation plan. | Delineation of sources around Moose Pond and Grum Creek. Environmental assessment not completed for borrow areas; vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in the revegetation plan. | N | Vangorda Grum mine area removed from project proposal scope | None | Conduct Initial field reconnaissance program: Dig test pits in proven borrows (Grum Creek/Moose Pond) Conduct field mapping and pionjar surveys of undefined sources.
403.6 | Develop and Decommission Grum Overburden Dump Borrow Area (Low Permeability Soils) | ? | Identify volumes, geotech/geochem parameters of Grum OB dump and Grum overburden dump foundation (approximately 8 million m3 + 1 million m3 = 9 million m3). | Grum Sulphide Cell used till from South Till Borrow Area; contractors indicated that Grum overburden pile would require significant effort to sort oversized materials (that is, may be large percentage of boulders in till material). Amount used was 240,227 m3 Impact on fish and terrestrial habitats and contamination in Haul Road granular sources. Quality and quantity of borrow material is undefined or poorly defined. Limiting EA issues associated with various potential sources. | Volume decline. Geotechnical characterizations. Geochemical characterizations. Foundation Investigations. Reclamation planning for borrow sources needs to be included in revegetation plan. Evaluate Till Stockpile at Vangorda Waste Dump. | Geochemical/geotech parameter studies are underway. | Y | Completed geological reconnaissance of North Wall of Grum Pit Excavated 10 test pits at Grum Overburden Dump Drilled 11 sonic borings in the Grum Overburden Dump Excavated 4 test pits in the Grum Overburden Dump Foundation Drilled 1 sonic boring in the Grum Overburden Dump Foundation Drilled 5 pionjar borings in the Grum Overburden Dump Foundation | CH2M HILL Canada Limited (CH2M). March 2015hh. Borrow Baseline Design Criteria Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March.
[6 empty] | Depth of foundation investigation is underway. | Y
403.7 | Develop and Decommission Area Northeast of Grum Pit (Low Permeability Soils) | ? | Identify volumes, geotechnical, and geochemical parameters of low-permeability borrow source; North Wall of Grum Pit. SRK Additional Borrow Studies 2004, Task 11a indicates bedrock ranges from 9 to 18m bgs (based on GPR) with probable overlying till. | Impact on fish and terrestrial habitats and contamination in Haul Road granular sources. | Volume decline. | Geochemical/geotech parameter studies are underway. | Y | See 403.6 | See 403.6
|  |  |  | Quality and quantity of borrow material is undefined or poorly defined. | Geotech characterizations. | Depth of foundation investigation is underway. | Y
|  |  |  | Limiting EA issues associated with various potential sources. | Geochem characterizations.
Foundation Investigations.
Reclamation planning for borrow sources needs to be included in revegetation plan.
403.8 | Develop and Decommission Area Rip Rap Sources (Faro Grum Vangorda Areas) | Sitewide | Identify and develop borrow sources of strong chemically stable rock for use in surface channels and drainage systems. Quarries will need to be excavated from granitic bedrock outcrops. Alternative: Investigate suitability of using cobbles/boulders mechanically separated from till overburden or geochemically inert waste rock during rock processing for other activities (that is, 201.1/.2/.3, 202, which requires large quantities of drainage rock to cover tailings area). | BGC indicates Grum Dump Rock Quarry has been exhausted (personal communication Nov. 2011). | Diamond drill and/or blasting exploration for four potential riprap quarries: Expanded existing RCDC quarry. Possible gabbro quarry site located downstream and uphill from the Cross-valley Dam but unsure of outcrop. Possible buried granite quarry location at north end of FCDC. No current outcrop noted and location may be outside mine footprint (EA issue). Possible granite quarry located north of the main haul road and west of the Grum transfer station; Faro Mine Road Granite Outcrop. Outcrop currently exists. | Total volumes of riprap and rockfill required. | N | Drilled 4 borings at Granitic Rock Outcrop Completed surface geophysical transects at Granitic Rock Outcrop and Grum Waste Rock Dump Quarry Explored shallow bedrock south of Faro Main WRD: Advanced 6 diamond drill holes Excavated 12 test pits Completed surface geophysical transects | CH2M HILL Canada Limited (CH2M). March 2015hh. Borrow Baseline Design Criteria Report, Faro Mine Remediation Project. Draft. Prepared for Government of Canada as represented by Aboriginal Affairs and Northern Development Canada and the Government of Yukon. March. | Total volumes of riprap and rockfill required.
[6 empty] | Estimate of size ranges for these materials. |  |  |  | Estimate of size ranges for these materials.
[6 empty] | Location of accessible quarry sites for production of these materials. |  |  |  | Evaluate calc-silcate sources in Faro WRD area
[6 empty] | Quantity and quality of the rock materials in potential quarry sites. |  |  |  | Evaluate calc-silcate sources in Faro WRD area

## Sheet1
Table B-1. Engineering Data Gaps Analysis – Status Summary of 2013 Tables
Faro Mine Remediation Project
2013 Summary Table | [7 empty] | FY 2016 Status Update
Activity ID | Task | Reclamation Unit | Description | Technical Uncertainties | Technical Assessments Required | Data Gaps Identified in 2013 | Proposed Field Work (in 2013) | Completed Fieldwork as of April 2016 | Project Scope Changes Since March 2013 | Remaining Gaps
ID | [6 empty] | (in 2013)
Sitewide
SW-001 | Mapping | Sitewide | Visual Aesthetics mapping for reclamation landscape planning. | Location of permafrost areas for planning of engineering structures. | Prepare current surface cover mapping; include layers for particle size distributions, existing vegetation type, and density. | Existing utility data; existing above ground and buried pipelines. | Complete site-wide utility survey. | Surveyed and inventoried sitewide water conveyance infrastructure (CH2M February 2016b) | Vangorda and Grum mine areas removed from project scope in spring, 2014. | Bathymetry data for Intermediate Dam Pond, Vangorda Pit, Grum Pit
|  |  | Provide detailed topography required for design at select locations. | Existing onsite surface material quality and texture. | Multi-spectral satellite imagery to assist with delineation of wet areas and zones of frozen sediment. Need to check whether 2012 aerial photography (which included infrared) is adequate). | Bathymetry surveys; IP Pond, Polishing Pond, Vangorda Pit, Grum Pit. | Conduct bathymetric surveys; Intermediate Dam Pond, Polishing Pond, Grum Pit, Vangorda Pit |  | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD . | Update surficial geology maps
|  |  |  | Existing onsite vegetation status. |  | Select locations may require surveys in key areas where tree cover may reduce accuracy of LIDAR mapping. | Survey new sampling locations. | Surveyed all new sample locations
[6 empty] | Geotechnical and chemical sampling location to date. | Map surface cover (GIS) – surficial geology mapped, update after field investigations completed. | Conducted sitewide Vegetation and Soil survey (CH2M March 2015z), (CH2M February 2015c)
[6 empty] | Review vegetation regrowth on Faro, Grum, and Vangorda dump sites. | Verify surface cover mapping of existing and revegetated areas.
Nested, comprehensive, fertility/texture data mapped onto surface topography.
SW-002 | Data Management and Chemistry | Sitewide | Incorporate additional historical electronic analytical, geochemical, and geotechnical data into warehouse if acquired. | Formatting of available electronic data requires additional processing to incorporate into data warehouse, and data that require processing before being loaded into the database will need QA/QC validation. | Integrate chemical and geotechnical data with GIS for SharePoint lookup. | Uncertain until data compiled and reviewed. | None.
New data added to the database as acquired.
SW-003 | Site Access Roads | Sitewide | Design access roads to provide reliable access to critical site locations during large storms events. | Design criteria for Access Roads; current capacity. | Design flow for culvert and drainages, loading capacity and use, requirements for all-weather access. | Condition survey of existing roads for use in short-term and long-term access. | Conduct field reconnaissance, measure and assess condition of culverts. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014. | Condition survey of existing roads
|  |  |  | Existing culvert capacities and physical condition. |  |  |  |  | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD .
SW-004 | Regional Groundwater Flow Modelling | Sitewide | Prepare a site-wide groundwater flow model of the Faro Mine Area and the Vangorda/Grum Area. This will be two separate models, one for each area. These models will provide estimates of groundwater flow directions, rates, and exchange between the surface water and groundwater systems within the model domain. The groundwater flow models will be used to estimate contaminant loading from groundwater to surface streams, support the design of groundwater interception systems, and evaluate the sensitivity of the performance of various waste rock cover systems on groundwater flow rates and SIS effectiveness. | The magnitude of the water budget components of the Faro Mine and Grum/Vangorda systems. The GoldSim model will provide initial estimates of these quantities. | Interpretation and integration of existing site water budget data with information collected during the 2012 field effort to develop a quantitative conceptual model of the site and convert that conceptual model into a numerical groundwater flow model. | The bedrock topography across the site, the spatial distribution of the hydraulic properties of the weathered rock aquifer and alluvial aquifer systems. The spatial and temporal distribution of hydraulic interaction between the GW/SW systems. | None. | See area-specific investigations | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  |  | The bedrock topography across the site, the spatial distribution of the hydraulic properties of the weathered rock aquifer and alluvial aquifer systems. |  | Collects results of fieldwork for individual areas of interest such as geophysics, drilling, well installation, and aquifer testing to use for the development of a regional GW flow model. |  |  | Site-wide modelling suspended in Fall 2015. Scope restricted to modelling required to support NFRC diversion design.
The spatial and temporal distribution of hydraulic interaction between the surface water and groundwater systems.
SW-005 | Surface Water Modelling | Sitewide | Developed site-wide hydrological model HEC-HMS in 2012, 2013 including all major conveyance elements and structures. | Some model parameterization components such as infiltration rates under various cover scenarios at some remedial areas on the site such as rock waste dumps are still unknown but will be supplied from efforts in other technical areas such as GW and re-vegetation. | Refinement of existing HEC-HMS hydrological model specific to each diversion design need and modelling of design storms specific to each diversion/catchment area. | Infiltration rates at specific areas including waste rock dumps under various cover scenarios. This will be provided through efforts in GW and re-vegetation discipline through modelling, literature reviews, and review of existing site data. | Maintain existing flow monitors and rainfall monitors. Obtain additional meteorological data at existing stations if equipment operational (temperature, wind, snow, and humidity). Obtain precipitation data concurrent with flow monitoring data collection. | Calibrated Meteorological stations (CH2M March 2014m) | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Modeled subcatchments to be used as tool for site-specific remediation activities including diversion designs. Water balancing and support for other disciplines. | Cover types in certain areas will be supplied from assessments in re-vegetation areas. | Integration of GW/SW interactions into hydrologic modelling. | Site specific physical data such as bed and bank materials within diversions. | Collect continuous flow data at newly established monitoring locations. | Bathymetric survey of Rock Drain Pond (CH2M March 2014m) | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD.
|  |  | A number of site specific hydraulic models were also developed to assess the Rose Creek diversion options. | The extent of the model discretization in certain areas such as the waste rock dumps is to be determined as it related to needs of particular diversion designs. | Some site specific hydraulic modelling is required to provide water surface profiles for some diversion structures. | Cover types in specific catchment areas. |  | Installed water level transducers at additional SW stages (CH2M March 2014d), (CH2M March 2014m), (Report Link ), (CH2M March 2015k), (Report Link),( CH2M March 2015n),(CH2M March 2015i) | Site-wide modelling suspended in Fall 2015. Scope restricted to modelling required to support NFRC diversion design.
|  |  | Additional site specific hydraulic models will be developed as required. | The interaction of GW and surface water will be further examined and incorporated into modelling considerations. | Additional flow monitoring at selected locations and acquisition of physical site data that vary by specific location onsite and diversion objectives is being collected as part of 2013 field efforts. | Sub-catchment delineation in site specific model areas such as waste rock dumps. |  | Completed channel cross section surveys (Report Link), (CH2M March 2015k), (Report Link),(CH2M March 2015n),(CH2M March 2015i)
|  |  |  | Uncertainties exist regarding the closure of several conveyance components, RCDC, Vangorda Creek, North Fork Rose Creek and additional opportunities for Grum Interceptor Ditch. These are to be assessed through alternatives review. | Physical site data including infiltration rates at specific features such as waste rock dumps and under various cover scenarios. | Conduct field surveys for use in SW modelling; cross sections, floodplains, structures etc. Confirm locations and scope through field reconnaissance. This will be completed for individual activity locations
Bed and bank materials characterizations to be carried out based on diversion design requirements.
Integration of re-vegetation and covers designs into catchment area model descriptions.
SW-006 | Site-Wide Groundwater/Surface Water Management Plan | Sitewide | Develop an overall site-wide strategy that considers the GW/SW objectives and key performance indicators (KPI) required to integrate the various onsite GW/SW activities. GW/SW man­agement activities assessed within an adaptive management plan (AMP). | Interactions of the GW and SW components. AMP integration of hydrology/hydraulic, groundwater, aquatics, wetland and terrestrial systems, and socio-economic objectives for water management planning. | Integration of all GW/SW diversion/water quality objectives and KPIs. Integration of aquatics, wetland, terrestrial systems, and socio-economic KPIs. | Objectives and KPIs on a site-wide basis for related disciplines. | None.
SW-007 | Cover Design Surface Analysis | Sitewide | Coarse woody debris as erosion control and revegetation cover support has been proposed; however, source, storage, and implementation have not been assessed. | Meso- and micro-topography information is missing from the cover type information and is a critical factor for this ecosystem. Resulting suitability for vegetation types and cover volumes needs to be assessed to provide appropriate topographic and planting opportunities. | Review surface treatment types and reconcile to current reclamation plan. Coarse, woody debris usage needs to be assessed for feasibility. | Assessment of coarse woody debris sources, storage, and application onsite to support this as a basis for reclamation surface design. | One field trial proposed for tailings area (see Activity 202.2) | Site visit completed August 25-27, 2015 (Report Link): | Vangorda and Grum mine areas removed from project scope in spring, 2014. | Trial cover for tailings area
|  |  | CHRM model results used to design and evaluate alternative covers need to be evaluated fully and tested against current performance on Grum Sulphide Cell. | Vegetation cover types depend on cover depth and microsite variation. Providing topography may require greater cover depths or gentler slopes to allow working of the cover material, which affects the material balance and landform planning. | Review CHRM model results with Grum Sulphide Cell performance. Need to review low- and very-low-infiltration cover locations onsite. | Check on area application of RLU types in current plan; review for new closure surface including ET covers. | All other field trials will be conducted after submittal of the Project Proposal during Advanced Design. | support technical direction on closure concepts for the WRDs and the RCTA | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD.
|  |  | Other unsaturated flow models (SHAW and VADOSE/W) need to be evaluated to model flow and snow/snowmelt effects. Cover infiltration descriptions suggest uncertainty regarding how the tailings cover will work with respect to vegetation cover. | Surface treatments cited in the C&R Plan are not used on maps – DSS, RAS, WDS, and SCS. | Application of alternative unsaturated flow model (SHAW or VADOSE/W). | Confirmation of very-low-infiltration cover performance and predictions of CHRM model. |  | facilitate information sharing to develop common ground on work completed to date
|  |  |  | Must re-evaluate the assumptions for very-low- and low-infiltration covers and locations shown in C&R Plan; compacted till may be adversely affected by freeze-thaw cycles. | ET cover design evaluation as addition to or replacement for low-infiltration covers. | Application of alternative unsaturated flow model. |  | consider key objectives and criteria to be discussed
|  |  |  | Consider ET cover design instead of, or in addition to, low‑infiltration covers for areas where cover material selection is proposed. | Function of cover materials is different for waste rock and tailings. Clarify cover expectations and revegetation planning over tailings for EA | Review ET cover design implications for very-low- and low-infiltration covers. |  | Cover Workshop completed October 21-23, 2015 (Report Link):
[5 empty] | Reconciliation of surface treatments from C&R Plan to current mapping of the site. Reconciliation of meso- and micro-topography requirements (for different cover types and revegetation requirements) with available cover material volumes. Review basis of design for Reclamation Landform Unit (RLU) surfaces and amendments, including topography, cover material type, and surface amendments. | Bulk density data for proposed cover materials, which are required to relate to soil erosion and vegetation establishment data. Initial soil bulk density is a critical factor in the success of any proposed ET soil cover. |  | Development of a base case and alternatives for landform design, regrading, and covers for the Faro Waste Rock Dumps and Rose Creek Tailings Area
Measure soil-water characteristic curves (SWCC) for representative growth media (till and fines).
SW-007 | Cover Design Surface Analysis (continued) | Sitewide |  |  | Analysis will be conducted related to waste rock dumps regrading and resloping related to the impacts of snow accumulation (particularly due to wind loading and wind redistribution) on: |  |  |  | Vangorda and Grum mine areas removed from project scope in spring, 2014.
[5 empty] | Landform design as it pertains to resloping and regrading waste rock dumps, snow loading on the leeward side of landforms, and upslope migration and deposition of snow in depressions on windward faces. |  |  |  | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD.
The geometry of proposed surface water management channels, conveyance of spring meltwater, snow blockage, and construction approaches that reduce mechanical clearing and provide capacity to keep meltwater contained in the channel.
SW-008 | Integrated Site Closure Plan | Sitewide | Completion of a closure drainage (surface and groundwater sources_ and allied landform plan, then overlaid by cover materials (soils) and revegetation plan. Required to be basis of closure impact and residual risk analysis for site environmental assessment, and to provide footprint information for drainage, access and landform features of the closure landscape to inform construction activities. | Closure plan for the site does not currently exist. A reclamation landform units plan exists in minimal detail, but it does not integrate drainage (or wet landscape) details or specify soil and vegetation prescriptions. | Completion of integrated closure planning will require input from the following technical disciplines: | Planning activities will require integrated plan review meetings for all disciplines, focused workshops on key disturbedundisturbed interface locations (NFRC, Emergency Tailings Area) and development of ArcView mapping layers for an integrated drainage plan, overlaid by soil prescription and vegetation (wetland and upland) layers. | None. | Covered in site-specific activities | Vangorda and Grum mine areas removed from project scope in spring, 2014.
[5 empty] | · Hydrology |  | Field work captured in task-specific activities. |  | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD.
· Water quality
· Hydrogeology
· Risk assessment
· Waste rock and covers
· Revegetation/reclamation
· Construction sequencing
· Wildlife and fisheries
SW-009 | Revegetation Materials Planning and Sourcing | Sitewide | Sourcing revegetation materials will require a 4- to 5-year lead time to grow plant material and prepare the large volumes of planting material for use exactly when required for erosion control. | Helicopter seeding has been proposed for steep revegetation areas; this needs to be assessed for feasibility, cost, seed volume, and timed with regrading and cover material sequencing. | Review of potential vegetation sources, with preference for (1) First Nations greenhousing or propagation facilities and (2) Yukon-based facilities. | Identification of potential greenhousing and nursery facilities. | None. | None. | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Seeding materials need to be sourced and checked for reliable quality with respect to weedy seed inclusion and large volumes required for native species and proposed agronomic species. | Some materials are planned to be whips or cuttings; source areas need to be identified for capacity to provide material and whether the areas have been assessed in the environmental assessment. Additional source areas may be required and must be identified. Methods of collection and planting need to be assessed for large areas planned in annual reclamation increments. | Environmental assessment needs to review if vegetation cutting/whip collection areas have been included in assessment. These need to be optimized to map potential donor areas with areas likely to be disturbed during construction and access work. | Identification of suitable seed sources and cutting/whip sources to be included in the local study area, if required. |  |  | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD.
|  |  |  | Use of legume species for soil nitrogenation and revegetation support. |  | Identification of seed application methods to be considered in reclaimed surface preparation including helicopter, hydroseeding, or surface application.
|  |  |  | Assessment of capacity for projected vegetation volumes needs to be performed so that material is grown with a 4- to 5-year lead time prior to revegetation requirements. |  | Data from EDI on current stock cost.
Not clear if facilities outside the province would be required to provide bulk vegetation volumes for annual reclamation.
SW-010 | Sitewide Soils Mapping | Sitewide | Soils data are currently dispersed in different formats and documents. Need site-wide database of soil quality to provide basis for material movement and balance, and planned reclamation covers. |  | Need to categorize data to help identify problematic high or low levels of Ph, Pb, As, Zn, and coarse fragments. | Production of site-wide soil database to house existing data and new baseline data to be collected for new borrow areas. | Collect soils data to augment available data. | Completed site-wide soil characterization survey (CH2M February 2015c) | Vangorda and Grum mine areas removed from project scope in spring, 2014. | None
[5 empty] | Consolidation of current soils information needs to be augmented with baseline data collected for new borrow areas. | Identification of problematic Ph, metals, and coarse fragment levels to assist in allocation of cover materials to reclaimed surface planning.
SW-011 | Update 2004 Site-Specific Seismic Hazard Assessment | Sitewide | The seismic hazard assessment was updated in 2013 by Dr. Gail Atkinson (Final Report titled Seismic Hazard Assessment for Faro, YK, April 2, 2013). | None. | None. | None. | None. | None
SW-012 | Identify Additional Areas with a High Probability of Becoming Contaminated Groundwater Discharge Pathways in the Future | Sitewide | Identify additional areas with a high probability of becoming groundwater discharge pathways in the future as ARD reactions continue to accelerate. Support the development of a long-term monitoring network that will identify areas of degrading groundwater quality and potential ARD pathways to be addressed through the AMP. | Implications of new excavations along toe of existing waste rock dumps associated with trenching and borrow source development. | Perform GIS analysis comparing current topography with pre-mining topography to identify buried drainages that may concentrate groundwater discharge. | Further investigate areas with a high potential to be future contaminant seepage pathways. | No field work required for Project Proposal. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014. | None
|  |  |  | May need to design sump areas to collect seepage along the waste rock perimeter and incorporate in GW/SW interaction model. |  |  | Groundwater sampling and installation of additional monitoring wells may be required in the future based on evaluation of site data.
SW-013 | Delineation of Permafrost at Faro Mine and Grum/Vangorda Area | Sitewide | The presence of massive or discontinuous permafrost within the groundwater system has a significant influence on groundwater flow directions, rates, and SW/GW interaction. | The design of an effective SIS requires knowledge of permafrost in the immediate area of the system. Permafrost may also alter contaminant migration pathways and require modification to groundwater monitoring network designs. | Perform detailed literature review to located previous studies or field investigations that delineated permafrost extent at the FMC. Proposed geophysical surveys in the vicinity of SIS installations can be expanded to identify the presence of permafrost in those areas. This is the same permafrost survey identified under the regulatory data gaps. | The potential for permafrost to influence the effective operation of the groundwater interception systems. | No field work required. Evaluation of permafrost will be conducted at site specific closure locations. | See area- specific investigations | Vangorda and Grum mine areas removed from project scope in spring, 2014.
Evaluate the potential of using multispectral satellite imagery and post-processing to identify areas with a high probability of having near-surface permafrost.
SW-014 | Site-wide Water Balance Model and Piezometer Installation | Sitewide | Develop an integrated GW/SW model that will provide an estimate of the site-wide water balance, contaminant loading, and surface water quality. | Existing model assumptions pertaining to flow/drainage conditions applications and geochemical model for waste rock dumps and tailings. | Review current model capabilities pertaining to water balance and model functionality. Build mass balance equations in the model to track water throughout the system under different hydrologic conditions and stages of remediation. User interface will be developed that facilitates sensitivity studies, summarizes all the user inputs, and promotes tool functionality. | Update infiltration and cover infiltration data with more accurate data if available. SRK (2006) provided an update to the infiltration rates, more recent data might be available. Information about the tailings location and how they are connected in the water balance. | None. | Continuous water level monitoring completed in Faro, Grum and Vangorda WRDs (CH2M October 2013b), CH2M March 2014c), CH2M March 2015b) | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Install piezometers into the Grum, Vangorda, and Faro waste rock dumps to monitor seasonal groundwater level fluctuations using recording pressure transducers. | Quality of existing and new data needs to be evaluated and confirmed for appropriate use. | Check of the improved model equations and conduct model runs at different scenarios. | Need access to the site hydrologic and analytical data and compile site-wide hydrologic and flow data. Calibrate model with existing field conditions from field data. |  |  | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD.
|  |  |  | Magnitude of fluctuation in groundwater levels driving the geochemical reactions within the waste rock. | Conduct sensitivity analysis on key parameters that influences the water balance and contaminant loading throughout the system. | Magnitude of seasonal groundwater level fluctuation within Faro, Grum and Vangorda waste rock dumps. |  |  | Site-wide modelling suspended in Fall 2015. Scope restricted to modelling required to support NFRC diversion design.
Develop post-processing tools to report results and summarize results of predictive modelling.
Incorporate the observed groundwater level fluctuations into the geochemical analysis performed to estimate future seep and groundwater quality.
SW-015 | Develop Geochemical Loading Models | Sitewide | Develop individual geochemical models for the waste rock dumps, the Rose Creek Tailings Facility, and the three pit lakes. Integrate into the overall site-wide water balance model to generate a comprehensive predictive water quality model for the site. | Currently do not have possession of geochemical models developed for the waste rock piles and Rose Creek Tailings Facility. Existing modelling did not include three pit lakes. Assume requirement to rebuild geochemical models for waste rock piles, tailings facility, and pit lakes. | Review of the working functions of all current models and submodels. Current model feeds on a series of geochemical submodels for each facility type (that is, WD, pit, TSF), which in turn are based on a series of field and lab tests and assumptions. Field and laboratory tests included oxygen and temperature profiles and static and kinetic laboratory testing. Review additional documents pertinent to the model development may also be necessary (for example, geochemical reports). | Anticipated water quality of surface runoff and seepage from waste rock dumps during construction. | Conduct sampling around each WRD and in pits, and aqueous sampling associated with seepage, porewater, groundwater, and surface water. | Drilled and install 10 GW, pore gas and thermistor port installations in sitewide WRDs; (CH2M October 2013b), (CH2M March 2015b),(Report Link), (Report Link) | Vangorda and Grum mine areas removed from project scope in spring, 2014.
[5 empty] | Spreadsheet database working functions need to be developed and the model needs to be calibrated and compared to the existing geochemical component of the GoldSim model. Exportable outputs need to be developed to export into the GoldSim model. | Leaching potential and sediment loading potential of freshly exposed (regraded) waste rock from each of the waste rock dumps. | Install or relocate monitoring points where sources are reconfigured or revised. | Completed 3x annual (Spring, Summer and Winter) monitoring of CH2M and Existing SRK WRD installations. (CH2M October 2013b), CH2M March 2014c), CH2M March 2015b) | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD.
[6 empty] | Geochemical sub models based on historical and field data to use as inputs to the GoldSim model. | Monitor at existing and newly installed points to capture evolution of the system with closure activities. | Completed site-wide seep sampling and pit lake profiling (CH2M October 2013a ), CH2M March 2014c), CH2M March 2015b) | Site-wide modelling suspended in Fall 2015. Scope restricted to modelling required to support NFRC diversion design.
[6 empty] | Update model with latest data available for each source included in the model (that is, 33+WRDs, 3 pits, and 2 TSF). | Conduct additional geochemical testing of samples from WRDs, ore piles, and oxide fine piles. Piezometer installations and associated laboratory testing required near East Waste Rock dump and at Northwest Waste Rock Dump. | Completed annual RCTA GW monitoring in fall (CH2M March 2013m), Report Link)
Drilled and install GW monitoring cluster in north portion of Intermediate Tailings (Report Link)
Drilled and installed 2 GW monitoring clusters in the Original Tailings Impoundment at mouth of the ETA canyon (CH2M March 2015b)
SW-016 | Evaluate Pit Lakes Dynamics for Water Treatment Collection and Storage, and Sludge Disposal | Sitewide | The C&R Plan proposes several different uses for the three pit lakes: storage for water treatment and sludge disposal at Faro Pit, storage for water treatment, and possible sludge disposal at Vangorda Pit. Whether the pit lakes are used for water collection and storage in advance of treatment or sludge storage post-treatment, an understanding of basic EPL physical- and chemical-state condition dynamics is required to properly manage inputs and withdrawals from the lakes. | Insufficient physic-chemical data available for pit lake limnology (that is, stratification data). Need fine-grain data to capture seasonal pit dynamics, including under ice data, year-round conductivity, temperature, density, dissolved oxygen, and redox data. | In situ data probes with battery power source to permit year round data collection. | Current data set is insufficiently fine grain to capture potential important dynamic processes; under-ice dynamics critical to understanding year-round lake dynamics because year round performance is not understood. These data are critical to understand stratification. Stratification dynamics are funda­mentally important to determine potential of sludge storage in Faro Pit. | Continue conducting pit lake profiles; additional seasonal sampling (Laberge). | Complete annual pit lake profiling in Faro pit lake in fall (CH2M October 2013a, CH2M March 2014c, CH2M March 2015b
|  |  |  | Need pit water balance, which will be collected in site-wide water balance. Need field samples for water quality data to corroborate instrumentation data. | Conductivity, temperature, density, dissolved oxygen, and oxidation-reduction data at three depths. |  |  | Complete depth-discrete pit lake sampling in Faro pit in fall 2012 (CH2M October 2013a)
[5 empty] | Pressure sensors at three depths in one or more locations. |  |  | Complete Vangorda and Grum Pit lake profiling in fall 2012 and 2013 (CH2M October 2013a) (CH2M March 2014c)
Pressure level gauge in lake.
Obtain samples June through August at depths of in situ redox sensors.
Redox evaluation, with corroborating wet chemistry data, the types of biogeochemical processes that occur with loss of oxygen (anoxic conditions). Redox data are essential to determine potential reductive dissolution of iron sludge from the WTP or for sulphide sequestration of zinc in settled algae.
Faro Mine Area (Activity Code 100)
101 – Faro Pit Safety Berm
101.1 | Faro Pit Wall Stability Management | Faro Mine WRDs and Faro Pit | Evaluate pit wall stability and consequences of failure | Long term stability of pit walls and long term management requirements. | Field inspection and evaluation to determine requirements/needs for (1) analytical stability evaluation, (2) instrumentation and monitoring, and (3) slope management including possible stabilization measures. | Requirements/needs for stability evaluation, subsurface information gathering and instrumentation and monitoring | Conduct reconnaissance, review geologic mapping, and review of previous evaluations and monitoring results. Assumed that installation of survey monuments and prisms completed by YG under separate TA. | Complete pit wall stability evaluation geological reconnaissance (CH2M March 2014q): | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  |  | Consequences of pit wall failures - a rapid slide in pit may cause wave that could endanger pumping infrastructure and operating personnel) |  |  |  | Drill, install and monitor 2 slope inclinometers and vibrating wire piezometers and 2 standpipe piezometers at Faro Creek Diversion along Northeast wall of Faro Pit. Downhole acoustic televiewer observations performed in boreholes before completing installs to characterize bedrock jointing (Report Pending)
101.2 | Safety Berm around the Pit | Faro Mine WRDs and Faro Pit | Construct berm around Faro Pit to restrict physical access. | H&S implications regarding the timing of berm construction. Need to allow for ongoing spalling of pit walls; 5-m offsets proposed can be expected to vary. | Identify borrow materials. |  | Conduct engineering geologic field reconnaissance. | Geological Reconnaissance completed at Faro Pit (CH2M March 2015oo) | Vangorda and Grum mine areas removed from project scope in spring, 2014.
Evaluate spalling of pit walls.
102 – Surface Water Diversions
102.1 | Faro Creek Diversion (East Valley) | East Side ARD Collection and Diversions | Relocate existing diversion channel to new alignment up hillside; intercept and convey Faro Creek along the eastern slope of Faro Creek Valley above the existing diversion channel. | Discontinuous permafrost, ground conditions, channel seepage losses, water quality, interaction of GW and SW, hydraulic analysis, and stability of the pit wall. Management of localized flows captured in existing FCDC drainage area. | Reassess diversion options, preliminary design criteria (C&R Plan, Table 4.1) Review of existing information regarding geotechnical, water quality, pit wall stability, channel stability, seepage, hydrology, hydraulics, assess current channel design capacity, diversion opportunities, and icing potentials. | Bed and bank materials characterizations. | Physical survey for cross sections, bed and bank materials characterizations, and floodplain cover. | Completed cross section surveys (2014 Report Link) |  | none
|  |  | Evaluate design criteria, need for overflow structure where natural creek meets diversion to spill excess floodwater into pit. | The existing FCDC will remain but will be revegetated. Local drainage will be captured, but the discharge from the existing FCDC needs to be considered in terms of drainage area and seepage and discharge points for high precipitation events that may overflow the revegetated channel. | Determination of local SW flow characteristics and drainage area to the existing FCDC and pit area have been carried out. This analysis will be refined. | New channel bed and bank material characterizations; additional soils data including more information on permafrost and ice content. Golder report (detailed comparison of alternatives) described test pits along alignment but refusal at shallow depths because of permafrost. | Monitor surface flow at NFRC monitoring stations and Faro Creek Diversion. | Geological reconnaissance of existing diversion and SRK 2009 Proposed diversion alignment (2014 Report Link)
|  |  | Address local SW flow to Faro Pit. |  | Overflow structure foundation and stability evaluations. Potential hydraulic analysis of structure. | Geotechnical data gaps at the new diversion channel alignment include Depth to bedrock | Conduct geotechnical field investigation: | Continuous SW level monitoring transducers deployed (2014 Report Link)
|  |  | Consider alternative of building new diversion along the west side that can potentially flow to North Wall Interceptor/Guardhouse Creek. |  | Permafrost impacts on design considerations. | Soil and rock mass strengths | Detailed engineering geological field reconnaissance and seismic refraction along alignment. | Completed Rapid Geomorphic assessment (Report pending)
|  |  | Design to preliminary design level of detail. |  | Riparian and floodplain re-vegetation designs. | Presence and extent of permafrost | Test Pits | Investigated seepage through Faro Valley (Report pending):
[5 empty] | Hydrologic model analysis for design flows in diversion. | Additional flow monitoring data collection at recommended 2013 stations for additional model refinement. | Geotechnical testing; gradation and index testing) | Drill and install 3 well clusters
[5 empty] | Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. |  |  | Conduct aquifer testing
Complete SW discharge measurements in FCD
Completed 22 surface geophysical transects in Faro Valley (Report Pending)
Drill 6 borings, install piezometers and thermistor ports along potential FCD alignment (Report pending)
102.2 | West Valley Extension | East Side ARD Collection and Diversions | Direct clean water from west side of valley around Faro Pit. | Same as Activity 102.1. | Same as Activity 102.1. | Same as Activity 102.1. | Physical survey of cross section data, potential bed and bank materials characterizations, and floodplain cover. | Same as 102.1
|  |  | Minimize seepage losses. |  |  |  | Conduct geotechnical field investigation:
Detailed engineering geological field reconnaissance and seismic refraction along alignment.
Test Pits
Geotechnical testing; gradation and index testing)
102.3 | North Wall Interceptor Ditch | West Side Diversions | Remediate existing North Wall Interceptor ditch (NWID) and discharge to Rose Creek below Cross Valley Dam; improve or construct access. | Discontinuous permafrost. | Some site specific hydraulic modelling required to provide water surface profiles. | Detailed cross section data including channel and floodplain for Upper Guardhouse Creek and NVID for modelling obtained from LiDAR. | Surveys for detailed cross section data, bed and bank materials characterizations, and flood plain cover characterization. | Excavated 5 test pits (Report Link) | Interim water treatment system constructed in Mill Site Area in 2014. Postponed and reduced scope of project proposal investigations due to budget and schedule implications. | Depth to bedrock and rock strength
|  |  | The Upper Guardhouse Creek flows into the NWID. Water from the creek is generally clean but contributes hydraulic load. | Amount of GW/SW interaction. Water quality. | Geotechnical, water quality, channel stability, seepage, hydrology, hydraulics modelling refinements, design storm flows, icing, soil cover, and revegetation options. | Channel bed and bank materials characterizations for modelling. | Collect soils data (geotechnical), ice data, flow data, and water profile data (surface elevations). | Complete geological reconnaissance (Report Link) | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD
|  |  | Design to preliminary design level of detail. | Little information available for area, need care to separate from Lower Guard House Creek. Design criteria needs to be evaluated in the context of the overall closure. | Limited data have been collected from the UGC and the NVID in terms of site-specific information. The valley slopes are extreme and determining channel capacity and design for erosion control is key. | Assess area below Cross Valley Dam for discharge design requirements to Rose Creek – flow management and design requirements. | Conduct geotechnical field investigation: | Completed channel cross section surveys (Report Link)
|  |  |  | Soil cover and revegetation plan required for remediated ditch area. | Preliminary information indicates depth of overburden in some areas; uncertain information. Determine impacts of flow on Rose Creek downstream from convergence. | Geotechnical data gaps at the new diversion channel alignment includes the following: | Detailed engineering geological field reconnaissance and seismic refraction along alignment. | Completed rapid geomorphic assessment (Report Pending)
|  |  |  | Discharge design for section below Cross-valley Dam needs to be determined. | Permafrost impacts on design considerations. | Depth to bedrock | Test Pits
|  |  |  | Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. | Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. | Soil and rock mass strengths | Geotechnical testing; gradation and index testing
Presence and extent of permafrost
102.4 | Lower Guardhouse Creek | RCTA | Intercept seepage from mill and stockpiles. | Seepage rates, water quality, interception potential, long-term performance of interception. Design criteria provided in the C&R Plan, Table 4.3, require definition and linkage to seepage management and water quality. SW contribution to flows. | Refinement of hydrologic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. | Detailed cross section survey data including channel and floodplain areas; channel bed and bank materials characterizations; soils data including permafrost; historical channel ice data, flow monitoring, and water profile data (surface elevations). | Surveys for detailed cross section data, bed and bank materials characterizations, and flood plain cover characterization. | Completed geological reconnaissance (Report Link) | Interim water treatment system constructed in Mill Site Area in 2014. Postponed and reduced scope of project proposal investigations due to budget and schedule implications | Depth to bedrock
|  |  | Direct water to Faro Pit by pipeline (ETA Activity 105). | Hydraulic modelling to contain design flow rates. Establish final design flow rate estimates and integrate evaluation of GW and SW. Evaluate GW interception based on monitoring results. | Establish design flow rate estimates and integrate evaluation of GW and SW. Evaluate GW interception based on monitoring results. | Additional flow monitoring data for model calibration and validation. | Evaluate channel seepage losses, water quality, flow data, and water profile data (surface elevations). | Completed specific conductivity survey Report Link) | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD | Geotechnical and hydrogeological characteristics of local material
|  |  | Install GW and SW monitoring network. | Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. | Seepage rates, water quality, interception potential, and long-term performance of interception. Design criteria provided in the C&R Plan, Table 4.3, require definition and linkage to seepage management and water quality. | Depth to bedrock and aquifer properties in area of planned seepage collection system. | Establish a flow monitoring station and collect continuous flow data. | Completed periodic flow monitoring at GDHSCK (Report Link), CH2M March 2014c), CH2M March 2015b)
|  |  | Improve or construct access road to the NW Dump near Upper Guardhouse Creek. |  |  | No information exists for this channel or its proposed final extension. Geotechnical data gaps includes: | Conduct seismic refraction survey to determine depth to bedrock in area of planned seepage collection system. Install monitoring wells and collect water level, water chemistry, and aquifer property data.
|  |  | Remove waste rock between W8 and W10 on Upper Guardhouse Creek. |  |  | Depth to bedrock | Detailed engineering geological field reconnaissance with test pitting along alignment
|  |  | Design to preliminary design level of detail. |  |  | Soil and rock mass strengths | Install borings, piezometers and thermistors
[6 empty] | Presence and extent of permafrost | Collect samples and determine ice content
[6 empty] | Permeability of soil and rock | Test permeability in situ. Conduct index tests (grading and Atterberg limits) on soil samples
Effectiveness of current system and need for enhancement.
103 – Zone II Pit
103.1 | Install Pump in Existing Wells, Piping, Heat Tracing | Faro WRDs and Pit | Reduce effects of contaminant yield from Zone II Pit. | Access and maintenance of year-round pumping system with minimal O&M costs. | Automate operations. |  | Detail field conditions of pipeline | Zone II pumping well operated and monitored by site Care and Maintenance Operator |  | none
|  |  | Maintain water level in Zone II Pit to maintain gradient towards the pit, away from NFRC. |  |  |  | Record operating data (pumping rate, water level, operation duration, etc.)
(New well-constructed in FY 2012).
104 – Oxide Fines and Low-grade Ore
104.1 | Relocate Oxide Fines to Low-grade Ore Stock Piles (LGSP) C | Faro WRDs and Pit | Relocate oxide fines to LGSP C to reduce contamination from these sources to GW and SW. | Volume of material to be relocated and covered. | Refined volume of oxide fines material to be relocated and covered. | Geotechnical properties: | Install borings and test pits to delineate volume of Oxide Fines Stockpile area. | Drilled 1 boring in Oxide Fines Stockpile and install GW monitoring well, thermistor port and pore gas ports (Report Link) |  | Geological reconnaissance of areal extent of oxide fines piles
|  |  | Alternative – Relocate oxide fines to the sulphide cells as a levelling (cushion) layer below the synthetic cover. | Foundation conditions of LGSP C (water table, and geotechnical properties) | Final landform design options, including water management plan – both LCSP C and sulphide cells. | LGSP C - Foundation stability, material gradation, GW characteristics and trafficability. | Excavate additional test pits on the plateaus of the fill areas to determine both the horizontal and vertical (depth below surface) extent of Plant Site Area impacted materials. | Excavated 3 test pits in Oxide Fines Stockpile and 1 test pit in LGSP C (Report Link)
|  |  |  | Constructability implications (for example, requirements for specialized equipment or operating procedures). | Optimize removal and consolidation to reduce footprint and costs; minimize environmental risk (for example, constructability, minimize disturbance). | Oxide Fines Stockpile | Collect and analyze samples of LGSP C, Oxide Fines Stockpile, and Plant Site Area materials for geotechnical and geochemical properties. | Results corroborate depths determined from pre-mining topography
|  |  |  | Under the alternative to relocate oxide fines to the sulphide cells, geochemical compatibility of oxide fines with sulphide waste. | Alternatives Assessment – Relocate oxide fines to LGSP C versus to sulphide cells. | Material gradation
Refinement of material volumes:
Oxide Fines Stockpile – Better establishment of the material types down to the original topography as well as better definition of the areal extent of the oxide fines and medium grade ore stored therein.
Plant Site Area – Better delineation to assess both the horizontal and vertical (depth below surface) extend of these materials.
For alternative to relocate oxide fines to sulphide cells, geochemical compatibility of oxide fines with sulphide waste.
104.2 | Relocate Medium-grade Ore (MGO), Including Brown and Green Oxide Fines (Oxide Fines #1) to LGSP C | Faro WRDs and Pit | Relocate MGO to LCSP C to reduce contamination from these sources to GW and SW. | Foundation conditions of LGSP C (water table and geotechnical properties) | Final landform design options – both LGSP C and sulphide cells. | Geotechnical properties: | Collect and analyze samples of LGSP C and MGO materials for geotechnical and geochemical properties. | LGSP C – See 104.1 above | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD. | Material gradation of medium grade ore
|  |  | Same issue as above. | Health and safety issues of moving MGO and brown/green oxide fines. | Optimize removal and consolidation to reduce footprint and costs; minimize environmental risk (for example, constructability, minimize disturbance). | LGSP C – Foundation stability, material gradation, GW characteristics, and trafficability. | Conduct soil boring at MGSP04 to determine thickness of ore pile. | MGO – none
|  |  | Alternative – Relocate this waste to the sulphide cells as a levelling (cushion) layer below the synthetic cover. | Constructability implications (for example, requirements for specialized equipment or operating procedures). | Alternatives evaluation that includes removing MGO to LGSP C versus to sulphide cells. | MGO – Material gradation.
|  |  |  | If alternative, geotechnical compatibility of MGO with sulphide waste. |  | For alternative to relocate MGO to sulphide cells, geochemical compatibility of MGO with sulphide waste, final landform design of sulphide cells (footprint, slope angles, height of capped cell).
104.3 | Cover and Revegetate LGSP A | Faro WRDs and Pit | Reduce contamination from these sources to GW and SW. | Implications for cover design if capped material generates heat. | Infiltration modelling (cover optimization); VADOSE/W, SLIDE (slope stability); TEMP/W; and re-evaluate design criteria in the C&R Plan, Table 4.6. | Review RLU planning basis with the Waste Pile and Tailings Discipline Team, | DCPT (within a grid into underlying soils). | Completed vegetation and soil survey (CH2M March 2015z), (CH2M February 2015c) | Development of remediation plan for NFRC prioritized in 2015 to address developing issue of contaminated seepage from Intermediate WRD | Material gradatation of LGSP A
|  |  | Alternative – Relocate this waste to the sulphide cells as a levelling layer for the synthetic cover or consolidate in LGSP C. | Grum Sulphide Cell is already capped with a very-low-infiltration cover that needs monitoring and possibly instrumentation. Need to maximize capping design and performance information for LGSP sites by closely monitoring results of existing GSC cover work. | Evaluate SW management – energy/erosion potential. | Cover and revegetation trial for LGSP reclamation to be recommended in the project proposal. | Evaluate cover design (if capping in place): Ten test pits for gradations/grain size and Atterberg limits testing.
|  |  |  | Proposed reclamation surface is rough and loose; however, the field investigation concluded that the microtopography is bad for plateau areas because it promotes ponding and infiltration. | Geochemical compatibility of low-grade ore with sulphide waste needs to be assessed in terms of potential leachability. | Existing site water balance versus water balance after final grading needs to be evaluated to determine surface and GW impacts.
[5 empty] | Health and safety issues of moving low-grade ore. | Water/sediment management plans: Drainage plan, sedimentation ponds/wet landscape options, existing stockpile topography; and final landform design options.
Design life reduction of the membrane due to conditions (temperature/caustic gas production).
Water table location and fluctuation.
104.4 | Cover and Revegetate LGSP C | Faro WRDs and Pit | Reduce contamination from these sources to GW and SW. | Implications for cover design if capped material generates heat or caustic gas is produced. | Infiltration modelling (cover optimization); VADOSE/W, SLIDE (slope stability); TEMP/W; and re-evaluate design criteria in the C&R Plan, Table 4.6. | Review RLU planning basis with Waste Pile and Tailings Discipline; consider a revegetation trial on this kind of slope/material. | Dig test pits; conduct gradation/grain laboratory testing size for cover. | Completed vegetation and soil survey (CH2M March 2015z), (CH2M February 2015c)
|  |  |  | Grum Sulphide Cell is capped with a very-low-infiltration cover needs monitoring, and possibly instrumentation. Need to maximize capping design and performance information for LGSP sites by closely monitoring results of existing GSC cover work. | Evaluate SW management – energy/erosion potential. | Existing site water balance versus water balance after final grading needs to be evaluated to determine surface and GW impacts. |  | Excavated 1 test pit in LGSP C (Report Link)
|  |  |  | Design life reduction of the membrane due to conditions (temperature/caustic gas production). |  | Water/sediment management plans: Drainage plan, sedimentation ponds/wet landscape options, existing stockpile topography; and final landform design options.
Proposed reclamation surface is rough and loose; however, the field investigation concluded that the microtopography is bad for plateau areas because it promotes ponding and infiltration.
105 – Emergency Tailings Area
105.1 | Remove Tailings to Rose Creek Tailings Facility | Mill and ETA | Remove tailings to Rose Creek Tailings Facility to reduce contaminant loading to GW and SW. | Constructability Implications (for example, requirements for specialized equipment or operating procedures). | Excavation plan that includes sequencing and hydrology and sediment management. | Suitable disposal location for tailings and underlying impacted soils. | Delineate tailings thickness and estimate extent of impacted o/g. Geochemical characterization of upper impacted o/g. | •Drilled one boring through ETA tailings into native overburden (CH2M March 2015r) |  | none
|  |  | Alternative – Leave the tailings in place and cover; channelize flow of major seeps (for example, X23) in granular trenches to a seepage collection point (part of 105.2 below). | Under alternative to leave tailings in place, geotechnical condition of Mine Access Road as a (pervious) solids retaining structure. | Hydrology and GW/SW interaction of closure configuration. | Quantity of contaminated fill to be removed downgradient from the Access Road. | Confirm suitable disposal location for tailings and underlying impacted soils. | Drilled two borings through mine access road to bedrock (CH2M March 2015r)
[5 empty] | Alternatives Assessment – Relative merits of removing tailings and underlying impacted soils versus leaving tailings in place and covering. For example, removal of the tailings could drain the wetland upgradient (SE of ETA). |  | Perform field assessment to determine viable excavation methods. | •Advanced six seismic CPT soundings (CH2M March 2015r)
[5 empty] | Alternatives Assessment – Relative merits of removing contaminated soils downgradient from the Access Road versus leaving in place. |  | If appropriate, quantify contaminated fill to be removed downgradient from Access Road.
105.2 | Install GW and SW Collection Systems | Mill and ETA | Intercept contaminated GW and SW before discharge into the Rose Creek Tailings Area. | Define bedrock surface. | Foundation evaluation for concrete dam structure, | SW flow calculations. Detailed cross section survey data including potential channel and floodplain areas. | Additional borings or test pits and seismic refraction surveys to define bedrock surface for concrete dam structure. | Complete surface geophysical transects CH2M March 2015s) |  | Detailed cross section surveys
|  |  | A low head concrete dam will be constructed at the entrance of the topographic “funnel” south of the Access Road. Since there is little soil cover at this location, it will be mainly a surface water collection system with the concrete structure founded on bedrock. | Quantify site water budget. | Concrete dam stability: | Potential channel bed and bank materials characterizations and floodplain cover characterization. | Conduct detailed cross section surveys | Excavated one test pit CH2M March 2015s)
|  |  | Construct diversion ditches, sump, and pumping stations for diversion of waters from ETA during construction. | Hydrogeologic assessment: seepage interception (funnel and gate) design options. | Seepage and stability | Rate of GW and SW inflow from Mill Creek Canyon. | Conduct detailed engineering geological field survey, characterize bed and bank materials. | Installed stilling wells and water level transducers at two SW locations CH2M March 2015s)
|  |  | Pipe to Faro Pit. |  |  | Aquifer property information in the Mill Canyon area. |  | Completed geological reconnaissance CH2M March 2015s)
Bedrock contact delineation in Mill Canyon and Old Faro Creek immediately downgradient from the WRD.
Rate of GW and SW inflow from Mill Building Site.
Alluvial aquifer thickness and bedrock topography south of the Mine Road.
105.3 | Cover and Revegetate ETA | Mill and ETA | Determine appropriate closure cover for ETA after tailings closure option is chosen (remove or leave in place). | Closure cover depends on the decision regarding the final disposal of tailings. | Closure surface configuration and capping materials need to be designed (if applicable). Cover soil availability and type needs to be determined. | SW flow calculations. | Surveys for detailed cross section data, bed and bank material characterizations | Completed vegetation and soil survey (CH2M March 2015z), (CH2M February 2015c) |  | none
|  |  | Tie revegetation plan in to existing adjacent vegetation at the toe of the Faro waste rock piles. | Existing vegetation needs to be characterized – will be affected by tailings removal due to impoundment of water in this area. Revegetation footprint could then be larger than the ETA. | Appropriate vegetation cover to fit in with existing adjacent vegetation. Area needs to be assessed and planned. | Detailed cross section survey data including potential channel and floodplain areas; potential channel bed and bank material characterizations and floodplain cover characterization. | Floodplain cover characterization.
|  |  | This is a high-visibility area adjacent to the site access point and, therefore, requires proactive planning for the reclamation surface. | Potential impact on North Fork Rose Creek downstream of the rock drain needs to be considered in revegetation and contour planning. | Failure modes and effects analysis of various ETA SIS configurations (for example, failure of active pumping). | Integration of SW and GW modelling approaches and results. | Survey existing vegetation and soils on site and adjacent. Cover soils availability and type assumed to be provided by site-wide soils mapping.
[6 empty] | Existing vegetation and soils need to be characterized to assess impact of remediation. | Investigate onsite/suitable vegetative species tolerance/translocation of metals and preferred soil cover type/makeup (for example, organics, nutrients), especially those of food chain concern; can be done after input from risk assessment depending on timing from that study.
Type and quantity of borrow materials required for regarding and revegetation (depends on design alternative selected).
106 – Waste Rock Dumps
106.1 | Regrade and Reslope Main and Intermediate Sulphide Cells | Faro WRDs and Pit | Consolidate smaller piles of highly reactive material into larger dumps where practical. | Chemical compatibility of sulphide cells with other fine grained materials to be capped under very low infiltration liners. Use fines as a cushioning layer for the liner. | Optimize regrading/resloping plan. | Confirmation of sulphide cell footprint. | Boreholes to confirm delineation of Sulphide Cell. | Excavated 12 test pits (Report Link) |  | none
|  |  | Predictive modelling (geochemical, hydrologic, and GW/SW interaction) and monitoring program to provide basis for AMP. | Delineation of sulphide cell footprint. | Develop sediment control plan. | Physical characteristics, including gradation of waste rock and any other materials that would form the foundation for the cover (necessary to design cushion layer for very low infiltration cover). | Dig test pits to support evaluation of regarded/resloped waste rock surface and any other materials that would form the foundation for the cover. | Drilled boring through Main Dump and completed with pore gas and thermistor ports (Report Link)
|  |  | Alternative – consolidate oxide fines and MGO to sulphide cells as cushioning layer below liner if alternative assessments for those areas warrant doing so. | Suitability of regraded/resloped waste surface to serve as foundation for cover. | Assess GW and SW interaction in affected foundation areas. |  | Conduct boring and sampling to support geotechnical, geochemical, and infiltration modelling.
Assess geotechnical stability of regraded/resloped waste.
Assess suitability of regraded/resloped waste surface to serve as cover foundation.
Confirm delineation of sulphide cell footprint.
For alternatives that include relocating oxide fines and/or MGO to sulphide cells, optimize regrading/resloping plan and use of fines as cushioning layer for the liner.
106.2 | Regrade and Reslope Waste Rock Dumps (upper surfaces) | Faro WRDs and Pit | Reduce infiltration in the plateaued upper surface of the dumps. | SW, GW, and geochemical modelling are not well integrated. IPR provided recommendations for review; enhanced modelling is underway to estimate the effectiveness of remediation over time and the application of adaptive management principals. | Update/integrate previous modelling (hydrology, water balance, and geochemical). Develop surface water management plan during and after construction. | Geotechnical characteristics of waste rock and soils. | Evaluate foundation conditions along perimeter for sediment control structures (dams and retention ponds and diversion channels). | Excavated seven test pits. (Report Link)
|  |  | Construct geotechnically stable landforms. | Location or application of wet landscape features, such as retention ponds/wetlands to retain flood flows and reduce the hydrograph peakiness. | Optimize regrading/resloping plan. |  | Dig test pits within the waste rock slope perimeter to a depth of the potential cut to assess physical characteristics of waste rock including gradation and to assess geochemical kinetics/leachability).
|  |  | Alternative - Consider infiltration galleries to manage 100-year flood conditions. | Destination of surface water runoff from waste rock plateau. | Establish cut/fill volumes for/from outside sources (that is, need for calc-silicate waste rock for drainage material on tailings; addition of material from Haul Road).
|  |  |  | Implications of using infiltration galleries to minimize runoff/sediment erosion. | Develop sediment control plan.
Assess borrow materials (till).
Assess potential locations for large scale waste rock processing facilities to generate appropriately graded borrow.
106.3 | Regrade and Reslope Waste Rock Dumps (perimeter slopes) | Faro WRDs and Pit | Construct geotechnically stable landforms. | SW, GW, and geochemical modelling are not well integrated. IPR provided recommendations for review; enhanced modelling in underway to estimate the effectiveness of remediation over time and the application of adaptive management principals. | Update/integrate previous modelling (hydrology, water balance, and geochemical). | Geotechnical and geochemical characteristics of waste rock that will be exposed as a result of regrading/resloping. | Dig test pits and sample along the toe of waste rock dump slope to evaluate geotechnical and geochemical conditions for potential to supply borrow. | Completed geological reconnaissance (Report Link) |  | None
|  |  | Minimize erosion of fine grained sediment. Provide robust means to convey storm flows down slopes (failure modes and effects analysis). | Destination of surface water runoff from waste rock plateau. | Develop surface water management plan during and after construction. | Volume of foundation materials at toe of waste rock dumps suitable for borrow. | Evaluate foundation conditions for sediment control structures (dams and retention ponds) and diversion channels. | Excavated seven test pits (Report Link)
|  |  | Alternative: Where possible, use “hybrid” option; combination of talus slopes and revegetated benches. Selective use of infiltration galleries will reduce the potential for erosion (for example, talus slopes). | Implications of using infiltration galleries to minimize runoff/sediment erosion. | Develop sediment control plan. | Locations of suitable areas for infiltration galleries to help control surface runoff and erosion. | Conduct reconnaissance to assess surface water management options. | Drilled and excavated approximately 21 other locations around toe of WRD slopes under other investigations (2015 NFRC Geotech Investigation), (CH2M March 2015j), (107.4 Investigation), (107.5 Investigation)
[5 empty] | Develop final landform design under the following considerations: | Ecosystem services analysis required to assess options for North Fork Rose Creek (downstream of rock drain) undisturbed reaches, with respect to resloping and cover on adjacent waste rock areas and hydrology of area depending on tailings removal or capping.
Optimizes regrading/resloping;
Defines final footprint of the waste rock dumps (for example, shift waste rock laterally to areas with a larger buffer zone between the toe of the slope and downgradient water bodies);
Considers Rose Creek stream realignment;
Incorporates existing talus slopes for energy dissipations, and;
Flattening the waste rock slope upgradient from the S-Wells will cover the seepage interception system and result in the covering Rose Creek (stream realignment considerations). Pulling the material up will be more expensive and technically challenging.
Establish cut/fill volumes for/from outside sources (for example, need for calc-silicate waste rock for drainage material on tailings; addition of material from Haul Road, etc.).
Assess the potential for using foundation material as borrow in areas where till or organics will be covered by resloped waste pile.
Under alternative design option, evaluate “hybrid” closure resloping and regrading geometries – combination of leaving existing talus slopes, adding benches, and selective revegetation. Determine if hybrid combination of talus slopes and benches is suitable for revegetation and if stakeholders will approve.
Assess impacts of expanding beyond area covered by current EA (for example, lateral shift of some waste rock material to the SW of the S-Wells may result in disturbance outside of current EA footprint).
106.4 | Cover and Revegetate East Sulphide Waste | Faro WRDs and Pit | Consolidate the smaller piles of highly reactive material into the larger dumps where practical, reduce infiltration, and revegetate. | Effectiveness, reliability, and performance of covers in short term and long term for stability, erosion protection, and reduction of infiltration. Very high-cost item for project. | Infiltration modelling, impacts to GW and SW. Assess design criteria in the C&R Plan, Table 4.9. | Need to review RLU planning basis to determine cover volume and suitability. | Evaluate cover requirements. Confirm availability of suitable cover materials (volume and grain size). | Completed vegetation and soil survey (CH2M March 2015z), (CH2M February 2015c)
|  |  | Alternative – Subaqueous deposition of sulphidic wastes in Faro Pit. |  | Cover optimization and identification of source material; optimization of short- and long-term vegetative performance is critical. | Existing site water balance versus water balance after final grading needs to be evaluated to determine surface and GW impacts. | Visually inspect sulphidic rock to determine requirements for levelling/protective base layer under the very low infiltration synthetic membrane | Advanced boring through east sulphide cell and completed with GW monitoring well, thermistor and pore gas ports (CH2M March 2015b)
[5 empty] | Consideration of wildlife requirements (habitat and/or exclusion) in cover vegetation design. |  | Delineate volumes for relocation for alternative design proposal.
106.5 | Cover and Revegetate Main and Intermediate Sulphide Cells | Faro WRDs and Pit | Maximize ET potential of the cover. | Proposed reclamation surface is rough and loose; however, the field investigation concluded that the microtopography is sub-optimal for plateau areas as it promotes ponding and infiltration. | Cover optimization and identification of source material; optimization of short- and long-term vegetative performance is critical. | Same as Activity Code 106.1. | Same as Activity Code 106.1.
|  |  | Minimize energy of runoff from covers and surrounding areas to limit erosion of fine grained sediment. |  | Consideration of wildlife requirements (habitat and/or exclusion) in cover vegetation design.
106.6 | Place Cover on Remaining Waste Rock and Revegetate | Faro WRDs and Pit | Reduce infiltration in the dumps; construct geotechnically stable landforms; maximize diversion of uncontaminated run off from covers and surrounding areas; and revegetate disturbed areas on all dump areas. | Additional technical considerations addressed under 106.1A/B. | Steep (2:1) slopes for waste rock are not feasible from a cover and revegetation perspective. Loose cover material faces three issues: how to apply it, how to keep it from working down into the waste rock surface and no longer providing a vegetation support, and how to prevent it from being eroded by surface water. | Review RLU planning basis with Waste Pile and Tailings Discipline Team to provide basis for access, cover material type and available volume. | Field work covered under Activity Code 106.1
|  |  | Revegetation information for steep waste rock areas with loose cover is not provided; feasibility of applying covers to 2:1 slopes and revegetating needs to be considered to confirm that this is a viable RLU. |  | Cover optimization and identification of source material; optimization of short- and long-term vegetative performance is critical. | Existing site water balance vs. water balance after final grading needs to be evaluated to determine surface and GW impacts.
Consideration of wildlife requirements (habitat and/or exclusion) in cover vegetation design.
106.7 | Cover and Revegetate Mt. Mungly (E&W) and Southwest Pit Wall Dump | Faro WRDs and Pit | Apply low-infiltration covers to the Mt. Mungly waste dumps (East and West) and the Southwest Pit Wall Dump. |  | Cover optimization. Detailed regrading plans, Reclamation Landform Unit (RLU) specifications. | Need to review RLU planning basis with Waste Pile and Tailings Discipline Team. | Evaluate cover performance requirements. Confirm availability of suitable cover materials (volume and grain size). | Completed vegetation and soil survey (CH2M March 2015z), (CH2M February 2015c) |  | Geotechnical and geochemical characteristics of Mt. Mungly and SE Pit Wall Dump waste rock
|  |  | Revegetation information for steep waste rock areas with loose cover is not provided; feasibility of applying covers to 2:1 slopes and revegetating needs to be considered to confirm that this is a viable RLU. |  | Steep (2:1) slopes for waste rock are not workable from a cover and revegetation perspective. Loose cover material faces three issues: how to apply it, how to keep it from working down into the waste rock surface and no longer providing a vegetation support, and how to keep it from being eroded by surface water. | Existing site water balance vs. water balance after final grading needs to be evaluated to determine surface and GW impacts. | Excavate test pits, conduct geotechnical and geochemical evaluation: evaluate waste rock gradation.
Cover optimization and identification of source material; optimization of short- and long-term vegetative performance is critical.
Consideration of wildlife requirements (habitat and/or exclusion) in cover vegetation design.
107 - Faro Groundwater
107.1 | Upgrade North Fork Rose Creek | East Side ARD Collection and Diversions | Protect North Fork of Rose Creek from potential sources of contamination. Divert from Faro waste rock piles. Increase capacity to 1:500 year event at 81 m3/sec and manage the PMF 384 m3/sec. Remove the NFRD and build new channel. | Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. Soil and permafrost conditions, geotechnical conditions, seepage rates, channel stability, flow, seepage, seepage management, contaminate source loading. Location of diversion relative to toe of waste piles, stability of piles, and effects on diversion. Uncertain as to final alignment. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. | Hydrologic and hydraulic model to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results; detailed cross section survey data, bed and bank materials characterizations. Soils data (geotech) ice data, flow data, and water profile data (surface). Additional flow monitoring data collection at Station “R7” for model calibration and validation. | Evaluate geologic conditions depth to and geometry of bedrock surface in vicinity of proposed cut-off wall and; soil and permafrost conditions along alignment of new channel on the south side of existing NFRC. | Completed surface geophysical transects across NFRC (CH2M March 2014m),(2015 NFRC Report Link) | Design concept changed in ??. Under new NFRC remediation concept the existing NFRC becomes a seepage collection channel. | None
|  |  | Divert from Faro waste rock piles. Increase capacity. | NFRC noted to be prone to rockfall hazards (Section 4.6.2) but this is not planned for in consideration of moving the creek channel and replacement of floodplain areas. (Source: C&R Plan Chapter 4). In addition, aquatic assessment recommends more structures and features for fish habitat and reclamation of riparian areas and banks, but there are no details in the Source: C&R Plan. (Chapter 8). | Some site specific hydraulic modelling required to provide water surface profiles. | Integrated planning required for the NFRC channel and valley area (including riparian and ponded areas), in conjunction with activities to reslope waste rock pile and remove all or part of haul road; need to weigh against possible cut-off wall construction. | Monitor GW and SW quality. | Completed GW/SW interaction potentiomanometer study upstream of rock drain (CH2M March 2014m), (CH2M March 2015i)
|  |  | Design to preliminary design level of detail. | The inclusion of Faro diversion as upstream tributary is not yet decided. | Review design criteria, PMP, PMF and water quality estimates. Channel design needs to provide low infiltration, long-term performance and a floodplain to handle the PMF. Establish final alignment and floodplain characteristics. | Ecosystem Services analysis required to quantify creek protection options for cut-off wall, creek liner, remove rock drain, and realign creek. | Surveys for detailed cross section data, potential bed and bank materials characterizations, and flood plain cover characterization. | Completed geological reconnaissance / bed and bank material characterization (CH2M March 2015i)
|  |  | Requires final selection of preferred alternative through an alternatives assessment. |  | Geotechnical, water quality, channel stability, seepage, hydrology, hydraulics modelling refinements, design storm flows, icing, soil cover, and re-vegetation options. | Impact of rerouting creek beds to reduce contaminated GW impact or construction of slurry walls that may cause daylighting of GW. | Collect soils data (geotech) ice data, flow data, and water profile data (surface elevations). | Completed cross section surveys (CH2M March 2015i), (2015 Report Link)
[5 empty] | Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. |  | Collect additional flow monitoring data at Station R7 for model calibration and validation. | Completed terrain hazard assessment (Report Link):
[5 empty] | Rockfall issues appear to be a natural hazard in headwaters area and a construction hazard when working with the Faro Mine waste rock piles. If Rose Creek is planned to be reconstructed with a liner, then consideration needs to be given to where it is best located in the valley to protect it from rock fall and seepage/GW from the waste rock slopes. Riparian areas in the floodplain need to be an integral part of channel planning. |  |  | GW/SW interaction study downstream of rock drain (Report Link)
[5 empty] | Permafrost impacts on design considerations. |  |  | Geotechnical Investigation - Drilling, piezometer and thermistor installation, test pitting, surface geophysical surveys, ground temperature monitoring (Report Link)
[5 empty] | Potential Faro diversion as tributary input depends on outcome of Faro diversion evaluations. |  |  | Groundwater Investigation - Aquifer testing, Slug testing, Water Level monitoring, Groundwater sampling (Report Link)
Completed rapid geomorphic assessment (2015 Report Link)
Completed tracer dilution study, cross section surveys (2015 Report Link)
107.2 | North Fork Rose Creek Cut-off Wall | East Side ARD Collection and Diversions | Protect NFRC from contamination. Construct cut-off wall and isolate creek from GW interception. | Location for placing wall; effectiveness, requirements for pumping (volume, duration, construction materials, and timing for pumping, and automation). Potential for bypassing cutoff and contaminating GW. | Optimize location for accessibility, short term, and long term performance; evaluate construction materials; reduce cost; and maximize GW cutoff effectiveness. | Hydrologic and hydraulic modeling to provide influent SW flow data and elevations. | Conduct geotechnical and geohydrologic investigations to determine location for wall. | None | Design concept for NFRC refined in 2014 / 2015. Existing creek channel to become a seepage collection channel.
[6 empty] | Integration of SW and GW modelling approaches and results. | Collect soils data (geotech), ice data, flow data, and water profile data (surface elevations).
[6 empty] | Detailed cross section survey data and bed and bank material characterizations. | Conduct geophysical seismic survey in proposed cut-off wall area with confirmation borings.
Soils data (geotechnical), ice data, flow data, and water profile data (surface elevations).
Bedrock contact delineation.
107.3 | Relocate Zone II Outwash Material to Intermediate Sulphide Cell | East Side ARD Collection and Diversions | Remove outwash material to Intermediate Sulphide Cell to reduce contaminant loading to NFRC and underlying aquifer; and construct access roads. | Stability of upgradient waste rock slope under current condition and during materials relocation. | Assessment of volumes of Zone II Outwash materials and underlying impacted soils to relocate. | Volume of materials, including underlying impacted soils to relocate. | Install borings/trenches to delineate volume of Zone II Outwash materials and underlying impacted soils. | Excavated four test pits (3 in outwash, 1 in upgradient Waste Rock slope) CH2M March 2015j | Design concept for NFRC refined in 2014 / 2015. Existing creek channel to become a seepage collection channel, negating requirement for remediation of Zone II Outwash sediments. | None – Design concept changed
|  |  | Alternative - Cover in place. | Volume depth of affected materials that will need to be relocated. | Geotechnical assessment of upgradient waste rock slope under current conditions and during relocation activities. | Stability of upgradient waste rock slope | Conduct analyses of underlying soils to estimate depth of impacted soils. | Drill, install and develop 8 monitoring wells (Report Link):
[5 empty] | Final landform design that incorporates upgradient waste rock dump. | Leaching characteristics of Zone II Outwash Material | Perform geotechnical assessment of upgradient waste rock slope, conduct sampling to support geotechnical, geochemical, and infiltration modelling.
Alternatives Assessment - Relocate outwash material versus cover in place.
107.4 | Install Zone II Outwash Collection System | East Side ARD Collection and Diversions | Intercept seepage from the Zone II Outwash Area; reduce contaminant loading to the NFRC and underlying aquifer. | Configuration of bedrock surface. | Develop three-dimensional numerical GW flow model. Investigate various alternative configurations of SIS design to optimize efficiency and minimize cost. Define bedrock surface. Define distribution of aquifer properties. Determine three dimensional extent of GW contamination. Quantify site water budget. Define degree and pattern of surface water/groundwater interaction. | Spatial distribution of alluvial aquifer thickness in outwash zone. | Install new wells along proposed line of interception system to delineate alluvial aquifer thickness. | •Drill, install and develop 8 monitoring wells. (Report Link) | Design concept for NFRC refined in 2014 / 2015. Existing creek channel to become a seepage collection channel, negating requirement for design of interception systems at Zone II Outwash. | None – Design concept changed
|  |  |  | Distribution of aquifer properties. |  | Spatial distribution of bedrock topography in outwash zone. | Conduct aquifer testing on new wells using existing wells in alluvium as additional monitoring points. | •Packer testing in bedrock. (Report Link)
|  |  |  | Magnitude and distribution of surface water/groundwater interaction between the NFRC and the underlying alluvial aquifer. |  | Hydraulic properties of the backfill materials in Zone II Pit. | Conduct geophysical survey along SIS alignment to refine bedrock topography. (Complete) | •Stream stage monitoring. (Report Link)
|  |  |  | Extent of GW contamination in the deeper portions of the aquifer. Response of aquifer system to GW pumping. |  | Spatial and temporal extent of GW/SW interaction between the alluvial aquifer and the NFRC. | Install additional bedrock monitoring wells to refine flow direction in bedrock aquifer and delineate bedrock aquifer properties. Perform aquifer testing in bedrock monitoring wells to improve understanding of bedrock aquifer properties. | •Complete surface geophysical transect. (Report Link)
|  |  |  | Magnitude of site water budget components. Geochemical conditions within the aquifer and potential for well fouling. |  | Horizontal GW flow patterns in the bedrock aquifer. | Perform depth-specific GW sampling during drilling of bedrock wells to refine interpretation of the distribution of contamination within the aquifer.
|  |  |  | Number of wells required for effective interception. |  | Three-dimensional distribution of contaminants near the proposed GW interception system.
|  |  |  | Need for permeable trench and cut-off walls. |  | Extent of hydraulic connection between the Zone II Pit and the outwash area, and the GW flux originating in the vicinity of the pit.
Number and spacing of extraction wells; permeable trench location.
Estimate GW flow and contaminant mass loading from extraction system (average and peak).
107.5 | Install S-wells GW Collection System | East Side ARD Collection and Diversions | Upgrade and complete existing GW SIS. Provide for permanent pumps, piping, power, and access. | Configuration of bedrock surface. | Develop three-dimensional numerical GW flow model. Investigate various alternative configurations of SIS design to optimize efficiency and minimize cost. | Alluvial aquifer thickness and the hydraulic properties of the alluvial and bedrock aquifers north of the SIS. | Perform aquifer test using the existing deep extraction well as pumping wells and other existing wells in the vicinity as monitoring wells to quantify the hydraulic properties of the weathered bedrock aquifer near the SIS. | •Drill, install and develop 6 monitoring wells (Report Link) | Design concept for NFRC refined in 2014 / 2015. Existing creek channel to become a seepage collection channel, negating requirement for design of interception systems at S-Wells SIS. | None – Design concept changed
|  |  |  | Distribution of aquifer properties. |  | Aquifer properties of the deep weathered bedrock aquifer in the vicinity of the existing SIS. | Install additional alluvial monitoring well near well S3 and perform aquifer testing using well S3 as a monitoring well to estimate alluvial aquifer properties between the SIS and the NFRC. | •Install and monitor 16 streambed piezometers for GW/SW interaction study (Report Link)
|  |  |  | Response of aquifer system to GW pumping. |  | Alluvial aquifer properties between existing SIS and the NFRC. | Perform a seismic refraction survey to delineate bedrock topography near the existing SIS. Extend to seismic survey conducted in 2012 at rock drain. | •Complete one seismic refraction geophysics line (Report Link)
|  |  |  | Magnitude of site water budget components. |  | Bedrock topography in the vicinity of the existing SIS. | Perform potentiomanometer study including instrumentation along the NFRC to improve characterization of stream/aquifer interaction.
|  |  |  | Geochemical conditions within the aquifer and potential for well fouling. Number of wells required for effective interception. |  | Spatial and temporal extent of GW/SW interaction between the alluvial aquifer and the NFRC. | Select monitoring well pair/stream gauge locations using these results. These monitoring wells will also monitor for possible by-pass of contamination through the SIS and subsequent transport to NFRC.
Need for cut-off wall.
107.6 | S-Wells GW Collection (part of ADM to capture future concentrated zones near source) | East Side ARD Collection and Diversions | Shallow and deep aquifer interception systems were constructed in 2009. Final component is installation of cut-off wall if monitoring indicates shallow aquifer sump and deep aquifer pumping wells do not provide sufficient capture. | Evaluation of adequacy of shallow and deep aquifer pumping wells to provide sufficient capture of contaminated GW. | Three-dimensional GW flow model; incorporate most recent operational data to estimate effectiveness of existing SIS and system enhancements. | GW seepage will be addressed at this site by the activities recommended under Activity Code 107.4. | No additional field work required. | None | Design concept for NFRC refined in 2014 / 2015. Existing creek channel to become a seepage collection channel, negating requirement for design of interception systems at S-Wells SIS. | None – Design concept changed
|  |  |  | Method of installation of the cut-off wall; location of bedrock, extent of wall required, and requirements for additional wells. | Conduct optimization study to maximize the capture of contaminated GW flow and cost.
108 - Faro Miscellaneous
108.1 | Reclaim Unnecessary Roads | Sitewide | Prevent long-term erosion and breach crossings to prevent blockage. | Road areas will require specific reclamation plans in keeping with required surface drainage plans and surrounding reclamation prescriptions. | Assessment needs to be made about culverts and crossings to be breached and resloped, and drainages restored. Previous closure prescription is to scarify road surfaces and revegetate, but no information available on quality of road construction materials. | Require assessment of road material quality. | Site reconnaissance, hold discussions with Care and Maintenance and YG to identify. | None
Require assessment for basis of design of road reclamation – revegetation or swale/channel formation as part of surface drainage plan.
108.2 | Reclaim Zone II Outwash Area | Faro WRDs and Pit | Cover and revegetate Zone II Outwash Area after installation of collection system to provide stable creek floodplain. | Configuration of outwash collection system and final placement of NFRC after rock drain is removed will dictate the cover and revegetation plan surface. | Once location of reconfigured NFRC is planned; need to assess loss of current vegetation cover and what can be salvaged and moved to other locations for soil and vegetation. | Assess current vegetation cover. | Site reconnaissance/soil and survey | Conduct sitewide Vegetation and Soil survey (CH2M March 2015z), (CH2M February 2015c)
|  |  | Alternative design: Cap in place. | Revegetation of this area is not currently considered within the reclamation plan but needs to be tailored to location of NFRC (if moved) and to existing valley vegetation. | Area may be covered by waste rock if NFRC is moved. | Assess current soil type and quality.
Locate stockpiling or direct placement areas.
Confirm availability of suitable cover material.
Confirm availability of suitable riparian plant species.
108.3 | Decontaminate and Demolish Buildings | Mill and ETA | The existing mill, administrative buildings, and surrounding infrastructure will be removed to mitigate potential long-term safety hazards. | Sampling for ACM and other designated substances may not be substantive enough to be useful for decommissioning purposes. Areas around buildings that are not tested may need to be treated as designated or ACM substances. | Site visit to identify items that might have been missed. Follow up sampling may be required. | Obtain, review, and catalogue site and building as-built plans and other construction documentation. | Conduct site reconnaissance and utility survey. | Survey and inventory of water conveyance infrastructure (Report Link) |  | Building and waste materials quantification.
|  |  | Extent of contamination of surfaces through plant is unknown. | Extent of process materials (rock and others) in pipelines, equipment, vessels, and holding areas is not extensively documented. Requirement to remove extensive volumes of this material will complicate decommissioning. | Address safety concerns with any of the onsite buildings and to clear areas for safe access to complete other assessments that may be required. | Determine if sufficient sampling has been performed to mitigate costs for abatement of materials assumed to contain designated substances due to lack of information to the contrary. |  | Compiled and scanned available as-built plans and construction documentation |  | Salvage assessment and evaluation of transportation cost to ship scrap to markets.
|  |  |  | Site plans, surveys, Material Safety Data Sheets, and other information involving plant construction and makeup are not currently available. | Perform site utility surveys. Use ground penetrating radar (GPR) if necessary for decommissioning and to understand H&S risks during work. | Building and waste materials quantification. |  |  |  | Utility and site surveys.
|  |  |  | A review of laydown areas in close proximity to the plant (boneyards) has not been completed. Implications and cost for decommissioning has not been evaluated. | Determine and obtain permits required to perform demolition. | Waste disposal recommendations.
|  |  |  | Options to revegetate and reclaim the site as part of the natural landscape after decommissioning need to be evaluated. | Analyze existing structures (plans if available) to determine less costly design for removal, decontamination, transport, and recycling or placement in a landfill. | Salvage assessment and evaluation of transportation cost to ship scrap to markets.
|  |  |  | Site survey required. | Hold discussions with Care and Maintenance staff to identify potential underground structures. | Utility and site surveys.
[5 empty] | Review and catalogue mill drawings. | Confirm availability of suitable cover material.
Assess suitable revegetation cover and cover microtopography.
Extent of contamination is not certain.
Appropriate cover type and revegetation plan needs to be assessed for this area for long-term liability management.
Determine if portions of foundations may be covered and revegetated. Determine available cover material types and volumes and appropriate revegetation plan.
108.4 | Relocate Contaminated Soil from Mill Site Area and Cover (rudimentary) | Mill and ETA | Remove hazardous materials and contaminated soil from Plant Site Area. Regrade Mill Area, cover, and revegetate. | Characterize contaminants, identify contamination levels, determine volume of material excavation; volume and source of backfill. | Determine appropriate location for an onsite landfarm for hydrocarbon contaminant treatment. | Extent of soil metals and hydrocarbon contamination and acid generating soils (lateral and vertical) near the Vehicle Maintenance Complex, Emergency Generator Area, Mill Diesel Tank, and Waste Oil Tank. | Conduct GPR surveys, drill soil borings or excavate test pits near the Vehicle Maintenance Complex, the Emergency Generator Area, the Mill Diesel Tank, and the Waste Oil Tank. | None
|  |  |  | Concentration threshold criteria for soil removal. | Specific revegetation prescription required, especially because this area is a candidate for an ET cover. | GW flow directions. | Conduct analyses for hydrocarbon, metal, polyaromatic hydrocarbons (PAH), and acid-neutralization potential (ANP) soil samples.
[5 empty] | Hold discussions with Care and Maintenance staff to identify potential underground structures. | Extent of associated GW contamination.
Assess suitable cover material quality.
Assess potential for ET vegetation cover, or appropriate revegetation prescription.
108.5 | Relocate Contaminated Soil from Faro Lube Shack and Tank Farm Area and Cover (rudimentary) | Faro WRDs and Pit | Remove hazardous materials and contaminated soil from the Plant Site Area. Regrade Mill Area, cover, and revegetate. | Characterize contaminant levels, determine volume of material excavation; volume and source of backfill. | Determine appropriate location for onsite landfarm for hydrocarbon contaminant treatment. | Determine permitting requirements | Conduct GPR surveys, drill soil borings or excavate test pits near the Vehicle Maintenance Complex, the Emergency Generator Area, the Mill Diesel Tank, and the Waste Oil Tank. | Excavated two test pits (Report Link) |  | Vertical extent of contamination
|  |  |  | Concentration threshold criteria for soil removal. | Specific revegetation prescription required, especially because this area is a candidate for an ET cover. | Extent of soil hydrocarbon contamination (lateral and vertical) near the Lube Shack and Tank Farm Area. | Conduct analyses for hydrocarbon, metal, polyaromatic hydrocarbons (PAH), and acid-neutralization potential (ANP) soil samples.
[5 empty] | Hold discussions with Care and Maintenance staff to identify potential underground structures. | GW flow directions.
Extent of associated GW contamination.
Assess suitable cover material quality.
Assess potential for ET vegetation cover, or appropriate revegetation prescription.
Tailings Area (Activity Code 200)
201- Dams
201.1 | Dewater Intermediate Tailings Area | RCTA | Current concept is for a dry revegetated surface on top of a cover over all the tailings surfaces. | Geochemical and geotechnical characteristics of tailings slimes and sediments. | Evaluation of tailings consolidation and the need for the waste rock trafficability layer to act as a drainage layer. | Rheologic parameters of tailings to evaluate pumpability and thickening characteristic. Geotechnical information for the area within 500m of the Intermediate Dam. | Conduct geotechnical investigations : | Drill and install monitoring well in north portion of Intermediate Tailings Impoundment (Report Link) |  | Bathymetric survey with subbottom geophysics
|  |  | Evaluate potential for backfilling the Intermediate Pond with coarse granular (for example, processed waste rock) or dewatered (dry) tailings prior to installing cover and revegetation of cover. | Volume of sediment. | Evaluation of the depth of freezing within the fine zone of the Intermediate Tailings Area and the implications for trafficability. | Geotechnical parameters (for example, undrained shear strength, depth of tailings, and porewater pressure). | Install piezocones (with ball penetrometers) or in-situ vane shear testing) extending through the Intermediate Tailings. | Same field work as tailings cover task:
|  |  | Revegetated surface and surface runoff will be isolated from tailings porewater. | Dewatering characteristics. | Time for consolidation to occur. Assess need for accelerated consolidation (for example, wick drains or similar). | Consolidation characteristics of tailings to enable prediction of tailings porewater expelled, rate of consolidation, and total depth of consolidation (to model drainage above tailings). | Conduct bathymetric survey with subbottom geophysics in the ID pond. | Drill 5 borings and install thermistor ports (CH2M March 2015m), (CH2M March 2015o):
|  |  |  | Sediment control and method of removal. |  | Seepage/water balance to determine design requirements of the backfilled pond area adjacent to the Intermediate Dam and options for actively managing tailings seepage by sump dewatering. | Install vibrocores to determine sludge thickness and obtain sludge samples. | advance 12 CPT soundings
[6 empty] | Possible requirement for processing waste rock for the trafficability layer to enable function as a drainage layer. | Conduct laboratory testing; grain size, Atterberg limits, shear strength, consolidation. | completed ground temperature monitoring in Spring, Fall, Winter (CH2M March 2015b), (Pending 2015 SW-015 report)
[6 empty] | Evaluation of freezing profile. |  | Advanced 6 CPT soundings in intermediate dam pond (Report Pending):
201.2 | Dewater Cross-valley Dam Pond | RCTA | Dewater the pond by pumping the water to the Faro Pit. Current concept is to retain the Cross Valley Dam, but to keep the Cross Valley Pond drained. Remove sludge and sediments to (1) facilitate construction of the Intermediate Tailings Dam raise and (2) to create a surface that can be revegetated. Collections systems to be installed downstream of the Intermediate Dam within the CVP area. | Chemical and physical characteristics of sludge and sediments; volume of sediment; dewatering characteristics; method for controlling surface and groundwater during excavation. | Methods of dewatering, treatment as required, and discharge of treated water. | Volume of sludge and sediment to be removed at Cross Valley Dam Pond. [Previous investigation by Ecometrix (Report titled Investigation on Zinc Controls at the Cross Valley Pond – Faro Mine Complex dated October 2010 was to investigate zinc concentrations in pond water, sludge and porewater in the CVP. Chemical testing was performed and lime demand estimated. The study did not characterize the volumes of sludge] | Survey sludge and sediment to estimate volume to be removed at Cross Valley Dam Pond: | Advance 6 CPT soundings in CVP (Report Pending) |  | Bathymetric survey with subbottom geophysics
|  |  |  | Sediment control and method of removal. | Methods of sludge removal, stabilization/drying of sludge, transportation of sludge, and sludge disposal at the existing sludge pond north of tailings impoundment. | Conduct geochemical and treatability testing as necessary [Ecometrix report has some information]. Rheologic parameters of sediment to evaluate pumpability and thickening characteristics) | Conduct bathymetric survey with subbottom geophysics in the Polishing Pond. | Advance 6 vibrocore borings in CVP (Report Pending)
[5 empty] | Stability of Intermediate Tailings Dam (seepage and piping, and drawdown slope stability) after dewatering of the Cross Valley Impoundment. |  | Install vibrocores to determine sludge thickness and obtain sludge samples
Conduct geotechnical, geochemical and treatability testing.
201.3 | Retain Cross-valley Dam | RCTA | To keep Cross Valley Pond as emergency storage facility and to capture any potential contaminated seep water. | Removal of Cross Valley Dam needs to be further evaluated. IRP recommends Cross Valley Pond be retained. Requires evaluation of Cross Valley Dam stability and spillway requirements (hydrology, hydraulics, and foundation conditions. Location and foundation conditions for downstream SIS will need evaluation. | Identify operational failure scenarios in which the Cross-valley Pond would be used if retained. Evaluate the potential effectiveness of treatment that would be provided under those scenarios. | Foundation conditions for new PMF Spillway and low level outlet. | Conduct investigations for spillway area (right abutment): | Excavate test pit in Cross Valley Dam Spillway (CH2M January 2015b) | Some discussion of bypass spillway, directing overflow from Intermediate pond around the CVP to discharge to Rose Creek.
|  |  | To allow flood water to egress from the Intermediate Dam spillway into the Cross Valley Pond, then exit through a new PMF spillway at the Cross Valley dam, and then enter the Rose Creek downstream from the Cross Valley Dam. |  | Flood routing (hydraulics) study: | Hydrologic and hydraulic model to provide influent SW flow data and elevations as well as routing and velocity data for spillway to Rose Creek. | Survey seismic lines (refraction survey).
[5 empty] | Route flow through pond and spillway at right abutment of Cross Valley Dam. |  | Install shallow borings to map depth of bedrock and diamond drill borings for rock coring. | Complete surface geophysical survey at Cross Valley Dam Spillway (Pending ID Spillway drilling report)
[5 empty] | Flood routing/dissipation in area downstream from Cross Valley Dam before floodwater discharges into Rose Creek |  | Conduct packer testing to determine rock permeability.
[5 empty] | If Cross Valley Dam is retained, dam stability evaluations: |  | Note that additional foundation investigation for the Cross Valley Dam, including sampling and laboratory testing to determine liquefied soil strengths for seismic analyses would be required if it is determined that the polishing pond will retain water for extended periods of time.
Seepage and slope stability
Liquefaction potential and mitigation
Deformation analyses (seismic)
Slope protection
Geotechnical instrumentation
201.4 | Raise Intermediate Dam (ID) | RCTA | To pass – without overtopping – floods larger than the 500-year return event and up to the Probable Maximum Flood (PMF) and route through new spillway. | Dam stability during PMF (flooding) and maximum credible earthquake (MCE) (seismic) events; requirements to modify internal drain and filters (will no longer have Cross Valley Dam water against downstream slope); liquefaction potential and seismic slope stability. Need to finalize/verify the amount of dam raise. | Flood routing (hydraulic) study to determine optimum dam raise in conjunction with spillway configuration and size. | Borrow material sources and borrow material characteristics (dike and dam embankment materials, filter/drain material, slope protection, tailing covers). Assume that Cross Valley Dam will be drained with no tailwater against the downstream slope. | Install borings along RCDC dike toe, depending on amount of raise determined appropriate. | Same field work as tailings cover task: |  | None
|  |  | Consider dam stability and contaminated groundwater collection. |  | Dam stability evaluations: | Tailings permeability for dewatering (assumed to be covered under the Tailings Cover task). | Perform CPTs for tailings cover constructability along the toe of the RCDC dike (see Tailings Cover task). | •Drill 5 borings and install thermistor ports (CH2M March 2015m), (CH2M March 2015o):
|  |  | Based on preliminary hydrologic analyses, an Intermediate Dam raise to El 1052 m (about 2.6m raise) is estimated |  | Seepage and slope stability | Hydrologic and hydraulic model to provide influent SW flow data and elevations as well as routing and velocity data. | Conduct laboratory testing including index, permeability and shear strength testing. | advance 12 CPT soundings (CH2M March 2015m)
[5 empty] | Internal filter and drain system adequacy |  | Investigate borrow material, as necessary. (See Borrow Material Task)
[5 empty] | Liquefaction potential and mitigation |  | Investigate tailings, conduct CPTs, and perform other fieldwork and related laboratory testing (see Tailings Cover task).
[5 empty] | Deformation analyses (static and seismic) |  | Conduct additional geotechnical investigation required, depending on height of dam raise required.
Borrow material considerations
Slope protection
Geotechnical instrumentation
Design of dewatering and excavation requirements for regrading tailings, including contaminated groundwater collection.
201.5 | Construct New Side Channel and Side Channel Dike | RCTA | In 2012, CH2M HILL performed an alternatives evaluation for flood routing of the Rose Creek through the Rose Creek tailings area. The evaluations are documented in the CH2M HILL report titled “Conclusions from Rose Creek Tailings Area Alternatives Evaluation” dated November 2012. This report details the evaluation of three different alternatives to route flood flows through the RCTA, and the risk analyses that were performed to form the basis for selecting a preferred alternative. The preferred alternative entailed the use of a single, large, armoured channel (the side channel) located immediately adjacent (north) of the Rose Creek Diversion (RCD) into which flood flows greater than the 500-year flood will be channeled. Flood flows in the side channel would then be routed through a new PMF Spillway at the right abutment of the Intermediate Dam. | Foundation conditions for new side channel dike. Thickness and nature of tailings under the dike as well as the side channel bottom footprint. | Side channel dike stability evaluations: | Subsurface information (foundation conditions) along the RCDC dike. | Investigate tailings, conduct CPTs, and perform other fieldwork and related laboratory testing (see Tailings Cover task). | Same field work as tailings cover task:
|  |  |  | Stability and integrity of the existing Rose Creek Diversion dike | Seepage and slope stability |  | Install borings and/or CPTs along new side channel alignment | Excavate seven test pits along crest of ID and 3 test pits in ID spillway (CH2M March 2014m)
[5 empty] | Internal filter and drain system adequacy |  | Conduct laboratory testing including index, permeability and shear strength testing. | Drill 5 borings and install thermistor ports (CH2M March 2015m), (CH2M March 2015o):
[5 empty] | Liquefaction potential and mitigation |  | Investigate borrow material, as necessary. | advance 12 CPT soundings (CH2M March 2015m)
Deformation analyses (static and seismic)
Borrow material considerations
Slope protection
Geotechnical instrumentation
Design of dewatering and excavation requirements for tailings below the side channel, or means for stabilizing/confining it in place.
201.6 | Construct Intermediate Dam Spillway | RCTA | Route the peak flood flows large enough to erode the fuse plug without overtopping the Intermediate Tailings Dam. Construct new spillway in bedrock at the north abutment of Intermediate Tailings Dam. | Optimize dam raise with spillway design (size, location, invert, overflow length, and location of tailings. | Flood routing (hydraulics) study: | Subsurface conditions for spillway: | Conduct additional geotechnical investigation required, depending on final spillway elevation and routing. | Excavate 3 test pits in ID spillway (CH2M March 2014m): | Some discussion of bypass spillway, directing overflow from Intermediate pond around the CVP to discharge to Rose Creek.
|  |  | Consider alternative of passing design flood over the top of a hardened embankment. | Design criteria require review. | PMF flood | Rock mass quality | Evaluate spillway on right abutment: | Drill 2 borings into bedrock (CH2M March 2015p)
|  |  | Operational considerations: |  | Flow velocity | Erosion resistance | Survey seismic lines (refraction survey). | Perform packer testing (CH2M March 2015p)
|  |  | SW assumed to be clean (long-term) and gravity drain; SW to be collected initially for monitoring and possible treatment |  | Scour criteria | Permeability (to evaluate uplift and seepage under concrete control spillway structure) | Install shallow borings to map depth of bedrock and diamond drill borings for rock coring. | Complete surface geophysical survey transects (2015 report pending)
|  |  | GW to be collected in waste rock layer underneath till cover and pumped for treatment |  | Incorporate potential for ice flows in flood routing | Subsurface conditions for energy structure/modifications downhill from the spillway. | Conduct packer testing to determine rock permeability. | Drill 5 borings into bedrock, install and develop 2 pumping wells and 3 piezometers (2015 report pending)
[5 empty] | For concrete control structure, perform seepage analyses to evaluate uplift forces and to design underdrain, uplift, or both Flow routing downstream from Intermediate Dam including channelization and erosion protection | Hydrologic and hydraulic model to provide influent SW flow data and elevations as well as routing and velocity data for spillway. PMF handling has been assessed previously and considerable information is available. Flooding information should be incorporated into any new hydraulic models developed. |  | Complete packer testing in bedrock (2015 report pending)
[5 empty] | Potential for winter flows and ice blockages |  |  | Drill 3 borings into bedrock, install and develop piezometers (Bypass drilling investigation report pending)
201.7 | Stabilize Secondary Dam by Densifying Foundations for East Limb Embankment | RCTA | Mitigation against liquefaction and dam instability during MCE. | Most cost-effective seismic mitigation: | Pseudo-static LE analyses to evaluate different stabilization alternatives. | Subsurface information covering the full length (for example, filling the gaps, of the East Limb of Secondary Dam) (existing borings tend to be clustered with gaps greater than 500 m between clusters). | Conduct seismic refraction surveys to determine depth to bedrock and measure shear wave velocities. | Drill and install 3 well pair clusters (Report Link)
|  |  | Also include embankment stability under all other loading conditions and erosion protection during PMF flooding. | Extent of liquefaction and slope instability | Two-dimensional (FLAC2D) dynamic/seismic analyses to more appropriately determine the cyclic shear stresses in the embankments for liquefaction assessments and mitigation design (shortcoming of the previous liquefaction assessment was using SHAKE91 [a one-dimensional analysis] for two-dimensional geometry). | Shear wave velocity (Vs) information. Liquefaction assessments will be more reliable with direct measurement of Vs instead of estimating these values from correlations with SPT blowcounts. | Verify geophysical information by performing downhole shear wave velocity measurements. | Perform downhole and surface geophysics (Report Link)
|  |  |  | Appropriate methods of ground improvement | Use FLAC2D to evaluate seismic deformation to optimize mitigation options. Criteria for acceptable deformations must be established first. |  | Collect SPT samples (N values and fine content)
Perform sieve analysis and index testing, as appropriate.
202 - Tailings Cover
202.1 | Cover Intermediate Tailings Area | RCTA | Prevent direct contact by wildlife with the tailings and minimize contaminated runoff. Current concept is for a dry revegetated surface on top of a cover over complete intermediate tailings surfaces. The Intermediate Pond will be filled with coarse granular (for example, processed waste rock) or dewatered (dry) tailings prior to installing cover and revegetation of cover. | The condition of the surface of the tailings within the tailings area varies by season. These conditions limit when and where equipment can successfully work on the tailings surface. | Determine settlement/differential settlement predictions; determine stability assessments (for example, edge effects during construction); hydrology, energy dissipation features; TEMP/W drainage, slope stability, and settling assessments; design of basal support layer (waste rock or geogrid); manage risks associated with differential settlement especially in area of energy dissipation features. | Hydrologic and hydraulic model to provide influent SW flow data and elevations as well as routing and velocity data in relation to swales. Erosive and conveyance characteristics of swales materials and vegetative cover. | Conduct additional geotechnical borings and CPT to characterize tailings profile. | Drill 5 borings and install thermistor ports (CH2M March 2015m), (CH2M March 2015o)
|  |  |  | Behavior of cover surface over long term after adding large fill thickness in pond area. | Determine cover placement method, depth of cover material, suitable surface cover material and microtopography features. Revegetation cover design requires consideration of ET or other cover requirements. | Source of base granular drainage material, filter compatible layer and final cover. Implications of geochemistry (leachability, decomposition of waste rock above tailings). |  | advance 12 CPT soundings (CH2M March 2015m), (CH2M March 2015o)
[6 empty] | Determine if material from NFRD the best source or can “less useful” waste rock be used. |  | completed ground temperature monitoring in Spring, Fall, Winter (CH2M March 2015b), (Pending 2015 SW-015 report)
Thickness of growth media (water balance).
Energy dissipation structure design and risks.
Ultimate contouring of tailings impoundment and the dynamics of any future intermediate pond (emergent vegetation).
Feasibility of sump in WR pore space adjacent to the Intermediate Dam to store tailings porewater covered with till/clay revegetated layer.
202.2 | Place Covers on Original and Secondary Impoundments and Revegetate | RCTA | To prevent direct contact by wildlife and birds with the tailings and to minimize contaminated runoff. | Detailed design of capture and conveyance measures; requirements for accessibility; cover stability; and long-term vegetation stability; differential and total settlement. | Surface hydrology (swales, ditching, and energy dissipation features); GW/SW interaction. | Need to assess mesotopographic and microtopographic features for tailings cover, and assess available cover material volumes and appropriate vegetation plan. | Install CPT probe holes. | None completed
|  |  |  | Current revegetation design includes use of agronomic grass species, out of keeping with revegetation of the contiguous Rose Valley area and may be an issue for further revegetation and development of an ET cover. | Microtopography and mesotopography determination, growth medium characterization in tailings cover material, vegetation type and application method. | Need to assess optimal cover material types in different areas of tailings cover to facilitate drainage of porewater and separation of clean SW from seepage areas. | Conduct instrumented cover placement trials to supplement existing cover trials; large lysimeter; characterize cover materials.
[5 empty] | Integrated assessment of geotechnical and vegetation cover (agronomic or native) issues for the tailings pond is needed to inform cover design. | Lysimeter installation required in dry consolidated and wet unconsolidated (but due to be drained) tailings materials. | Note: discuss with YG, proceeding with cover trial recommended by IPRP.
Cover and revegetation trial required for the tailings surface.
Revegetation plan and evapotranspirative aspect of the cover design.
Energy dissipation structure and implications for revegetation planning.
Microtopography and landforming.
203 - Rose Creek Diversion
203.1 | Upgrade Rose Creek Diversion Upstream from Fuse Plug | RCTA | The Rose Creek Diversion upstream from the fuse plug and downstream from the convergence of the North and South Forks of Rose Creek currently has capacity for the 674 m3/sec PMF based on the cross-sectional area between the Secondary Dam and the hillside. The upgrade is required to stabilize the existing embankments. | Stability of the channel banks need to be addressed. Design of new approximately 400m overflow weir in the location of the existing fuse plug/overflow weir needs to be are discussed in separate activity below and must be considered for design of the RCD upstream of the overflow weir. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. | Additional flow monitoring data collection at stations in place. | Surveys for detailed cross section data, bed and bank materials characterizations. | Install water level transducer at X3A / RCSG-4 (CH2M March 2015n)
|  |  | Perform modifications to pass the PMF through upstream portion of RCDC, including widening and/or deepening of the channel. Provide erosion protection of channel sideslopes and channel bottom. | Rose Creek Diversion Channel needs to increase capacity; stability of the channel banks needs to be addressed. Existing channel carries salmon and is considered a navigable water. Assess changing elevation of channel with respect to tailings and effects on seepage and contamination. | Some site specific hydraulic modelling required to provide water surface profiles. | Rock mass strengths and soil strengths to assess cut slope stability of south slope. | Collect additional flow monitoring data at surface monitoring stations. | Complete 2 cross section surveys (CH2M March 2015n)
|  |  | Design to preliminary design level of detail. | Icing of channel resulting in reduction of flow capacity during high flow events. Assess icing related risks. | Permafrost impacts on design considerations. | Debris flow potential.
|  |  |  | Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. | Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. | Potential for icing.
[5 empty] | Geotechnical, water quality, channel stability, seepage, hydrology, hydraulics modelling refinements, design storm flows, icing, soil cover, and re-vegetation options. | Quarry sources for large angular riprap.
[5 empty] | Existing channel carries salmon and is considered a navigable water. Assess changing elevation of channel with respect to tailings and effects on seepage and contamination. | Infiltration rates for any tributary covers.
[5 empty] | South slope stability: | Cover material in catchment area.
Rock cut slope stability
Assess permafrost issues and potential stability issues
Assess potential for channel blockages due to the follow: (1) debris flows, or south slope slides, (2) icing problems, and (3) minor slope failures (during smaller floods) and vegetation.
203.2 | Construct Erosion Dissipation Structure | RCTA | Construct an erosion dissipation layer on tailings cover downstream from a new overflow weir. Flood water will flow from the erosion dissipation structure into a new side channel that will run parallel and immediately next to the Rose Creek Diversion. | Potential backwater conditions require hydraulic modelling to evaluate whether the flood can pass the lower channel without overtopping the dike or intermediate dam. | Review of current PMP and PMF estimates. Erosion potential, water quality, stability, hydrology, hydraulics, and construction materials (riprap sources). Assessment of the design of the energy dissipation structures and settlement of underlying material. | Hydrologic and hydraulic model to provide influent SW flow data including velocities, erosive forces, and elevations. | Conduct detailed reconnaissance and review of geologic mapping, to assess conditions and settling characteristics. Review of current site conditions through condition survey. | •Geological reconnaissance (CH2M March 2015q)
[6 empty] | Detailed topographic survey data, potential bed and bank material characterizations. | Conduct geotechnical field investigation including borings for area underlying native materials and CPTs in tailings area. Perform CPT in conjunction with the CPT work performed as part of Tailings Cover task.
Flow data, and water profile data (surface elevations).
Foundation strength: natural versus tailings area. Define extent of waste materials (assume it will be removed).
Borrow sources for riprap.
203.3 | North Fork Rock Drain, Create Channel | RCTA | Create channel through rock drain by either (1) installation of a culvert (trenchless installation or by cut and cover), or by breaching the road embankment to create a notch for the channel. | Determine the concept for rock drain [complete rock drain removal vs. creating a channel (notch) through the rock drain vs. installing a large culvert (trenchless installation or cut and cover)]. | Geotechnical, hydrology, and hydraulics for passing flow through new channel section and erosion potential. | Geotechnical data along new alignment, including excavatability, permeability, erosion potential, etc. | Review current site conditions through condition survey. | Surface geophysical surveys across NFRC upstream and downstream of Rock Drain (CH2M March 2014m)
|  |  | To restore the North Fork of Rose Creek and protect from potential sources of contamination. | Large undertaking will remove primary access route from Faro and Vangorda/Grum sites. Key issues are slope stability, maintenance of access, geochemical conditions, sedimentation, and constructability. Effects on wildlife, including resident grayling must be integrated into design. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. | Geochemical properties of Haul Road embankment (rock drain) for use as borrow source at the tailings dam. | Complete detailed cross sections surveys, and bed and bank material characterizations. | Drill 2 borings at downstream toe of Rock Drain (CH2M March 2014m)
|  |  | Restore the North Fork of Rose Creek and protect it from potential sources of contamination. | The extent of effects on fish and fish habitat are unknown. | Fisheries and fish habitat reviews are required to determine the quality and quantity of fish habitat that would be incorporated into design. | Rock drain hydraulic characteristics. | Collect flow data and water profile data (surface elevations) from existing stations. | Perform dye test through the Rock Drain (CH2M March 2014m)
|  |  | Design to preliminary design level of detail. | Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. | Permafrost impacts on design considerations. |  |  | Collect Weekly water elevation surveys at NF1 and NF2 (CH2M March 2014m):
|  |  | (Coordinate with Activity Code 107.1) |  | Re-vegetation requirements. |  |  | Advance boring through Rock Drain (2015 NFRC DBR Report Link):
Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. Rock drain may have some flood attenuation capacity that can be incorporated in hydrological evaluations.
203.4 | Construct New Overflow Weir | RCTA | Replace existing fuse plug/overflow section with a new overflow weir. Weir will be hardened to resist erosion. | Design criteria and functionality of the overflow weir. | Hydrology, hydraulics, erosion potential, and functional parameters associated with the overflow weir. Design of the overflow weir embankment including seepage and slope stability, and erosion protection. | Hydrologic and hydraulic model to provide influent SW flow data and elevations and erosion/load information for the design of the fuse plug. | Review current site conditions through condition survey. | •Advance 2 borings into bedrock (Report Link)
|  |  |  | Length and configuration of overflow weir required. | Hydrology, hydraulics, and erosion potential. | Detailed cross section survey data. | Conduct detailed reconnaissance and review geologic mapping, to assess conditions.
|  |  |  | Embankment and foundation conditions for overflow weir. | Evaluation of foundation conditions for overflow weir. | Soils data (geotechnical), ice data, flow data, and water profile data (surface elevations). | Review current site conditions through condition survey.
[6 empty] | Quarry sources for fuse plug material. | Install borings to determine foundation conditions at fuse plug structure.
203.5 | Upgrade Rose Creek Diversion Downstream from Fuse Plug | RCTA | Provide adequate freeboard to enable the RCDC to pass the flow of Rose Creek on a year-round basis for all flows up to the 500-year flood event. | Significant leakage from the channel in its current configuration – 30% at low flow. | Geotechnical, hydrology, hydraulics, and erosion potential. Repairs and improvements to the channel and the dike, riprap modifications, steep channel section, portions of the dike may be raised and/or buttressed to mitigate settlement or loss of freeboard. | Hydrologic and hydraulic model to provide influent SW flow data and elevations. | Conduct detailed reconnaissance and review geologic mapping and as-built information. | Drill, install and develop six well clusters along the RCDC dike crest (Report Link) |  | none
|  |  | Provide adequate freeboard to enable the RCDC to pass the flow of Rose Creek on a year-round basis for all flows up to the 500-year flood event. | The relationship defining flows related to the RCDC and the ID spillway. | Rose Creek Diversion dike stability: | Detailed cross section survey data, bed and bank material characterizations. Flow data, and water profile data (surface elevations). | Install borings along RCD dike crest and toe. | Geological reconnaissance of RCD (CH2M 2014m)
|  |  |  | The settlement of the RCDC dike upstream of the Intermediate Tailings Dam. | Seepage and slope stability | Relationship determination between the RCDC flows, water surface elevations, and the raising/flow requirements in the Intermediate Tailings Dam spillway. | Conduct laboratory testing including index, permeability and shear strength testing. | Advance 2 borings into bedrock (Report Link):
[5 empty] | Internal filter and drain system adequacy | Seepage losses from RCDC.
Liquefaction potential and mitigation
Deformation analyses (static and seismic)
Borrow material considerations
Slope protection
Geotechnical instrumentation
203.6 | Construct a Fish Bypass (ladder) | RCTA | Replacement of existing drop structures in the downstream portion of the RCDC with a larger fish bypass system. | Fish surveys indicate fish bypass ladder not required |  |  | None. | None
203.7 | Revegetate Riparian and High Bank Areas | RCTA | Erosion control and habitat (fish and wildlife) require vegetated surfaces to work concurrently with engineered diversion structures. |  | Locate appropriate soils for growth medium. Complete revegetation design for riparian areas and associated wetlands. | Characterize source and availability of soil cover materials. | None. | None
[5 empty] | Design soil and vegetation covers based on engineering design for creek, to enhance geotechnical design. | Characterize vegetation community for riparian revegetation.
204 – Groundwater Collection
204.1 | Construct Intermediate Dam Cut-off Wall | CVD | Install grout cut-off wall to bedrock in the area of the Intermediate Tailings and Cross Valley dams to direct water either to a central sump or directly into a pipeline; water will be pumped to Faro Pit or directly to the WTP. | Foundation information is not available for the area between the Intermediate Tailings and Cross Valley dams. Data show subsurface at the cross valley and downstream location consist of loose alluvium. Cut-off wall would be located downstream from Cross Valley Dam if Cross Valley Dam is retained. | Assessment of cut-off wall design required. Optimization and detailed design will need to be done during the detailed engineering design phase. Before completion of the cut-off wall and trench, a monitoring system will be installed both upgradient and downgradient from the collector system. | Potential interaction with SW. | None. (Completed in 2012/2013) | None
Bedrock contact delineation.
204.2 | Construct Intermediate Dam Interception Trench | CVD | Direct water either to a central sump or directly into a pipeline; water will be pumped to the Faro Pit or directly to the WTP during the treatment period of the year (early spring to early winter). | Configuration of bedrock surface. | Develop three-dimensional numerical GW flow model. Investigate various alternative configurations of GW interception design to optimize efficiency and minimize cost. Use GoldSim model or other model to provide boundary conditions for the GW flow model. Estimate GW flow and contaminant mass loading from extraction system (average and peak). This approach is also required if SIS is constructed downstream from Cross Valley Dam. | Potential interaction with SW. | None. (Completed 2012/2013) | None
| (changed to CVD SIS) |  |  | Distribution of aquifer properties. |  | Bedrock topography in the vicinity of the GW interception system downstream from the Cross Valley Dam.
|  |  |  | Response of aquifer system to GW pumping. |  | Aquifer properties of both the alluvial and weathered bedrock aquifers along the interception system alignment, including areas on the northeast and southwest extents of the valley fill aquifer.
|  |  |  | Magnitude of site water budget components. |  | Delineation of the alluvial aquifer thickness, bedrock topography, and aquifer properties downgradient from the planned GW interception system.
|  |  |  | Geochemical conditions within the aquifer and potential for well fouling. |  | Extent of hydraulic connection between the alluvial aquifer and Rose Creek downstream from the Cross Valley Dam.
Number of wells required for effective interception. Need for permeable trench and cut-off walls.
Effectiveness of collector trench and need for additional GW wells extending to bedrock.
205 - Miscellaneous Closure Activities
205.1 | Construct New Polishing Pond near the New Faro Area WTP | Mill / ETA |  |  | None. Not required |  | None. | None
Vangorda/Grum Area (Activity Code 300)
301 - Vangorda Pit
301.1 | Pit Wall Stability |  | Evaluate pit wall stability including stability of slopes above the access road ramp where pipeline is located. | Long term stability of pit walls. | Field inspection and evaluation to determine requirements/needs for (1) analytical stability evaluation, (2) instrumentation and monitoring, and (3) slope management including possible stabilization measures. | Requirements/needs for stability evaluation, subsurface information gathering and instrumentation and monitoring. | Conduct geologic engineering reconnaissance. Monitor field data. | Geological Reconnaissance (CH2M March 2014q): | Vangorda and Grum mine areas removed from project scope in spring, 2014.
| (new activity) |  | This is a new activity. | Consequences of pit wall failures (slide in pit may cause wave that could endanger pumping infrastructure and operating personnel) | Slope stability analysis. |  | Portion of this work planned for completion fall 2013 under separate task authorization.
301.2 | Construct Safety Berms (Vangorda Pit) |  | Construct the safety berms around Vangorda Pit. | Construction and design optimization will be completed during the detailed engineering process. | Surface hydrology (drainage ditches) and sediment control (retention/settling ponds). |  | Conduct engineering geologic field reconnaissance. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
Construct an access road along the alignment of the berm.
301.3 | Reslope and Cover Vangorda Pit Waste Rock Piles |  | Regrade smaller waste rock dumps in the southeastern portion of Vangorda Pit. Cover with till – ET cover. Revegetate areas within days of sloping. | Pit walls are retrogressing in some areas; slope instability issues. Potential of rockfalls. | Equipment access and foundation conditions. | Cover material volumes. | Evaluate equipment access, GW water level, foundation conditions. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Construct rock drains/ditches to prevent seeps from daylighting and ponding on revegetated surfaces. | Water level fluctuation in pit (risk of flooding revegetated areas and killing vegetation). | Water level fluctuations, pit wall stability. | Cover microtopography and revegetation plan. | Dig test pits to investigate seeps and design potential drainage collection systems; gradations and visual assessment.
|  |  |  | Geotechnical and geochemical variability of deposit. | Appropriate cover material volumes and revegetation planning. | Geochemical and geotechnical characterization of waste piles within the open pit. | Install boreholes/standpipes to below GW table to test for perched water within rock piles.
|  |  |  | Available subsurface information. |  | Slope stability study and analysis of pit walls. | Evaluate slope stability of retrogressing pit walls. Collect sufficient data to carryout modelling analysis.
|  |  |  | Location and number of seeps that could daylight on revegetated surface. |  | Evaluate requirements for slope stability monitoring (install inclinometers actively survey pit walls during construction, or bore holes if needed).
302 - Vangorda Dump
302.1 | Reslope Vangorda Waste Dump (plateau area) |  | Decrease infiltration through the dump, prevent dust generation and migration, and prevent direct uptake by wildlife. | Geotechnical properties and geochemical variability of waste. | Optimize resloping plan. | Geotechnical and geochemical characteristics of waste rock and soils. | Dig test pits within the waste rock at top of slope to depth of the potential cut to assess physical characteristics of waste rock, including gradation, and assess geochemical kineticsleachability. Evaluate foundation condition along perimeter for sediment control structures (dams, retention ponds, and diversion channels). | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Control SW runoff. | Runoff volumes, efficient and reliable control structures. | Develop surface water management plan during and after construction.
302.2 | Reslope Vangorda Waste Dump (perimeter slopes) |  | Construct geotechnically stable landforms that are consistent with long-term revegetation plans. | Conveyance of surface water runoff down the dump slopes without eroding cover. | Develop final landform design under the following considerations: | Stability of 2.7:1 slope for erosion revegetation (slope facing creek). | Evaluate foundation conditions for sediment management structures. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  |  | Failure modes and effects analysis of water conveyance channels (that is, ice jam). | Optimized resloping | Geotechnical and geochemical characteristics of waste rock that will be exposed as a result of regarding/resloping. | Dig test pits and sample along the toe of waste rock dump slope to evaluate geotechnical and geochemical conditions for potential to supply borrow if toe of slope is extended.
[5 empty] | Toe of slope is constrained by creeks in several areas; limited opportunities for downgradient sediment management. | Reactivity of regraded waste rock for sediment management and long term revegetation.
Protection of the stream channel immediately to the south of the toe of the Vangorda WR Dump.
Develop surface water management plan during and after construction.
Develop sediment control plan.
Assess foundation conditions to allow for sediment collection ditch.
Optimize seepage interception along toe of slope (currently appears to be part way up the slope).
302.3 | Place Low-infiltration Cover on Vangorda Waste Rock and Revegetate |  | Place low-infiltration cover on Vangorda Waste Rock dump and revegetate. | Allowable infiltration through cover, optimization of cover versus seepage interception and treatment. | Cut and fill optimization. | Final topography of waste dump. | Conduct engineering geological field reconnaissance for constructability review and cover material suitability. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  |  | Proposed reclamation surface is rough and loose; however, field investigation concluded that microtopography is bad for plateau areas because it promotes ponding and infiltration. | Infiltration modelling/cover optimization. | Sediment characteristics (geochemical and geotechnical) of material to be exposed during cut/fill (especially erodible fines). | Estimate waste rock gradation to evaluate filter compatibility with till cover.
[5 empty] | Need to review RLU planning basis with Waste Pile and Tailings Discipline Team. | Cover material needs to be identified for source and quality.
Existing site water balance versus water balance after final grading needs to be evaluated to determine surface and GW impacts.
Evaluate till stockpile as a potential borrow source.
Sediment control, especially on freshly covered slopes.
302.4 | Place Very Low Infiltration Cover Over Baritic Fines |  | Prior to regrading waste rock, cover baritic fines stockpiled on the northeastern side of the dump with a very-low-infiltration cover. Slope waste rock upslope of the fines and cover with a low-infiltration cover. | Clear delineation of limits of baritic fines/cover suitability and short-term and long-term performance. | Infiltration modelling/cover optimization. | Need geotechnical information for baritic fines to evaluate capping design and possible relocation. | Dig test pits for subsurface investigation to delineate limits of baritic fines; visual inspection; two gradations. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Alternative – Relocate baritic fines to sulphide cell as bedding layer for very low infiltration line. Only feasible if baritic fines have not migrated/leached excessively into the underlying waste rock. | If alternative design: Chemical compatibility of baritic fines with material in sulphide cell. | Sediment control and management of contaminated water (primarily surface contact water). | Evaluation of possible contamination of waste rock below baritic fines due to leaching of baritic fines. | Install boreholes to collect samples of waste rock below the baritic fines.
[6 empty] | Accurate delineation for baritic fines (conflicting areas and volumes). | Evaluate foundation conditions for sediment management structures.
[6 empty] | Sediment control plans during construction (if moved: relocate toward centre of Sulphide Cell rather than toward slope of waste rock pile). | Conduct geotechnical and geochemical testing.
302.5 | Place Very Low Infiltration Cover over Main Dump Sulphide Cell |  | To decrease infiltration through the dump and to prevent dust migration and direct uptake by wildlife. | Allowable infiltration through cover; optimization of cover versus seepage interception and treatment. | Cut and fill optimization and infiltration modelling/cover optimization. | Cover material volumes need to be assessed for this area. | Conduct engineering geological field reconnaissance. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Alternative 1 – Consider consolidating baritic fines on sulphide cell as finer (cushion) layer at liner contact. | If Alternative 1: Chemical compatibility of baritic fines with material in sulphide cell | Lessons learned from capping Grum Sulphide Cell. Need to monitor processes ongoing in that cover and requirement for liner. | Cover microtopography and revegetation plan needs to be assessed.
|  |  | Alternative 2 – Design 2:1 slopes for impervious liner and develop 3:1 or flatter slopes outside the liner to facilitate revegetation. |  | Merits of very low infiltration cover need to be assessed. | Gradation of waste rock (relates to necessity for cushion layer below cap).
Additional monitoring (for example, lysimeters and monitoring wells).
Design evaluations of Alternatives 1 and 2.
303 - Vangorda Creek Diversion
303.1 | Construct New Vangorda Diversion |  | Potential revegetation of the diversion and adjacent areas needs to be assessed. | The existing final design for the permanent realignment of the Vangorda Creek Diversion was performed by others; energy dissipation, erosion prevention measures and intake structure were incorporated into the final design. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. | Geotechnical data and soils data collection along final route only in the case the route alignment will change from the current SRK alignment. | Field work will be completed under TAR 18. | Drill 3 borings along proposed VCD alignment (SRK 2010), complete as standpipe piezometers (CH2M March 2014d): | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | To permanently realign Vangorda Creek around Vangorda Pit to minimize leakage into pit and provide a safe setback for the diversion away from the pit slope. | Potential revegetation of the diversion and adjacent areas needs to be assessed. Energy dissipation design elements especially along steep sections. | Some site specific hydraulic modelling required to provide water surface profiles. | The final alignment has not been selected. |  | Complete surface geophysical survey transects at SRK proposed VCD alignment, granitic rock outcrop, and grum waste rock dump quarry (CH2M March 2014d)
|  |  | Vangorda diversion is a component of the MTP and detailed design will be completed. | Erosion protection requirements. | Physical hydrologic/hydraulic modelling is required for final design. | Additional flow monitoring data being collected in 2013/14 for Vangorda, data to be coincident with precipitation data collected at existing meteorological stations (the Grum Dump) for additional model calibration and validation. |  | Collect and log surface samples from Granitic Rock Outcrop and Grum Waste Rock Dump Quarry (CH2M March 2014d)
|  |  |  | Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. | Alignment, energy dissipation, routing, gradient, materials, cost, geotechnical conditions, hydrology, hydraulics, erosion potential, and potential revegetation to manage erosion. | Revegetation planning for channel stabilization and riparian area erosion control. |  | Topographic Survey of SRK's proposed VCD alignment (CH2M March 2014d)
|  |  |  | Design flows have been selected. The exact alignment and hydraulic design are still uncertain. | Impacts on downstream Dixon Creek will need to be considered in the selected design. Re-vegetation to manage erosion needs to be included in design basis to assess cover materials and vegetation species required. |  |  | Fluvian geomorphic assessment of Vangorda creek (CH2M March 2014d)
[5 empty] | Permafrost impacts on design considerations. |  |  | Inspect Meteorological stations (CH2M March 2014d)
[5 empty] | Diversion design to final level including channel and floodplain geometry, stability and catchment area. |  |  | Reconnaissance of SRK's proposed VCD alignment (CH2M March 2014d)
303.2 | Upgrade Runoff Interceptor Ditch to Dixon Creek |  | Divert uncontaminated surface runoff from the northeast side of the Vangorda to the south and into Dixon Creek via the Dixon Creek Diversion. | Seepage rates, water quality, interception potential, long-term performance of interception. Design criteria provided in Table 4.3 require definition and linkage to seepage management and water quality. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. | Flow data, and water profile data (surface elevations). | Conduct detailed reconnaissance and review of geologic mapping, to assess conditions. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Upgrade channel to pass the 500-year storm. | Erosion protection requirements. | Some site specific hydraulic modelling required to provide water surface profiles. | Availability of flow data in Dixon Creek upstream from the confluence of Dixon Creek with Shrimp Creek. | Review current site conditions through condition survey.
|  |  | Place filter material and riprap sized for the flows in the channel, to prevent erosion. | Discontinuous permafrost, ground conditions, channel seepage losses, interaction of GW and SW, hydraulic analysis. | Geotechnical, hydrology, hydraulics, and erosion potential. | Subsurface conditions: | Collect additional continuous flow data in Dixon Creek upstream of the confluence of Dixon Creek and Shrimp Creek.
|  |  | Design to preliminary design level of detail. |  | Permafrost impacts on design considerations. | Permeability | Conduct detailed engineering geology field reconnaissance
[5 empty] | The GW/SW interaction is particularly important because of the seepage issue. | Permafrost occurrence
[5 empty] | Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area. Geotechnical, water quality, channel stability, seepage, hydrology, hydraulics modelling refinements, design storm flows, icing, soil cover, and re-vegetation options. | Erodability of base material
304 - Grum Pit
304.1 | Pit Wall Stability |  | Evaluate pit wall stability specifically the alluvium/colluviums slope at east wall of Grum Pit. | Long term stability of pit walls and management requirements. | Slope stability assessment: | Rate and magnitude of alluvium/colluvium soil slope movement | Conduct reconnaissance, review geologic mapping, review previous evaluations, and monitor results as available. | Geological Reconnaissance and survey monument installation (CH2M March 2014q): | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Perform stability evaluation and install slope movement instrumentation (prisms) | Consequences of pit wall failures (slow movements of large volume of material may impact available storage in pit and a rapid slide in pit may cause wave that could endanger pumping infrastructure and operating personnel) | Development of analytical slope stability model |  | Install slope movement instrumentation in unstable alluvium/colluviums soil slope at the east wall. Portions of this work planned to be completed under separate task authorization.
Calibration with measured slope movements
Assessment of margin of safety against slope failure
304.2 | Construct Safety Berms (Grum Pit) |  | Restrict access to human and wildlife for safety purposes. | Acceptable methods for providing safer barricades that will not be snow covered and ineffective. | Safety berms around Grum Pit and polishing ponds in the slot. | Sufficient geotechnical data. | Conduct engineering geologic field reconnaissance. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
305 - Grum Interceptor Ditch
305.1 | Divert Grum Interceptor Ditch away from Grum Pit |  | Interceptor ditch will be diverted away from Grum Pit. | Foundation conditions along Access Road next to the proposed ditch alignment and at the earth dam proposed at headworks. | Refinement of hydrologic and hydraulic models to provide influent SW flow data and elevations. Integration of SW and GW modelling approaches and results. Bed and bank materials characterizations. | Soils data (geotechnical), ice data, flow data, and water profile data (surface elevations). | Conduct detailed reconnaissance and review of geologic mapping. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Design to preliminary design level of detail. | Characteristics of overburden at the trapezoidal interceptor channel and cut slots at pit bench crest and at the south end of Grum Pit. | Some site specific hydraulic modelling required to provide water surface profiles. |  | Review current site conditions through condition survey.
[5 empty] | Geotechnical, hydrology, hydraulics, and erosion potential. Interceptor will be diverted away from Grum Pit. |  | Conduct engineering geological field reconnaissance
Permafrost impacts on design considerations.
Re-vegetation requirements.
Diversion design to preliminary level including channel and floodplain geometry, stability and catchment area.
305.2 | Construct Algae Filter at Slot Cut in Grum Pit |  | YG discontinued algal treatment in 2012. It will not be resumed. Grum Pit water will be treated in the Faro WTP. |  |  |  | None. | None
306 - Grum Waste Dump
306.1 | Reslope and Regrade Grum Waste Dump and Pull Back Crest |  | Reduce infiltration in the plateaued upper surface of the dumps. | SW, GW, and geochemical modelling are not well integrated. IPR provided recommendations for review. Enhanced modelling is underway to estimate the effectiveness of remediation over time and the application of adaptive management principals. | Update and integrate previous modelling (hydrology, water balance, and geochemical) to optimize ET model and erosion reduction. | Geotechnical and geochemical characteristics of waste rock and soils, including those that will be exposed as a result of regrading/resloping. | Evaluate foundation conditions along perimeter for sediment control structures (dams and retention ponds), and diversion channels. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Construct geotechnically stable landforms. |  | Develop surface water management plan during and after construction. | Volume of foundation materials at toe of waste rock dumps suitable for borrow. | Dig test pits within the waste rock slope perimeter to depth of the potential cut to assess physical characteristics of waste rock, including gradation, and assess geochemical kinetics/leachability.
|  |  | Minimize energy of runoff from covers and surrounding areas. |  | Consider infiltration galleries to facilitate surface water management | Locations of suitable areas for potential infiltration galleries to help control surface runoff and erosion. | Dig test pits at the foundation toe to evaluate geotechnical conditions and clarify potential for borrow through geochemical sampling to assess possible contamination from leachate seepage.
|  |  | Revegetate disturbed areas on all dump areas. |  | Optimize regrading/resloping plan considering final footprint constraints; evaluate option of expanding the toe. |  | Conduct detailed engineering geology field reconnaissance.
Development sediment control plan.
Assess borrow materials (till).
306.2 | Place Very Low Infiltration Cover on Grum Sulphide Cell |  | Control infiltration to significantly reduce the amount of water entering the surface of the waste (less than 0.5% of the mean annual precipitation). | No lysimeters are installed to monitor infiltration. It is difficult (nearly impossible) to determine the effectiveness of the existing cover without installing new instrumentation. Must conduct detailed lessons learned exercise for the Grum sulphide cover to optimize cover design going forward. | Cell already capped. Need to evaluate the performance of the cap for stability, reducing infiltration, and reducing contaminate discharge. | . | Propose additional instrumentation to enable monitoring of cover performance. Detailed visual inspection to evaluate cover performance and revegetation effort. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Bottom third of waste pile remains at high slope angle; SW appears contaminated; and need long term plan for SW disposition. |  | Final waste pile geometry and disposition of SW. |  | Existing data review and ongoing field assessment review.
Multidisciplinary team of design leads visit the Grum Sulphide Cell during the spring freshet to evaluate the performance of the recent retrofit and complete a lessons learned analysis of the cover design and water conveyance structures.
Continued review of GSC revegetation work by EDI.
306.3 | Place Vegetative Cover on Grum Waste Dump and Revegetate |  | Control infiltration and maintain vegetation growth. | Optimum cover and vegetative materials. | Evaluate performance of annual rye seeding, root and leaf density, and ability to continue with revegetation of deeper-rooted species/whips and cuttings into surface. | Data on seeding versus barley performance. | Conduct engineering geology field reconnaissance to evaluate protective cover requirements. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Cover the Main Dump with a rudimentary cover that has the minimum thickness of soil needed to allow plant growth. | Cover layer has been packed smooth, which may contribute to runoff and drilling issues, and create issues for planting and successful growth of shrub and tree species planned for further revegetation activities. | Continue evaluation of vegetation performance to provide information for soil cover composition, topography, and vegetation cover on other proposed, very low infiltration covers. | Review of planned further revegetation efforts. Continued review of vegetation performance over next 5 years.
|  |  |  | Revegetation of drainage-related structures does not appear to be in the plan, but would assist with erosion control. | Evaluate performance of drainage structures without vegetative cover. | Review of revegetation planning to align with planning for other landforms.
|  |  |  | Location and quality of borrow material. |  | Review of soil cover physical and geochemical characteristics.
307 - Grum Overburden Dump
307.1 | Reslope Grum Overburden Dump and Revegetate |  | The Grum Overburden Dump is the primary source of glacial till borrow material; after all borrow material at the dump has been removed, the area will be regraded and revegetated. | Appropriate configuration for terrestrial wildlife. | Infiltration modelling; VADOSE/W; SLIDE (slope stability), and TEMP/W (freeze-thaw). | Foundation conditions along dump perimeter are not defined. | Evaluate foundation conditions along dump perimeter for sediment control structures (dams, retention ponds) and diversion channels. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Potential integration of final excavated area for use as storage for emergency pit water management. | Sediment control. | Review sediment data from Grum OB Dump toe ditches and review literature regarding rill design. |  | Collect sediment and water samples from toe ditch area.
|  |  |  | Need to understand the contribution of surface texturing (ripping versus vertical or horizontal rilling) to sediment movement off-slope and moisture retention in soils. | Need to assess geochemical and textural impact of using phyllite rather than glacial till as vegetation cover substrate. |  | Perform field evaluation of erosion control on vegetation trial slope areas.
|  |  |  | Current revegetation trial appears to have used graded phyllite (ore) rather than glacial till. Need to understand geochemical and textural impact, because this is not the planned material for other cover areas. | Develop surface water management plan during and after construction. Optimize regarding/resloping plan. Develop sediment control plan. |  | Conduct engineering geology field reconnaissance to evaluate protective cover requirements.
Evaluate disposition of treatment plant sludge as potential subgrade material for liner or disposal in Grum Pit.
308 - Grum Ore Transfer Pad
308.1 | Regrade, Cover and Revegetate Ore Transfer Pad |  | Cover pad with very low infiltration cover, seed, and allow to revegetate naturally. Construct a temporary sediment collection ditch to divert runoff from the revegetated ore transfer pad away from a nearby stream until the vegetation has established. | Infiltration rates through cover. | Infiltration modelling (cover optimization); surface hydrology, energy dissipation swales; and TEMP/W. | Revegetation trial required ore transfer pad covers and slopes, especially where hydrocarbon-contaminated or sludge materials may be applied. | Evaluate foundation conditions along ore transfer pad perimeter for sediment control structures (dams and retention ponds), and diversion channels. Pilot testing with lysimeters. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Alternative – Consider consolidation or complete removal of the geochemically reactive fines (typically less than 1-m thick) and exposure of underlying phyllite waste rock that could be exploited as a potential borrow source | Appropriate configuration for terrestrial wildlife. | Need to review RLU planning basis with Waste Pile and Tailings Discipline Team, and plan a revegetation trial on this kind of slope/material. | Cover material needs to be identified for source and quality. | Evaluate cover performance; Confirm availability of suitable cover materials (volume and grain size).
|  |  |  | Sediment control. | Evaluate the potential for consolidation or complete removal due to limited thickness of geochemically reactive fines. | Need to assess impact of ore transfer pad on adjacent pond and wetland complex. | Conduct engineering geological field reconnaissance to evaluated cover requirements.
|  |  |  | Proposed reclamation surface is rough and loose; however, the field investigation concluded that microtopography is bad for plateau areas because it promotes ponding and infiltration. | Evaluate phyllite as potential borrow source for low visibility areas or as vegetation growth medium. | Determine rationale for capping without consolidation. | Test pits for investigation along the toe (downstream toe). Test pits on top of ore transfer pad to further delineate extent of reactive fines.
|  |  |  | If the thin layer of sulphidic fines is removed and the underlying phyllite is exploited, it will be necessary to develop appropriate closure scenario. Could potentially include development of constructed wetland. |  | Geotechnical characterization of ore transfer waste material (gradations, angularity, and hardness). | Alternative 1: Boreholes to test phyllite as potential borrow source; geochemical screening of representative samples of phyllite for use as growth medium.
|  |  |  | Impact on surrounding wetland areas needs to be assessed. |  | Thickness of geochemically reactive fines. | Conduct geochemical testing to characterize total metals and leachability.
309 - Vangorda/Grum Groundwater
309.1 | Install Grum GW Collection and Cut-off Walls |  | Capture contaminated GW seeping from the Grum Waste Rock Dump. | Pre-mining land surface topography and bedrock topography, subsurface material properties within and beneath Grum WRD, and areas where future seepage from the WRD may occur. | Condition of the Access Road below Grum Dump (construction vehicle access). | Bedrock surface topography, pre-mining land surface topography, spatial distribution of hydrostratigraphic units, and saturated thickness within and beneath Grum WRD and along the associated proposed SIS corridor. | Reconnaissance of Grum Area for access limitations to identify where access roads will be needed to conduct planned GW-related fieldwork. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Optimization and detailed design will be performed during the detailed engineering design phase. If monitoring indicates insufficient capture of contaminated GW, a cut-off wall and permeable collector trench will be constructed along the Access Road. Pumps would be installed in the collector trench to direct water to the Central Pond. |  | Pads for pumping wells and clear pipeline alignments. | Reliable XYZ locations of existing monitoring and operational infrastructure in the Grum Area. | Conduct seismic refraction survey with confirmation drilling atop Grum WRD and along the associated SIS corridor.
[5 empty] | Evaluate central pond foundation in vicinity of Grum Creek crossing. | Seasonal gaining versus losing reaches along Vangorda Creek between Vangorda and Grum WRDs. | Conduct potentiomanometer testing along Vangorda Creek to assess gaining and losing reaches between Vangorda and Grum waste Rock Dumps.
[5 empty] | Pump wells and pipelines. | GW monitoring network in Grum Area to provide sufficient early warning triggers in accordance with the AMP. GW flow directions near proposed SIS corridor and near the Grum WRD toe. | Drill and install additional monitoring wells and piezometers in and downgradient from Grum WRD to improve the AMP monitoring network. Instrument these wells with automatic data logging pressure transducers.
[5 empty] | House primary discharge pump in a heated enclosure on the side of the central holding pond. Install GW monitoring wells between and downgradient from the pumping wells. | Subsurface hydraulic properties along and upgradient from the proposed SIS corridor. | Drill and install stilling wells along Vangorda Creek and instrument these wells with automatic data logging pressure transducers.
[5 empty] | Evaluate GW flow directions and GW quality at existing and planned monitoring well and piezometer locations. |  | Conduct GW sampling at existing and newly installed wells, piezometers, and seeps.
Develop three-dimensional numerical GW model of the Vangorda/Grum Area to simulate GW levels and GW flow directions. This model will also be used to forecast performance of the Grum WRD SIS under different assumed configurations to optimize interception efficiency and minimize cost. This model will aid in forecasting metal loading to the SIS.
309.2 | Install VWRD Seepage Collection System |  | Minimize contaminant loading with covers to decrease infiltration and subsequent seepage. |  | Seepage collection system in place at the Vangorda Waste Rock Dump consists of French drains to funnel the seepage into a collection ditch that discharges to Little Creek Pond. More active collection of GW seepage from the VWRD is currently not required but may become necessary in the future if contaminant concentrations increase significantly. | Addressed under Activity Code 309.6. | None. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
A conceptual design for a GW collection system will be developed.
309.3 | Install Vangorda GW Collection System |  | Capture contaminated GW seeping from the Vangorda WRD. | Pre-mining land surface topography and bedrock topography, subsurface material properties within and beneath Vangorda WRD, and areas where future seepage from the WRD may occur | Evaluate GW flow directions and GW quality at existing and planned monitoring well and piezometer locations. | Bedrock surface topography, pre-mining land surface topography, spatial distribution of hydrostratigraphic units, and saturated thickness within and beneath Vangorda WRD. | Reconnaissance of Vangorda Area for access limitations to identify where access roads will be needed to conduct planned GW-related fieldwork. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
[5 empty] | Develop three-dimensional numerical GW model of the Vangorda/Grum Area to simulate GW levels and GW flow directions. This model will also be used to forecast performance of the Vangorda WRD SIS under different assumed configurations to optimize interception efficiency and minimize cost. This model will aid in forecasting metal loading to the SIS. | Reliable XYZ locations of existing monitoring and operational infrastructure in the Vangorda Area. | Conduct surface geophysics survey with confirmation drilling atop Vangorda WRD and along the associated SIS corridor.
[6 empty] | Robust GW monitoring network in Vangorda Area to provide sufficient early warning triggers in accordance with the AMP. GW flow directions near proposed SIS corridor and near the Vangorda WRD toe. | Drill and install additional monitoring wells and piezometers in and downgradient from Vangorda WRD to improve the AMP monitoring network. Instrument these wells with automatic data logging pressure transducers.
[6 empty] | Subsurface hydraulic properties along and upgradient from the proposed SIS corridor. | Conduct aquifer (pumping) tests at newly installed monitoring wells and piezometers. Conduct GW sampling at existing and newly installed wells, piezometers, and seeps.
310 - Vangorda/Grum Miscellaneous
310.1 | Remove Culverts, Decommission, and Revegetate |  | Breach all culverts and crossings, and revegetate the disturbed areas. Not yet determined whether haul road should be used as source of cover material; quality needs to be tested. | The flattening and revegetation of the haul road sideslope is currently under review. | Remove culverts (includes 10 major culverts in the North Fork River drainage). | Flow requirements for redesigned conveyance components. | None. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  |  | Will need to develop a sediment control and SW management plan for the work. | Decommission embankments.
|  |  |  | Possible source material for covers may be incorporated in haul road, but need to core road to check. | Remove/flatten safety berms.
|  |  |  | Removal of haul road across entire Rose Creek valley needs to be assessed. | Reclaim by hydroseeding each dump site, breached area, and area of disturbance to eliminate the potential need for hauling and placing topsoil.
310.2 | Demolish Buildings (treatment plant and the steel culvert over Grum Portal) |  | Remove existing buildings and infrastructure that will not be required after closure to mitigate potential long-term safety hazards. | Sampling for ACM and other designated substances may not be substantive enough to be useful for decommissioning purposes. Areas around the buildings that are not tested may need to be treated as designated or ACM substances. | Obtain, review, and catalogue site plans and other construction documentation for competitive procurement. | Sufficient sampling to mitigate costs for abatement of materials assumed to contain designated substances due to lack of information to the contrary. | Site reconnaissance. | Survey and inventory of water conveyance infrastructure (CH2M February 2016b) | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Extent of contamination of surfaces through buildings is unknown. | Site plans, surveys, Material Safety Data Sheets, and other information involving plant construction and makeup are not currently available. | Depending on EBA’s scope, obtain a demolition execution approach through a structural engineer. | Process material quantification. | Utility and site survey.
|  |  | Demolish buildings along with their foundations. Only the contaminated foundation components will be removed for proper disposal while the clean foundations will be covered in place (some may be buried within the toe of the Resloped waste rock dump) and revegetated. | Options to revegetate and reclaim the site as part of the natural landscape after decommissioning need to be evaluated. | Site visit to identify items that may have been missed. Follow up sampling may be required. | Waste disposal recommendations.
|  |  | Prior to any demolition works, a full inspection will be conducted on all site buildings to identify all hazardous waste, salvageable materials, and structural safety concerns. A solid waste management plan will be developed and a list of permits prepared. | Remove existing buildings that will not be needed after closure and that would be a long-term safety hazard. | Address safety concerns with onsite buildings to clear areas for safe access to complete other assessments that may be required. | Salvage assessment.
|  |  |  | Revegetate site and reclaim as part of a landscape plan. | Perform site utility surveys. Use GPR if necessary for decommissioning and to understand H&S risk during work. | Utility and site surveys.
[5 empty] | Retain a demolition contractor to assist in scrap assessment. | Assess suitable cover material quality.
[5 empty] | Determine and obtain permits required to perform demolition. | Assess potential for ET vegetation cover, or appropriate revegetation prescription.
Specific revegetation prescription required, this area is a candidate for an ET cover.
310.3 | Remove WTP Settling Pond |  | Construction of the new single WTP at the Faro Mine makes the current settling pond unnecessary. | Closure and disposal requirements for material below the pond. Settling ponds have had leakage issues in the past. | After the water treatment settling pond is cleaned of sludge, the berm should be breached. Breach, riprap, and cover the Water Treatment Settling Pond after the new plant is operational. Breach the dams at the Sheep Pad Ponds (built to capture sediment from the Grum Interceptor Ditch before discharging into Vangorda Creek); the pad ponds do not need to be covered. | Subsurface conditions below the settling pond. | Need to determine ability to access because the pond is in use. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
Sludge will be dredged to the Grum Pit using the new dredge system with conveyance in the existing pipeline and a new section into the pit opposite the pump barge.
310.4 | Remove Contaminated Soils (Fuel Lube Station) |  | Remove hazardous materials and contaminated soil at the site that could cause a long-term impact on the surrounding environment. | Volume of material excavation; volume and source of backfill. | The C&R Plan, Table 6.13, outlines design criteria. | Extent of soil hydrocarbon contamination (lateral and vertical) near the Lube Shack and Tank Farm. | Excavate soil test pits near the Lube Shack and the Tank Farm and collect hydrocarbon, metals, PAH, and ANP soil samples to delineate contamination. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  |  | Concentration threshold criteria for soil removal. |  | GW flow directions.
Extent of associated GW contamination.
310.5 | Construct Bioremediation Cell |  | Treat hydrocarbon contaminated soil. | Location of landfarm is to be determined; likely on a waste rock dump near mill buildings. | The C&R Plan, Table 6.13, outlines design criteria. |  | None. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
310.6 | Reclaim Roads |  | Prevent long-term erosion and breach crossings to prevent blockage. | Road areas will require specific reclamation plans in accordance with required surface drainage plans and surrounding reclamation prescriptions. | There is currently no specific prescription for road revegetation or information about road material quality to predict vegetation success. | Require assessment of road material quality for use as cover materials or requirements for revegetation. | None. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  | Culverts and crossings will be breached and resloped and drainages restored. Scarify road surfaces and revegetate. |  |  | Require assessment for basis of design of road reclamation – revegetation or swale/channel formation as part of surface drainage plan.
310.7 | Little Creek Pond |  | The C&R Plan does not provide for the Little Creek Dam, but notes that it may be used. It is assumed that the dam will be used as part of closure. | The need for this structure is undefined and will be determined based on the need for SW and GW collection and storage. The dam is considered a low-hazard dam; therefore, it has a small spillway (500-year event). | Initial review indicates polishing pond in conjunction with a new WTP not required. | Embankment and foundation properties (strength and permeability). | Conduct field reconnaissance. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  |  | C&R Plan states that the future of the LCP is yet to be determined, but it will probably not continue to function as a collection pond for seepage from the Vangorda Waste Rock Dump. The C&R Plan suggests that the LCP might be used as a polishing pond for the WTP | If retained, review of geologic mapping and as‑built information. | Piezometric conditions in the dam and the foundation. | Install hollow-stem auger borings:
[5 empty] | Engineering analyses: | Erosion protection (riprap) requirements for wave action (assuming that a pond will need to be retained). | SPT and undisturbed samples, as appropriate
[5 empty] | Spillway capacity |  | Piezometers, including monitoring
[5 empty] | Seepage analysis |  | Conduct index tests (grading and Atterberg Limits) on soil samples.
[5 empty] | Slope stability including pseudostatic (seismic) stability |  | Test shear strength
400 - Site Wide Activities
401 - Haul Road
401.1 | Remove Culverts, Decommission, and Revegetate |  | Breach all culverts and crossings, and revegetate the disturbed areas. Not yet determined whether the haul road should be used as a source of cover material; quality needs to be tested. | Rockfall issues appear to be a natural hazard in valley areas and are construction hazards in dealing with the Faro Mine waste rock piles and high Haul Road berms. Value of reconstruction of valley areas after Haul Road material removal needs to be assessed. | Remove culverts (includes 10 major culverts in the North Fork River drainage). Decommission embankments. Remove or flatten safety berms. Reclaim by hydroseeding each dump site, breached area, and area of disturbance to eliminate the potential need to haul and place topsoil. | Dump or cover materials resulting from decommission of haul road not yet assessed in revegetation and reclamation planning; need to study and report back into waste rock and cover inventory. | None. | None
|  |  | The flattening and revegetation of the haul road sideslope is currently under review. | Possible source material for covers may be incorporated in Haul Road, but need to sample road materials to confirm. Removal of Haul Road across entire Rose Creek Valley needs to be assessed. | Integrated planning required for the NFRC valley area (including riparian and ponded areas), in conjunction with activities to reslope the waste rock pile and remove all or part of the haul road.
Will need to develop a sediment control and SW management plan for the work.
401.2 | Alternative analysis for retention of haul road |  | To provide route for Vangorda pipeline to WTP at Faro, Haul Road may be retained. | Need to assess potential interim 10-15 year impact to wildlife and fish during interim works; then perpetual impact as part of closure surface. | Alternatives analysis required for retention of Haul Road impact on material balance, fish and wildlife access. Assess whether portion of haul road can be used as borrow source. | Require wildlife and fisheries alternatives analysis. | None.
|  |  |  | Approx 800,000 m3 of waste rock from the Haul Road was planned for cover on the Rose Creek Tailings Facility. |  | Require material balance review.
Require analysis of rock drain retention options for fish passage in NFRC.
401.3 | Construct Haul Road Access from Vangorda to RCTA |  | Breach all culverts and crossings, and revegetate the disturbed areas. The flattening and revegetation of the haul road sideslope is currently under review. Will need to develop a sediment control and SW management plan for the work. |  | Construct temporary haul roads. | Review of new haul road access area inclusion in environmental assessment, and basis of reclamation design required for affected area. | None. | None
Not clear if haul road access alignment has been assessed in the environmental assessment. Need to check if undisturbed areas will be affected by construction; assess and plan for conservation and reclamation of area.
401.4 | Construct Cross-Site Mine Water Pipeline |  | A new HDPE cross-site pipeline will be constructed on the Haul Road to convey Vangorda/Grum-area water to the new Faro WTP. This pipeline will also have a branch to the Faro Pit for temporary storage. It will be operated only during the warm season (e.g. May-Sept) and will be dewatered prior to winter. Cleanout will by pigging. For protection from the elements as well as from traffic damage and vandalism, it is expected to either be buried shallowly or have fill placed over it. | Detailed alignment up from Vangorda and Grum Pits and along the Haul Road. | Determine final alignment. | Subsurface conditions along alignment. | Test pitting along alignment, conduct geotechnical testing, gradation and Atterberg Limits testing. | None | Vangorda and Grum mine areas removed from project scope in spring, 2014.
|  |  |  | Design Capacity (preliminary design capacity is 2,000 USgpm). | Determine final design capacity. | Source of fill if covered rather than buried
402 - Water Treatment
402.1 | Construct new Faro Water Treatment Plant and Piping |  | Design and build new WTP and pipelines to treat contaminated wate. (design completed to ~90% level under TAR 13) | C&R Plan includes potential for two new WTPs, Faro Area and Vangorda/Grum Area. | Determine source(s) of on-site borrow for backfill and concrete aggregate. | Availability and suitability of on-site borrow for backfill and concrete aggregate. | None. Work will be completed under TAR 013. | See site-wide borrow tasks | In 2013 WTP design was suspended; proceeded with procurement and construction of an Interim water treatment system
YG has decided to construct a single WTP located in the southwest corner area of the Faro Mill Yard. The plant will initially not have filters and will discharge through the CVP.
A new pipeline will be constructed on the Haul Road to transport Vangorda/Grum-area water to the new WTP or to the Faro Pit for temporary storage (See Activity Code 301.2). Vangorda/Grum-area water will be collected and stored in the Vangorda and Grum Pits and will be pumped through this pipeline during the warmer months, e.g. May – September.
On-site borrow source for backfill and for concrete aggregate is uncertain.
|  |  |  | Effluent discharge limits is critical to WTP filter system design. | Evaluation of concentrations based on a risk assessment and treatment technology-specific achievable basis. | Discharge limits for treated water including sulphate/TDS. | None.
|  |  |  | Treatment effectiveness achievable by a new HDS/filtration system (ability to consistently meet discharge limits). | Use 2012 pilot test results to assess potential performance required from the future filtration system. | Performance of new WTP in comparison to potential new discharge requirements | None. |  | In 2013 WTP design was suspended; proceeded with procurement and construction of an Interim water treatment system
|  |  |  | Design and operating parameters for achieving optimum WTP performance. | Evaluation of WTP performance without filters in comparison to potential new discharge requirements. | Filter system design and operating parameters.
|  |  |  | If site discharge limits require very low effluent concentrations, an advanced treatment process may be required in addition to filtration. If sulphate discharge is regulated, NF/RO treatment may be required. | Evaluate discharge limits relative to treatment performance expected for the HDS/filtration process. | Need for sulphide addition, NF/RO, or other advanced water treatment process to meet discharge limits. | Conduct bench or pilot tests (or both) of to evaluate filter performance using Interim treatment plant effluent. | None
|  |  |  | Precipitation and scale formation in pipelines is unknown but likely if waters allowed to oxidize or sources waters blended. | Review chemical composition of water to be piped and possible different waters to be combined in pipelines. | Potential for precipitate formation and scaling in water collection and conveyance pipelines. | Characterize relevant water streams. | Routine monitoring of influent water streams by site care and maintenance operator | In 2013 WTP design was suspended; proceeded with procurement and construction of an Interim water treatment system
[5 empty] | Geochemical modelling. | Design features needed to mitigate problems from precipitation and scaling. |  | Bi-annual monitoring of site-wide seeps by CH2M (CH2M October 2013b), CH2M March 2014c), CH2M March 2015b)
|  |  |  | Sludge disposal capacity in Faro Pit now that it will also store sludge produced from treatment of Vangorda/Grum-area water. | Calculate annual net water balance of water collected and conveyed to new WTP (GoldSim modelling). | Quantity requirements and capacities for water and sludge storage in Faro Pit. | None. |  | In 2013 WTP design was suspended; proceeded with procurement and construction of an Interim water treatment system
Calculate estimated annual sludge production and solids volume conveyed to Faro Pit as well as final in-situ storage volume over time.
|  |  |  | The appropriateness and effectiveness of sludge disposal in the pits. | Assessment of sludge dissolution, fate, and effects on water chemistry. | Geochemical stability of sludge deposited in Faro Pit. | Conduct geochemical characterization of current pit water conditions. | Faro pit lake profiling and sampling completed annually (CH2M October 2013b), CH2M March 2014c), CH2M March 2015b) | In 2013 WTP design was suspended; proceeded with procurement and construction of an Interim water treatment system
Perform laboratory extraction and analysis of HDS sludge (from pilot study) under geochemical conditions in pit(s).
402.2 | Polishing Pond |  | Construct new Polishing Pond near the new Faro Area WTP. | None – not required |  |  | None. | None
CH2M HILL has determined that a polishing pond is not required following construction of the HDS treatment facilities.
402.3 | Construct Vangorda WTP and Piping |  | A single WTP located in the area of the Faro Mill will be constructed. Piping route evaluated under separate activity. | None – not required |  |  | None.
403 - Borrow Area Development
403.1 | Develop and Decommission Faro Borrow Sources | Sitewide | Identify all necessary borrow sources and develop plans to rehabilitate borrow areas. |  | Some assessments completed on borrow sources. Good quality armour rock is hard to find. | Delineation of sources d/s of tailings area. Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan. | At completion of 2013 field work, need to evaluate whether additional work is required at all sites listed in this section or at additional locations.
|  |  | Impact on fish and terrestrial habitats, habitat compensation and contamination in Haul Road granular sources. |  | Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan.
See specific areas below
403.2 | Develop and Decommission Faro Borrow Sources – Granular Soil | Sitewide | Identify all necessary granular borrow sources and develop plans to rehabilitate borrow areas. | Impact on fish and terrestrial habitat and habitat compensation. | Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan. | Amount and quality/composition of material that has been used since the estimates were developed. | Field investigations are underway: | Geological reconnaissance (CH2M March 2015w)
|  |  | Expand Rose Creek borrow site. | Quality and quantity of borrow material is undefined or poorly defined. | Delineation of sources downstream of tailings area. | Geochemical/geotech parameters | Dig test pits to explore potential borrows; include field mapping | Excavate test pits (CH2M March 2015w)
|  |  | New – Intermediate Dam spillway. | Limiting EA issues associated with various potential sources. |  | Delineation of sources. Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan. | Explore Rose Creek Borrow site, the Haul Road Borrow site and East of North Fork of Rose Creek | Drill pionjar borings (CH2M March 2015w)
|  |  | Potential – east of North Fork of Rose Creek. Could be developed in connection with relocation of NFRC. |  |  |  |  | The 2015 Investigation of NFRC diversion alignment included extensive drilling, test pitting and geophysical surveys east of NFRC (NFRC DBR).
403.3 | Develop and Decommission Faro Borrow Sources – Low Permeability | Sitewide | Identify necessary granular borrow sources and develop plans to rehabilitate borrow areas. | Potential Areas: | Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan. | Amount and quality/composition of material that has been used since the estimates were developed. | Survey vegetation and rare plants. | Geological reconnaissance (CH2M March 2015w)
|  |  | Rose Creek Haul Road. | East of North Fork of Rose Creek; could be developed in connection with relocation of NFRC | Delineation of potential borrow sources d/s of RCTA. | Geochemical/geotech parameters. | Conduct initial field reconnaissance and field investigations: | Excavated test pits (CH2M March 2015w)
|  |  | Expand tailings borrows. | Between Faro Waste Rock Dump and original Tailings Impoundment |  | Delineation of sources. Environmental assessment not completed for borrow areas – vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in revegetation plan. | Field studies underway at Rose Creek Haul Road | Drill pionjar borings (CH2M March 2015w)
|  |  |  | East of Fresh Water Supply Reservoir |  |  | Dig test pits (Tailings Borrow, between Faro Waste Rock Dump and original Tailings Impoundment and East of Fresh Water Supply Reservoir). | 2015 Investigation of NFRC diversion alignment included extensive drilling, test pitting and geophysical surveys east of NFRC , South of Main WRD, and at the former Freshwater Reservoir Dam (NFRC DBR).
|  |  |  | Impact on fish and terrestrial habitat and habitat compensation |  |  | Install boreholes to native contact.
|  |  |  | Quality and quantity of borrow material is undefined or poorly defined. |  |  | Conduct field mapping and pionjar (hand-held drill) surveys of undefined sources.
Limiting EA issues associated with various potential sources.
403. 4 | Develop and Decommission Haul Road as a Borrow Source | Sitewide | Haul Road material to be used to cover tailings area, contouring, and regarding. | Quality and quantity of borrow material is undefined or poorly defined. | Investigations to date on the Haul Road have been minimal and inconsistent. | Need an investigation that includes consistent geochemical/geotechnical testing. | Perform screening-level assessment. | Drilled 1 boring through the haul road near the Rock Drain (NFRC DBR)
Dig test pits (shallow) for visual inspection in miscellaneous potential borrow sources.
403.5 | Develop and Decommission Vangorda-Grum Granular Borrow Areas | Sitewide | Identify necessary borrow sources and develop plans to rehabilitate borrow areas. | Impact on fish and terrestrial habitats and contamination in Haul Road granular sources. | Some assessment completed on borrow sources. | Delineation of sources around Moose Pond and Grum Creek. Environmental assessment not completed for borrow areas; vegetation and rare plant surveys required. Reclamation planning for borrow sources needs to be included in the revegetation plan. | Conduct Initial field reconnaissance program: | None | Vangorda and Grum mine areas removed from project scope in spring, 2014. | Conduct Initial field reconnaissance program:
|  |  | Impact on fish and terrestrial habitats and habitat compensation. | Quality and quantity of borrow material is undefined or poorly defined. | Environmental assessment not completed for borrow areas – vegetation and rare plant surveys are required. Reclamation planning for borrow sources needs to be included in the revegetation plan. |  | Dig test pits in proven borrows (Grum Creek/Moose Pond) |  |  | Dig test pits in proven borrows (Grum Creek/Moose Pond)
|  |  |  | Limiting EA issues associated with various potential sources |  |  | Conduct field mapping and pionjar surveys of undefined sources. |  |  | Conduct field mapping and pionjar surveys of undefined sources.
403.6 | Develop and Decommission Grum Overburden Dump Borrow Area (Low Permeability Soils) | ? | Identify volumes, geotech/geochem parameters of Grum OB dump and Grum overburden dump foundation (approximately 8 million m3 + 1 million m3 = 9 million m3). | Grum Sulphide Cell used till from South Till Borrow Area; contractors indicated that Grum overburden pile would require significant effort to sort oversized materials (that is, may be large percentage of boulders in till material). Amount used was 240,227 m3 | Volume decline. | Geochemical/geotech parameter studies are underway. | Include reclamation planning for borrow sources in revegetation plan. | Geological reconnaissance of North Wall of Grum Pit (CH2M March 2015w) |  | None
|  |  |  | Impact on fish and terrestrial habitats and contamination in Haul Road granular sources. | Geotechnical characterizations. | Depth of foundation investigation is underway. | Initial field program: sonic boreholes and samples. Samples are being collected to delineate soil distribution. Initial geochemical analysis on representative samples, Test pits for visual assessment for gradations | Excavated 10 test pits at Grum Overburden Dump (CH2M March 2015w)
|  |  |  | Quality and quantity of borrow material is undefined or poorly defined. | Geochemical characterizations. |  | Collect the following samples: | Drilled 11 sonic borings in the Grum Overburden Dump (CH2M March 2015w)
|  |  |  | Limiting EA issues associated with various potential sources. | Foundation Investigations. |  | select samples for further geochemical (for example, leach testing) | Excavated 4 test pits in the Grum Overburden Dump Foundation (CH2M March 2015w)
[5 empty] | Reclamation planning for borrow sources needs to be included in revegetation plan. |  | Geotechnical (for example, gradations) testing. | Drilled 1 sonic boring in the Grum Overburden Dump Foundation (CH2M March 2015w)
[5 empty] | Evaluate Till Stockpile at Vangorda Waste Dump. |  |  | Drilled 5 pionjar borings in the Grum Overburden Dump Foundation (CH2M March 2015w)
Drilled 2 borings at granitic rock outcrop (CH2M March 2015w)
403.7 | Develop and Decommission Area Northeast of Grum Pit (Low Permeability Soils) | ? | Identify volumes, geotechnical, and geochemical parameters of low-permeability borrow source; North Wall of Grum Pit. | Impact on fish and terrestrial habitats and contamination in Haul Road granular sources. | Volume decline. | Geochemical/geotech parameter studies are underway. | Include reclamation planning for borrow sources in revegetation plan. | See 403.6
|  |  | SRK Additional Borrow Studies 2004, Task 11a indicates bedrock ranges from 9 to 18m bgs (based on GPR) with probable overlying till. | Quality and quantity of borrow material is undefined or poorly defined. | Geotech characterizations. | Depth of foundation investigation is underway. | Initial field program underway: surface samples, test pits for visual assessment; and boreholes.
|  |  |  | Limiting EA issues associated with various potential sources. | Geochem characterizations. |  | Select samples for Geochem. Geotech (for example gradations) testing.
Foundation Investigations.
Reclamation planning for borrow sources needs to be included in revegetation plan.
403.8 | Develop and Decommission Area Rip Rap Sources (Faro Grum Vangorda Areas) | Sitewide | Identify and develop borrow sources of strong chemically stable rock for use in surface channels and drainage systems. | BGC indicates Grum Dump Rock Quarry has been exhausted (personal communication Nov. 2011). | Diamond drill and/or blasting exploration for four potential riprap quarries: | Total volumes of riprap and rockfill required. | Conduct initial field reconnaissance and field investigations at RCDC quarry and possible granite quarry location at north end of FCDC. | Drill 4 borings at Granitic Rock Outcrop (CH2M March 2015w)
|  |  | Quarries will need to be excavated from granitic bedrock outcrops. |  | Expanded existing RCDC quarry. | Estimate of size ranges for these materials. | Field studies and installation of diamond drill holes at the Faro Mine Road Granite are underway. | Completed surface geophysical transects at Granitic Rock Outcrop and Grum Waste Rock Dump Quarry (CH2M March 2015w)
|  |  | Alternative: Investigate suitability of using cobbles/boulders mechanically separated from till overburden or geochemically inert waste rock during rock processing for other activities (that is, 201.1/.2/.3, 202, which requires large quantities of drainage rock to cover tailings area). |  | Possible gabbro quarry site located downstream and uphill from the Cross-valley Dam but unsure of outcrop. | Location of accessible quarry sites for production of these materials. | Geotech samples from the Grum Dump Rock Quarry and the Faro Mine Road Granite Outcrop have been collected for Geochem and Geotech analyses. | Explore shallow bedrock south of Faro Main WRD (2015 NFRC DBR):
[5 empty] | Possible buried granite quarry location at north end of FCDC. No current outcrop noted and location may be outside mine footprint (EA issue). | Quantity and quality of the rock materials in potential quarry sites. | Perform Geochemical suite of test including metals, ABA, paste pH and leach extraction, followed by possible kinetic tests. | Advance 6 borings
[5 empty] | Possible granite quarry located north of the main haul road and west of the Grum transfer station; Faro Mine Road Granite Outcrop. Outcrop currently exists. |  | Geotech tests include: | Excavate 12 test pits
[7 empty] | Specific gravity and absorption | Surface geophysical transects
Unconfined Compressive Strength
Petrographic
Freeze-thaw durability
Wetting-drying durability
Other soundness tests
Notes:
ID = Intermediate Dam
IPR = Independent Peer Review
IPRP = Independent Peer Review Panel
KPI = key performance indicator
LCD = Little Creek Dam
LCP = Little Creek Pond
LD/SF = lime demand and solids formed
LGSP = low-grade ore stock pile
m = metre
m bgs = metre(s) below ground surface
m/cm = metre per centimetre
Remove these columns.
I believe these columns need to stay because they were part of the original table. The intent here is to add to the end of the original table.
Why are these columns blank?
Did we not do some bathymetry work in the CVP/IP with more planned for 2016? I would annotate where we know some of these gaps will be closed or if they were but have not been reported yet.
This does not seem to be related to the proposed field work. The information in the column should be checked again to make sure that the scope changes are relevant.
Agreed. Between this completed fieldwork, the project scope change and remaining gaps, each element of proposed fieldwork should be addressed.
Seems like the big picture scope changes could be listed up front, then only include specific changes in this table.
I agree with Steve’s comment. These seem out of place in that they don’t, or only peripherally, relate to the specific gaps and field requirements that were identified.
If VGA has been removed do we still consider this a gap? I think no if we are saying the scope changed.
Not relevant to roads
This is relevant. Are there any associated remaining gaps??
NFRC Head Pond? Are the naming conventions in here correct?
Is this complete?
Not a reference
Not a reference
Appears to be the most relevant scope change but if this impacted the planned work, then would we not expect some remaining gaps?
These are all design advancement that I assume are summarized in the CDRM. I would omit but add a project scope change in that cover design was removed from our scope in late 2015.
I think these inputs should be specifically related to why work did not get completed
I’m not aware of any deliverable where this is discussed, but this is what I’ve gathered from results I’ve observed… I don’t think further borings are needed to determine depth to buried native surface anywhere at Faro site.
This pile appears very similar to LGSPC.
I think our results suggested there is no clear boundary / footprint to the Sulphide cell(s).
Not familiar with current conceptual design for this area