## CC-A
|  | SHEET TITLE: |  | Clinton Creek Option A LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.262
2 | Major Road Improvements |  |  |  | 3.62
3 | Slope Stabilization |  |  |  | 0.245
4 | Drop Structure 4 Repair |  |  |  | 0.8
5 | Construction Water Management |  |  |  | 0.516
6 | Support Equipment |  |  |  | 0.163
7 | Support Labour |  |  |  | 0.54
8 | Asbestos Control |  |  |  | 0.77
9 | Fuel Transportation |  |  |  | 0.005
10 | Indirects |  |  |  | 2.69
Note: Cost Breakdown in Appendix 3, Option CC-A
Subtotal |  |  |  |  | 9.611
| EPCM |  |  |  | 0.9611
| Contingency (25%) |  |  |  | 2.643
Total Estimated Capital Costs |  |  |  |  | 13.2151
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 3.7336
2.1 | Repair 4 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 536000 | 5 | 100 | 3.7336
3 | Replacement |  |  |  | 6.1777
3.1 | Replace 2 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 1246000 | 7.5 | 100 | 5.6059
3.2 | Replace Drop Structure 4 Armouring (Cost Breakdown in Appendix 3) | 1273000 | 45 | 100 | 0.57179
Subtotal |  |  |  |  | 11.5454
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 11.5454
Equivalent Annual Operational Costs |  |  |  |  | 0.31533
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 24.7605
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (15 km) (Cost Breakdown in Appendix 3) | 3898000 | 20 | 100 | 5.5871
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 6.6118
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 6.6118
Equivalent Annual Cost |  |  |  |  | 0.18058
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## CC-B
|  | SHEET TITLE: |  | Clinton Creek Option B LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.758
2 | Major Road Improvements |  |  |  | 3.629
3 | Waste Rock Dump Stabilization |  |  |  | 9.017
4 | Access Road Construction |  |  |  | 0.218
5 | Creek Bed Stabilization |  |  |  | 2.05
6 | Support Equipment |  |  |  | 0.532
7 | Support Labour |  |  |  | 0.81
8 | Asbestos Control |  |  |  | 0.85
9 | Fuel Transportation |  |  |  | 0.045
10 | Indirects |  |  |  | 10
Note: Cost Breakdown in Appendix 3, Option CC-B
Subtotal |  |  |  |  | 27.909
| EPCM |  |  |  | 2.7909
| Contingency (25%) |  |  |  | 7.675
Total Estimated Capital Costs |  |  |  |  | 38.3749
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 6.102
2.1 | Repair 8 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 876000 | 5 | 100 | 6.102
3 | Replacement |  |  |  | 6.8347
3.1 | Replace 2 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 1246000 | 6.25 | 100 | 6.8347
Subtotal |  |  |  |  | 14.5707
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 14.5707
Equivalent Annual Operational Costs |  |  |  |  | 0.39795
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 52.9456
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (15 km) (Cost Breakdown in Appendix 3) | 3898000 | 20 | 100 | 5.5871
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 6.6118
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 6.6118
Equivalent Annual Cost |  |  |  |  | 0.18058
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## CC-B2
|  | SHEET TITLE: |  | Clinton Creek Option B2 LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.758
2 | Major Road Improvements |  |  |  | 3.603
3 | Waste Rock Dump Stabilization |  |  |  | 9.017
4 | Access Road Construction |  |  |  | 0.215
5 | Creek Bed Stabilization |  |  |  | 2.622
6 | Support Equipment |  |  |  | 0.532
7 | Support Labour |  |  |  | 0.81
8 | Asbestos Control |  |  |  | 0.85
9 | Fuel Transportation |  |  |  | 0.045
10 | Indirects |  |  |  | 10.02
Note: Cost Breakdown in Appendix 3, Option CC-B2
Subtotal |  |  |  |  | 28.472
| EPCM |  |  |  | 2.8472
| Contingency (25%) |  |  |  | 7.8298
Total Estimated Capital Costs |  |  |  |  | 39.149
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
Subtotal |  |  |  |  | 1.6341
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 1.6341
Equivalent Annual Operational Costs |  |  |  |  | 0.04463
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 40.7831
Note: This is considered a walk-away solution. Therefore site access would not need to be maintained.

## CC-C
|  | SHEET TITLE: |  | Clinton Creek Option C LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.281
2 | Major Road Improvements |  |  |  | 3.172
3 | Bulk Earthworks |  |  |  | 0.865
4 | Access Road Construction |  |  |  | 0.155
5 | Creek Bed Stabilization |  |  |  | 1.158
6 | Construction Water Management |  |  |  | 0.908
7 | Support Equipment |  |  |  | 0.163
8 | Support Labour |  |  |  | 0.54
9 | Asbestos Control |  |  |  | 0.77
10 | Fuel Transportation |  |  |  | 0.009
11 | Indirects |  |  |  | 4.962
Note: Cost Breakdown in Appendix 3, Option CC-C
Subtotal |  |  |  |  | 12.983
| EPCM |  |  |  | 1.2983
| Contingency (25%) |  |  |  | 3.5703
Total Estimated Capital Costs |  |  |  |  | 17.8516
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 8.5678
2.1 | Repair 12 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 1230000 | 5 | 100 | 8.5678
3 | Replacement |  |  |  | 17.9112
3.1 | Replace 2 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 1246000 | 2.5 | 100 | 17.9112
Subtotal |  |  |  |  | 28.1131
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 28.1131
Equivalent Annual Operational Costs |  |  |  |  | 0.76782
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 45.9648
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (15 km) (Cost Breakdown in Appendix 3) | 3898000 | 20 | 100 | 5.5871
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 6.6118
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 6.6118
Equivalent Annual Cost |  |  |  |  | 0.18058
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## CC-C2
|  | SHEET TITLE: |  | Clinton Creek Option C2 LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.281
2 | Major Road Improvements |  |  |  | 3.608
3 | Bulk Earthworks |  |  |  | 0.865
4 | Access Road Construction |  |  |  | 0.158
5 | Creek Bed Stabilization |  |  |  | 0.828
6 | Construction Water Management |  |  |  | 0.908
7 | Support Equipment |  |  |  | 0.163
8 | Support Labour |  |  |  | 0.54
9 | Asbestos Control |  |  |  | 0.77
10 | Fuel Transportation |  |  |  | 0.009
11 | Indirects |  |  |  | 4.29
Note: Cost Breakdown in Appendix 3, Option CC-C2
Subtotal |  |  |  |  | 12.42
| EPCM |  |  |  | 1.242
| Contingency (25%) |  |  |  | 3.4155
Total Estimated Capital Costs |  |  |  |  | 17.0775
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 3.7336
2.1 | Repair 4 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 536000 | 5 | 100 | 3.7336
3 | Replacement |  |  |  | 6.9871
3.1 | Replace 2 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 1246000 | 7.5 | 100 | 5.6059
3.2 | Replace 550 m Riprap-Lined Channel (Cost Breakdown in Appendix 3) | 3075000 | 45 | 100 | 1.3812
Subtotal |  |  |  |  | 12.3548
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 12.3548
Equivalent Annual Operational Costs |  |  |  |  | 0.33743
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 29.4323
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (15 km) (Cost Breakdown in Appendix 3) | 3898000 | 20 | 100 | 5.5871
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 6.6118
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 6.6118
Equivalent Annual Cost |  |  |  |  | 0.18058
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## CC-C3
|  | SHEET TITLE: |  | Clinton Creek Option C3 LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.281
2 | Major Road Improvements |  |  |  | 3.608
3 | Bulk Earthworks |  |  |  | 0.865
4 | Access Road Construction |  |  |  | 0.215
5 | Creek Bed Stabilization |  |  |  | 1.125
6 | Construction Water Management |  |  |  | 0.908
7 | Support Equipment |  |  |  | 0.163
8 | Support Labour |  |  |  | 0.54
9 | Asbestos Control |  |  |  | 0.768
10 | Fuel Transportation |  |  |  | 0.009
11 | Indirects |  |  |  | 4.322
Note: Cost Breakdown in Appendix 3, Option CC-C3
Subtotal |  |  |  |  | 12.804
| EPCM |  |  |  | 1.2804
| Contingency (25%) |  |  |  | 3.5211
Total Estimated Capital Costs |  |  |  |  | 17.6055
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Replacement |  |  |  | 1.6242
2.1 | Replace 750 m Riprap-Lined Channel (Cost Breakdown in Appendix 3) | 3616000 | 45 | 100 | 1.6242
Subtotal |  |  |  |  | 3.2583
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 3.2583
Equivalent Annual Operational Costs |  |  |  |  | 0.088989
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 20.8638
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (15 km) (Cost Breakdown in Appendix 3) | 3898000 | 20 | 100 | 5.5871
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 6.6118
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 6.6118
Equivalent Annual Cost |  |  |  |  | 0.18058
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## CC-D
|  | SHEET TITLE: |  | Clinton Creek Option D LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.646
2 | Major Road Improvements |  |  |  | 3.173
3 | Waste Rock Dump Stabilization |  |  |  | 2.213
4 | Access Road Construction |  |  |  | 0.155
5 | Creek Bed Stabilization |  |  |  | 1.158
6 | Construction Water Management |  |  |  | 0.908
7 | Support Equipment |  |  |  | 0.218
8 | Support Labour |  |  |  | 0.809
9 | Asbestos Control |  |  |  | 0.788
10 | Fuel Transportation |  |  |  | 0.017
11 | Indirects |  |  |  | 5.75
Note: Cost Breakdown in Appendix 3, Option CC-D
Subtotal |  |  |  |  | 15.835
| EPCM |  |  |  | 1.5835
| Contingency (25%) |  |  |  | 4.3546
Total Estimated Capital Costs |  |  |  |  | 21.7731
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 8.5678
2.1 | Repair 12 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 1230000 | 5 | 100 | 8.5678
3 | Replacement |  |  |  | 10.5249
3.1 | Replace 2 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 1246000 | 4.1667 | 100 | 10.5249
Subtotal |  |  |  |  | 20.7268
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 20.7268
Equivalent Annual Operational Costs |  |  |  |  | 0.56609
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 42.4999
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (15 km) (Cost Breakdown in Appendix 3) | 3898000 | 20 | 100 | 5.5871
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 6.6118
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 6.6118
Equivalent Annual Cost |  |  |  |  | 0.18058
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## CC-D2
|  | SHEET TITLE: |  | Clinton Creek Option D2 LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.646
2 | Major Road Improvements |  |  |  | 3.608
3 | Waste Rock Dump Stabilization |  |  |  | 2.213
4 | Access Road Construction |  |  |  | 0.155
5 | Creek Bed Stabilization |  |  |  | 0.828
6 | Construction Water Management |  |  |  | 0.908
7 | Support Equipment |  |  |  | 0.218
8 | Support Labour |  |  |  | 0.742
9 | Asbestos Control |  |  |  | 0.79
10 | Fuel Transportation |  |  |  | 0.017
11 | Indirects |  |  |  | 5.24
Note: Cost Breakdown in Appendix 3, Option CC-D2
Subtotal |  |  |  |  | 15.365
| EPCM |  |  |  | 1.5365
| Contingency (25%) |  |  |  | 4.2254
Total Estimated Capital Costs |  |  |  |  | 21.1269
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 3.7336
2.1 | Repair 4 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 536000 | 5 | 100 | 3.7336
3 | Replacement |  |  |  | 3.1542
3.1 | Replace 2 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 1246000 | 12.5 | 100 | 3.1542
Subtotal |  |  |  |  | 8.5219
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 8.5219
Equivalent Annual Operational Costs |  |  |  |  | 0.23275
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 29.6487
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (15 km) (Cost Breakdown in Appendix 3) | 3898000 | 20 | 100 | 5.5871
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 6.6118
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 6.6118
Equivalent Annual Cost |  |  |  |  | 0.18058
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## CC-D3
|  | SHEET TITLE: |  | Clinton Creek Option D3 LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.646
2 | Major Road Improvements |  |  |  | 3.608
3 | Waste Rock Dump Stabilization |  |  |  | 2.213
4 | Access Road Construction |  |  |  | 0.22
5 | Creek Bed Stabilization |  |  |  | 1.125
6 | Construction Water Management |  |  |  | 0.91
7 | Support Equipment |  |  |  | 0.218
8 | Support Labour |  |  |  | 0.742
9 | Asbestos Control |  |  |  | 0.788
10 | Fuel Transportation |  |  |  | 0.017
11 | Indirects |  |  |  | 5.262
Note: Cost Breakdown in Appendix 3, Option CC-D3
Subtotal |  |  |  |  | 15.749
| EPCM |  |  |  | 1.5749
| Contingency (25%) |  |  |  | 4.331
Total Estimated Capital Costs |  |  |  |  | 21.6549
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
Subtotal |  |  |  |  | 1.6341
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 1.6341
Equivalent Annual Operational Costs |  |  |  |  | 0.04463
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 23.2889
Note: This is considered a walk-away solution. Therefore site access would not need to be maintained.

## CC-E
|  | SHEET TITLE: |  | Clinton Creek Option E LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.646
2 | Major Road Improvements |  |  |  | 3.719
3 | Waste Rock Dump Stabilization |  |  |  | 4.655
4 | Access Road Construction |  |  |  | 0.228
5 | Construction Water Management |  |  |  | 0.91
6 | Support Equipment |  |  |  | 0.347
7 | Support Labour |  |  |  | 0.54
8 | Asbestos Control |  |  |  | 0.81
9 | Fuel Transportation |  |  |  | 0.029
10 | Indirects |  |  |  | 5.53
Note: Cost Breakdown in Appendix 3, Option CC-E
Subtotal |  |  |  |  | 17.414
| EPCM |  |  |  | 1.7414
| Contingency (50%) |  |  |  | 9.5777
Total Estimated Capital Costs |  |  |  |  | 28.7331
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
Subtotal |  |  |  |  | 1.6341
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 1.6341
Equivalent Annual Operational Costs |  |  |  |  | 0.04463
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 30.3672
Note: This is considered a walk-away solution. Therefore site access would not need to be maintained.

## CC-E2
|  | SHEET TITLE: |  | Clinton Creek Option E2 LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.646
2 | Major Road Improvements |  |  |  | 3.719
3 | Waste Rock Dump Stabilization |  |  |  | 5.15
4 | Access Road Construction |  |  |  | 0.228
5 | Construction Water Management |  |  |  | 0.91
6 | Support Equipment |  |  |  | 0.33
7 | Support Labour |  |  |  | 0.54
8 | Asbestos Control |  |  |  | 0.802
9 | Fuel Transportation |  |  |  | 0.029
10 | Indirects |  |  |  | 5.805
Note: Cost Breakdown in Appendix 3, Option CC-E2
Subtotal |  |  |  |  | 18.159
| EPCM |  |  |  | 1.8159
| Contingency (25%) |  |  |  | 4.9937
Total Estimated Capital Costs |  |  |  |  | 24.9686
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
Subtotal |  |  |  |  | 1.6341
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 1.6341
Equivalent Annual Operational Costs |  |  |  |  | 0.04463
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 26.6027
Note: This is considered a walk-away solution. Therefore site access would not need to be maintained.

## CC-E3
|  | SHEET TITLE: |  | Clinton Creek Option E3 LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.646
2 | Major Road Improvements |  |  |  | 3.72
3 | Waste Rock Dump Stabilization |  |  |  | 5.15
4 | Access Road Construction |  |  |  | 0.24
5 | Creek Bed Stabilization |  |  |  | 0.828
6 | Construction Water Management |  |  |  | 0.91
7 | Support Equipment |  |  |  | 0.347
8 | Support Labour |  |  |  | 0.54
9 | Asbestos Control |  |  |  | 0.808
10 | Fuel Transportation |  |  |  | 0.03
11 | Indirects |  |  |  | 6.585
Note: Cost Breakdown in Appendix 3, Option CC-E3
Subtotal |  |  |  |  | 19.804
| EPCM |  |  |  | 1.9804
| Contingency (25%) |  |  |  | 5.4461
Total Estimated Capital Costs |  |  |  |  | 27.2305
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
Subtotal |  |  |  |  | 1.6341
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 1.6341
Equivalent Annual Operational Costs |  |  |  |  | 0.04463
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 28.8646
Note: This is considered a walk-away solution. Therefore site access would not need to be maintained.

## CC-F
|  | SHEET TITLE: |  | Clinton Creek Option F LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 1.049
2 | Major Road Improvements |  |  |  | 3.614
3 | Waste Rock Dump Stabilization |  |  |  | 46.55
4 | Creek Bed Stabilization |  |  |  | 1.4
5 | Construction Water Management |  |  |  | 1.84
6 | Support Equipment |  |  |  | 0.68
7 | Support Labour |  |  |  | 0.54
8 | Asbestos Control |  |  |  | 0.88
9 | Fuel Transportation |  |  |  | 0.352
10 | Indirects |  |  |  | 17.55
Note: Cost Breakdown in Appendix 3, Option CC-F
Subtotal |  |  |  |  | 74.455
| EPCM |  |  |  | 7.4455
| Contingency (25%) |  |  |  | 20.4751
Total Estimated Capital Costs |  |  |  |  | 102.3756
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 0.68916
1.1 | Visual Inspections | 15000 | 2 | 100 | 0.27122
1.2 | Surveys | 60000 | 5 | 100 | 0.41794
Subtotal |  |  |  |  | 0.68916
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 0.68916
Equivalent Annual Operational Costs |  |  |  |  | 0.018822
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 103.0648
Note: This is considered a walk-away solution. Therefore site access would not need to be maintained.

## CC-G
|  | SHEET TITLE: |  | Clinton Creek Option G LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.243
2 | Major Road Improvements |  |  |  | 3.61
3 | Bulk Excavation |  |  |  | 0.865
4 | Access Road Construction |  |  |  | 0.158
5 | Creek Bed Stabilization |  |  |  | 1.255
6 | Construction Water Management |  |  |  | 0.908
7 | Support Equipment |  |  |  | 0.163
8 | Support Labour |  |  |  | 0.54
9 | Asbestos Control |  |  |  | 0.77
10 | Fuel Transportation |  |  |  | 0.008
11 | Indirects |  |  |  | 3.58
Note: Cost Breakdown in Appendix 3, Option CC-G
Subtotal |  |  |  |  | 12.1
| EPCM |  |  |  | 1.21
| Contingency (25%) |  |  |  | 3.3275
Total Estimated Capital Costs |  |  |  |  | 16.6375
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 8.5678
2.1 | Repair 4 Gabion Drop Structures and Gabion Channel (Same as "Repair 12 Drop Structures", Cost Breakdown in Appendix 3) | 1230000 | 5 | 100 | 8.5678
3 | Replacement |  |  |  | 14.7002
3.1 | Replace 2 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 1246000 | 7.5 | 100 | 5.6059
3.2 | Replace 550 m Gabion Channel (Cost Breakdown in Appendix 3) | 4454000 | 15 | 100 | 9.0944
Subtotal |  |  |  |  | 24.9021
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 24.9021
Equivalent Annual Operational Costs |  |  |  |  | 0.68012
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 41.5396
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (15 km) (Cost Breakdown in Appendix 3) | 3898000 | 20 | 100 | 5.5871
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 6.6118
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 6.6118
Equivalent Annual Cost |  |  |  |  | 0.18058
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## CC-H
|  | SHEET TITLE: |  | Clinton Creek Option H LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.664
2 | Major Road Improvements |  |  |  | 3.631
3 | Waste Rock Dump Stabilization |  |  |  | 2.213
4 | Access Road Construction |  |  |  | 0.16
5 | Creek Bed Stabilization |  |  |  | 1.255
6 | Construction Water Management |  |  |  | 0.908
7 | Support Equipment |  |  |  | 0.273
8 | Support Labour |  |  |  | 0.54
9 | Asbestos Control |  |  |  | 0.798
10 | Fuel Transportation |  |  |  | 0.017
11 | Indirects |  |  |  | 4.898
Note: Cost Breakdown in Appendix 3, Option CC-H
Subtotal |  |  |  |  | 15.357
| EPCM |  |  |  | 1.5357
| Contingency (25%) |  |  |  | 4.2232
Total Estimated Capital Costs |  |  |  |  | 21.1159
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 8.5678
2.1 | Repair 4 Gabion Drop Structures and Gabion Channel (Same as "Repair 12 Drop Structures", Cost Breakdown in Appendix 3) | 1230000 | 5 | 100 | 8.5678
3 | Replacement |  |  |  | 7.9284
3.1 | Replace 2 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 1246000 | 12.5 | 100 | 3.1542
3.2 | Replace 550 m Gabion Channel (Cost Breakdown in Appendix 3) | 4454000 | 25 | 100 | 4.7743
Subtotal |  |  |  |  | 18.1304
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 18.1304
Equivalent Annual Operational Costs |  |  |  |  | 0.49517
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 39.2462
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (15 km) (Cost Breakdown in Appendix 3) | 3898000 | 20 | 100 | 5.5871
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 6.6118
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 6.6118
Equivalent Annual Cost |  |  |  |  | 0.18058
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## CC-I
|  | SHEET TITLE: |  | Clinton Creek Option I LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.76
2 | Major Road Improvements |  |  |  | 3.62
3 | Waste Rock Dump Stabilization |  |  |  | 3.11
4 | Access Road Construction |  |  |  | 0.22
5 | Creek Bed Stabilization |  |  |  | 1.953
6 | Support Equipment |  |  |  | 0.48
7 | Support Labour |  |  |  | 0.54
8 | Asbestos Control |  |  |  | 0.834
9 | Fuel Transportation |  |  |  | 0.03
10 | Indirects |  |  |  | 8.335
Note: Cost Breakdown in Appendix 3, Option CC-I
Subtotal |  |  |  |  | 19.882
| EPCM |  |  |  | 1.9882
| Contingency (25%) |  |  |  | 5.4675
Total Estimated Capital Costs |  |  |  |  | 27.3377
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 6.102
2.1 | Repair 8 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 876000 | 5 | 100 | 6.102
3 | Replacement |  |  |  | 6.8347
3.1 | Replace 2 Gabion Drop Structures (Cost Breakdown in Appendix 3) | 1246000 | 6.25 | 100 | 6.8347
Subtotal |  |  |  |  | 14.5707
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 14.5707
Equivalent Annual Operational Costs |  |  |  |  | 0.39795
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 41.9084
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (15 km) (Cost Breakdown in Appendix 3) | 3898000 | 20 | 100 | 5.5871
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 6.6118
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 6.6118
Equivalent Annual Cost |  |  |  |  | 0.18058
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## CC-I2
|  | SHEET TITLE: |  | Clinton Creek Option I2 LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.76
2 | Major Road Improvements |  |  |  | 3.6
3 | Waste Rock Dump Stabilization |  |  |  | 3.11
4 | Access Road Construction |  |  |  | 0.21
5 | Creek Bed Stabilization |  |  |  | 2.527
6 | Support Equipment |  |  |  | 0.5
7 | Support Labour |  |  |  | 0.81
8 | Asbestos Control |  |  |  | 0.84
9 | Fuel Transportation |  |  |  | 0.03
10 | Indirects |  |  |  | 8.82
Note: Cost Breakdown in Appendix 3, Option CC-I2
Subtotal |  |  |  |  | 21.207
| EPCM |  |  |  | 2.1207
| Contingency (25%) |  |  |  | 5.8319
Total Estimated Capital Costs |  |  |  |  | 29.1596
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
Subtotal |  |  |  |  | 1.6341
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 1.6341
Equivalent Annual Operational Costs |  |  |  |  | 0.04463
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 30.7937
Note: This is considered a walk-away solution. Therefore site access would not need to be maintained.