## September 2016
Progress Report
Date | 2016-09-16 | 2016-09-17 | 2016-09-18 | 2016-09-19 | 2016-09-20 | 2016-09-21 | 2016-09-22 |  | 2016-09-23 | 2016-09-24 | 2016-09-25 | 2016-09-26 | 2016-09-27
Activity | evening prep for Spy. | field. Deb and Graham up Congdon Creek by truck, ATV and foot to southern claim block. Up to 2 dozen sheep on slopes opposite South Spy. | field. Deb and Graham by heli to Sweet 16 showing. 20 sheep on slopes opposite. | office. Graham and Deb in D.Bay. Ron, Jean and Bill H. travelled to D.Bay. Arrived in evening | field. Graham, Ron, Jean out to Taz and then moved at 3 pm to north of Claim Post. 40-50 sheep on opposite slopes. | field. Graham, Ron, Jean out to south Spy. VLF. 10 sheep in area, | end program. Return to Whse. Weather not sutable for flying.
Soil Samples |  | 0 | 0 | 0 | 11 |  |  | 0
Rock Samples |  | 9 | 7 | 0 | 3+ |  | 0

## People 2016
name | position | 2016-09-16 | 2016-09-17 | 2016-09-18 | 2016-09-19 | 2016-09-20 | 2016-09-21 | 2016-09-22 | 2016-09-23 | 2016-09-24
Midnight Mines
Bill Harris | Manager | 2016-09-19: 0.5; 2016-09-20: 0.5; 2016-09-21: 0.5
Debbie James | Geologist/GIS | 0.5 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5
Graham Davidson | Geologist | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5
Jean Pautler | Geologist | 2016-09-19: 0.5; 2016-09-20: 1; 2016-09-21: 1; 2016-09-22: 0.5
Ron Berdahl | Prospector | 2016-09-19: 0.5; 2016-09-20: 1; 2016-09-21: 1; 2016-09-22: 0.5
Total |  | 1 | 2 | 2 | 3.5 | 4 | 4 | 2 | 0 | 0
living costs* |  | 1 | 2 | 2 | 4 | 4 | 5*** |  | 0 | 0
VLF | bar: 2016-09-21
XRF - day | bar: 2016-09-17 to 2016-09-21
trucks - day | bar: 2016-09-16 to 2016-09-22
quads - day | bar: 2016-09-16 to 2016-09-22
G. Davidson truck | bar: 2016-09-16 to 2016-09-22
assays |  | 0 | 9 | 7 | 0 | 20 | 12
helicopter |  | 2016-09-21: 3.4**
total |  | 2016-09-16: field days
* Jean in camper
**total hours up to 21st, spread over 3 days.
***Bill K hotel cost