## Sheet1
Date | Personel | Mandays | Description | Excavator Time (hrs) | ATV | Truck
2019-05-28 | Morgan | 1 | MOBILIZATION of Excavator and tools to Swede Creek HLFT | 7 | 1 | 1
2019-05-29 | Morgan | 1 | Dig, sample, reclaim SP19-001 and SP19-002. Some digging in pits that encountered permafrost and left open to thaw | 6 | 1 | 1
2019-05-30 | Morgan | 1 | Digging, sampling, reclaiming and panning SP19-001 and SP19-002 | 4 | 1 | 1
2019-05-31 | Morgan | 1 | Digging, sampling, reclaiming and panning SP19-003 and SP19-004 digging around other pits and exposing frozen ground to thaw. | 4 | 1 | 1
2019-06-01 | Morgan | 1 | Digging, sampling, reclaiming, testing, SP19-05, 06 and 07 | 4 | 1 | 1
2019-06-02 | Morgan | 1 | Dig, sample, reclaim, pan SP19-08. Opened a few other holes that were frozen and worked more on previos pits that were left to thaw. | 3 | 1 | 1
2019-06-03 | Morgan | 1 | Dig, sample, reclaim, pan SP19-09, 10, 11, 12, 13 and 14 | 3 | 1 | 1
2019-06-04 | Morgan | 1 | Dig , sample, reclaim, pan SP19-015, 16, 17 and 18. Worked a bit on already open pits that were thawing. | 4 | 1 | 1
2019-06-05 | Morgan | 1 | Prospecting for digging spots and acces on the South side of the HLFT. Dug, sampled, reclaimed and tested SP19-019 | 4 | 1 | 1
2019-06-06 | Morgan | 1 | Scouting for access and walking excavator through difficult terrain to access Empire creek ridge area. Got within 300 meters of my destination. | 4 | 1 | 1
2019-06-07 | Morgan | 1 | Finished walking excavator to ridge above Empire creek mouth. Prospected and scraped around the area. Started digging a trench to sample the shallow bedrcok gravel interface of the area. | 4 | 1 | 1
2019-06-08 | - | - | - | - | - | -
2019-06-09 | Morgan | 1 | Finished digging remainder of trench and sampling SP19-031 to 36 | 3 | 1 | 1
2019-06-10 | Morgan | 1 | Reclaimed trench area and dug, sampled, reclaimed, tested pits for SP19-037 and 038 | 4 | 1 | 1
2019-06-11 | Morgan | 1 | Walked excavator up hill and dug, sampled, reclaimed, tested SP19-039 to 044 | 4 | 1 | 1
2019-06-12 | Morgan | 1 | Walked excavator back to main trail from Empire area ridge. Slow difficult going on rough trial. Trying to leave no trace. Dug an SP19-045. Frozen a 3m but took sample anyway. Only possible sample from this area and wasn’t planning on coming back soon. | 4 | 1 | 1
2019-06-13 | Morgan | 1 | Walked excavator back to site of Shaft 1 and Pit18-01 of 2018 year to dig a deeper pit. Started clearing area to dig 2 meter hole that the excavator could get in to. | 4 | 1 | 1
2019-06-14 | Morgan | 1 | Kept clearing and digging the pit for SP19-046. took sampel and tested the sample | 4 | 1 | 1
2019-06-15 | - | - | - | - | - | -
2019-06-16 | Morgan | 1 | Walked excavator down to main20 pup road and dug pits on the way, Dug, sampled, reclaimed and tested SP19-047 and 048 | 4 | 1 | 1
2019-07-11 | Morgan | 1 | Staking Lease on Empire Creek |  | 1 | 1
2019-07-24 | Morgan | 1 | Staking claims on 20 PUP |  | 1 | 1
2019-10-08 | Morgan | 1 | Walking excavator back to Top of World highway | 6 | 1 | 1
2019-10-14 | Morgan | 1 | Demobilizing and trucking excavaotr and tools out of Swede. |  | 1 | 1
2019-10-15 | Morgan | 1 | Staking Claims on Bench of Discovery Pup. |  | 1 | 1