## TOO Cost statement
WLF 2023 Project Costs
PROJECT: WLF - WOLF
White Gold Corp
Service Providers: Groundtruth Exploration, Groundtruth Drilling, WGO, Great Slave Helicopters, Minconsult Exploration Services, BV Labs Vancouver, Tintina Air
Timeline: July 2nd - July 13th, 2023
1.0: RAB Drilling - Groundtruth Drilling, GroundTruth Exploration, Bureau Veritas, Great Slave Helicopters, Tintina Air
| Item | Service Provider | Description | YMEP Rate |  | PropertyAmount | YMEP Eligeable Expenses | Invoice #
1.1: RAB Drilling Production | Drill Production | Groundtruth Drilling | Rig Rate charged per day 8.8 days at 3500/day | 75% |  | 30800 | 23100 | INV 1148
| Weather Rate | Groundtruth Drilling | 1 day charged at $2625/day. | 75% |  | 2625 | 1968.75 | INV 1148
| Meterage Rate | Groundtruth Drilling | 300.3m at $30/meter | 75% |  | 9009 | 6756.75 | INV 1148
| Consumables | Groundtruth Drilling | Consumables: Drill bits, Drill fuel | 75% |  | 4457.63 | 3343.2225 | INV 1148, INV11094
| Sampling Technician | Groundtruth Drilling | 10.75 day units at $600/day | Technician - $350/day |  | 6450 | 3850 | INV 1148
| Drillcore sampling | Groundtruth Drilling | 300.3m at $5/meter | 75% |  | 1501.5 | 1126.125 | INV 1148
| Mobilization | Groundtruth Drilling | 24 hours at 80$/hr | 75% |  | 1920 | 1440 | INV 1148
| Field Portable XRF | Groundtruth Exploration | 9 days at $350/day | 110/day |  | 3150 | 990 | INV11055R
| Optical Televiewer | Groundtruth Exploration | 9 days at $450/day | 75% |  | 4050 | 3037.5 | INV11055R
| Drill Geologist | Groundtruth Exploration | Drillcore logging, XRF data production. 10.75 days at $850 | Technician - $350/day |  | 9137.5 | 3762.5 | INV11055R
| Drill moves Setup/Teardown of rig | Groundtruth Drilling | Per worker rate per hour when on project - 36 hours at 80$/hr | 75% |  | 2880 | 2160 | INV 1148
| Cessna 206 Charter | Tintina Air | Fly in fishing tool for OTV retrieval | Air travel within Yukon - 100% |  | 2875 | 2875 | 7958
| Total RAB Drilling Production |  |  |  |  | 78855.63 | 54409.8475
| Item | Service Provider | Description | YMEP Rate |  | PropertyAmount | YMEP Eligeable Expenses | Invoice #
1.2: Assays and Shipping | Assay costs - RAB Drilling | Bureau Veritas | Lab assay expenses: 34+60+49+64 at $54.31/sample | 100% |  | 11242.06 | 11242.06 | VANI474208, VANI475010, VANI474563, VANI474209
| Total Assays and Shipping |  |  |  |  | 11242.06 | 11242.06
| Item | Service Provider | Description | YMEP Rate |  | PropertyAmount | YMEP Eligeable Expenses | Invoice #
1.3: Helicopter, Transport, fuel | Helicopter time | Great Slave Helicopters | Transportation drill crew from Thistle Camp to WLF property, drill support, and drill moves. 39.04 hours at $1875/hour | 100% |  | 73196.3 | 73196.3 | IN010079, IN010142,IN010024, IN009901
| Fuel | AFD Petroleum Limited | Bulk fuel purchase on invoice_SI00023845 on June 06th, 2023($1.2274/L) was used to estimate fuel cost for the entire drilling program at an average burn rate of 1.25 barrels/hr or 200 L/hr and a total of 39.04 hours of flight time | 100% |  | 9583.5392 | 9583.5392 | Sales invoice_SI00023845
| Total Helicopter and Transport for RAB Drilling |  |  |  |  | 82779.8392 | 82779.8392
| Item | Service Provider | Description | YMEP Rate | Total Invoiced to WGO across all programs | PropertyAmount | YMEP Eligeable Expenses
1.4: Crew Travel | Crew Travel | Groundtruth Drilling | Travel for crew to Whitehorse and back 50% of total costs applied to WLF | 0%? Outside of yukon | 13665.59 | 6832.795 | 0 | INV 1148, INV1152
| Total RAB Drill Crew Travel to Whitehorse |  |  |  | 13665.59 | 6832.795 | 0
| 1.0: RAB Drilling - Total |  |  |  |  | 179710.3242 | 148431.7467
2.0 Pad Building - Minconsult Exploration Services, Great Slave Helicopters.
2.1: Pad Building Labour | Item | Service Provider | Description | YMEP Rate | Total Invoiced to WGO across all programs | PropertyAmount | YMEP Eligeable Expenses | Invoice #
| Employee man-days | Minconsult Exploration Services | Pad building labour - 10% of total invoiced hourly expenditures of 89,392.5 applied to WLF | $300/day (10% of 74 man-days) | 89392.5 | 8939.25 | 2220 | 10-23Jun2023WG
| Equipment Rental | Minconsult Exploration Services | 2x Fly Basket and tools - $225/day per basket, 14 days | $100/day (as per Daily field expenses) | 6300 | 630 | 280 | 10-23Jun2023WG
| Total Pad Building Labour |  |  |  | 95692.5 | 9569.25 | 2500
2.2: Helicopter | Item | Service Provider | Description | YMEP Rate |  | PropertyAmount | YMEP Eligeable Expenses | Invoice #
| Setouts and Pickups | Great Slave Helicopters | Flight time= 2.85hrs at $1875/hr | 100% |  | 5343.75 | 5343.75 | IN009799, IN009901
| Fuel | AFD Petroleum Limited | Bulk fuel purchase on invoice_SI00023845 on June 06th, 2023($1.2274/L) was used to estimate fuel cost for the entire drilling program at an average burn rate of 1.25 barrels/hr or 200 L/hr and a total of 2.85 hours of flight time | 100% |  | 699.618 | 699.618 | Sales invoice_SI00023845
| Total Helicopter support for Pad Building |  |  |  |  | 6043.368 | 6043.368
2.3: Crew Travel/Mobilization | Item | Service Provider | Description | YMEP Rate | Amount | PropertyAmount | YMEP Eligeable Expenses | Invoice #
| Vehicle Km's | Minconsult Exploration Services | Contractor Work Vehicle Mobilization to site - 335Km's at $0.62/day | $0.6/km | 207.7 | 20.77 | 21.105 | 10-23Jun2023WG
| Travel and Lodging | Minconsult Exploration Services | Hotel expenses by contractor for travel to Whitehorse | - | 5584.15 | 558.415 | 0 | 10-23Jun2023WG
| Employee travel per diem | Minconsult Exploration Services | 20 day units at $75/day | - | 1500 | 75 | 0 | 10-23Jun2023WG
| Tintina Flight to Thistle Camp | Minconsult Exploration Services | Supervan charter Whitehorse-Thistle-Whitehorse - 50% applied to WLF | 100% | 6555 | 3277.5 | 3277.5 | 6907
| Total Mobilization/Travel for Pad Building Crew |  |  |  | 13846.85 | 3931.685 | 3298.605
| 2.0:Pad Building - Total |  |  |  | 109539.35 | 19544.303 | 11841.973
2023 Wolf Expenditure Summary | [5 empty] | WLF Project Total | YMEP Eligible Expenses
| 1.1: RAB Drilling Production |  |  |  |  | 78855.63 | 54409.8475
| 1.2: Assays and Shipping |  |  |  |  | 11242.06 | 11242.06
| 1.3: Helicopter, Transport, fuel |  |  |  |  | 82779.8392 | 82779.8392
| 1.4: Crew Travel |  |  |  |  | 6832.795 | 0
| 1.0: RAB Drilling - Groundtruth Drilling, GroundTruth Exploration, Bureau Veritas, Great Slave Helicopters, Tintina Air |  |  |  |  | 179710.3242 | 148431.7467
| 2.1: Pad Building Labour |  |  |  |  | 9569.25 | 2500
| 2.2: Helicopter |  |  |  |  | 6043.368 | 6043.368
| 2.3: Crew Travel/Mobilization |  |  |  |  | 75 | 3298.605
| 2.0 Pad Building - Minconsult Exploration Services, Great Slave Helicopters. |  |  |  |  | 19544.303 | 11841.973
Total 2023 Wolf Expenditure | [5 empty] | 199254.6272 | 160273.7197
| YMEP Claim Amount |  |  |  |  | 50000

## Sheet1
2023 Toonie Expenditure Summary |  | TOO Project Total with Tax | YMEP Eligible Expenses
| 1.1: RAB Drilling Production | 58878.729 | 39421.5467
| 1.2: Assays and Shipping | 11332.9056 | 11332.9056
| 1.3: Helicopter, Transport, fuel | 74308.2182 | 74308.2182
| 1.4: Crew Travel | 7174.4505 | 0
| 1.0: RAB Drilling - Groundtruth Drilling, GroundTruth Exploration, Bureau Veritas, Great Slave Helicopters | 151694.3033 | 125062.6706
| 2.1: Pad Building Labour | 5023.8562 | 1180
| 2.2: Helicopter | 8071.875 | 8071.875
| 2.3: Crew Travel/Mobilization | 3824.1971 | 3451.425
| 2.0:Pad Building - Total | 16919.9284 | 12703.3
Total 2023 Toonie Expenditure |  | 168614.2317 | 137765.9706
YMEP Claim Amount |  | 50000